## OoG
Programme Implementation Report For The Period 2014-2015
County Government Entity:
S/No. | Name Of Project | Gps Reading | Project Cost (A) | Sub County | Location (Ward) | Name Of Company Contracted | Name Of Directors | Contacts | Project Start Date (B) | Expected Date Of Completion (C) | Project Lag-Time = (C-B) | Payments Done To Date (D) | Outstanding Amount = (A-D) | Level Of Completeion (%) | Is Project In Use? (Yes/No) | Remarks/Observations
1 | Construction Of Governor's Residence |  | 141856817 | Central | Kanamkemer | Mazeng & Const Co. Ltd | [5 empty] | 65184757 | 76672060 | 30 | No | Work On Going, Foundation And Erection Of Pilaars Done. Concrete Fencing Done. Contractor Not On Site.

## F & P
Programme Implementation Report For The Period 2014-2015
County Government Entity:
S/No. | Name Of Project | Gps Reading | Project Cost (A) | Sub County | Location (Ward) | Name Of Company Contracted | Name Of Directors | Contacts | Project Start Date (B) | Expected Date Of Completion (C) | Project Lag-Time = (C-B) | Payments Done To Date (D) | Outstanding Amount = (A-D) | Level Of Completeion (%) | Is Project In Use? (Yes/No) | Remarks/Observations
Central
1 | County Treasury Building |  | 44545369 | Central | Kanamkemer | Lomia Energy | [5 empty] | 26726426 | 17818943
2 | Citizen Resource Centre-Kerio |  | 34613328 | Central | Kerio | Edou Akide Const | [5 empty] | 24229329 | 10383999
3 | Revenue Networking |  | 35930979 | Central | Lodwar Township | Sense Network Consultants | [5 empty] | 25151685 | 10779294
Loima
1 | Lorugum Citizen Resource Centre |  | 46769510 | Loima | Turkwel | Loima Development Limited | Vinson Ekai Nang'olol | 726000000 | 3rd March,2015 |  |  | 32738657 | 14030853 | 90% | No | Building Complete But No No Office Furniture. Basketball And Lawn Tennis Court Almost Complete, Awaiting Raising Of Reems And Lawn Tennis Posts. Fence Complete.
2 | Lokiriama Revenue Generating Centre |  | 57966872 | Loima | Lokiriama/Lorengikippi | Ekori Agete Enterprise |  |  | April, 2015 |  |  | 32565456 | 25401416 | 20% | No | Fence And Washrooms Almost Complete. No Building Constructed
West
2 | 4 Blocks, 2 Units Each, Un Lokichogio Compound | N '04°12.452' E034°21.930' |  | West | Lokichogio | Rudolf Construction Co Ltd |  |  | 2015-07-15 | 2015-10-15 |  |  |  | 10% | No | Materials And Laborers On Site

## WIA
Programme Implementation Report For The Period 2014-2015
County Government Entity:
S/No. | Name Of Project | Gps Reading | Project Cost (A) | Sub County | Location (Ward) | Name Of Company Contracted | Name Of Directors | Contacts | Project Start Date (B) | Expected Date Of Completion (C) | Project Lag-Time = (C-B) | Payments Done To Date (D) | Outstanding Amount = (A-D) | Level Of Completeion (%) | Is Project In Use? (Yes/No) | Remarks/Observations
Central
1 | Drilling Of B/Hole |  | 2429600 | Central | Lodwar Township | Lake Turkana Supply | [5 empty] | 728880 | 1700720
2 | Drilling Of B/Hole |  | 2826560 | Central | Kangatotha | Lopirpira Const | [5 empty] | 847968 | 1978592
3 | Drilling Of Lolupe B/Hole |  | 2586900 | Central | Kanamkemer | Turkana B Group Link | [5 empty] | 776070 | 1810830 | 100 | No | Drilled Water Tested And Not Salite.A Waiting For Handpump.High Pressure Of Water.It Is Accessble.
4 | Drilling Of Nakalale B/Hole |  | 2263000 | Central | Kerio Delta | Magee Const | [5 empty] | 678900 | 1584100 | 0 | No
5 | Cons Of Waterpan |  | 9213474 | Central | Kanamkemer | Aluru Co. | [5 empty] | 2764042.2 | 6449431.8
6 | Cons Of Waterpan |  | 9194078.8 | Central | Kangatosa | Urum Lose Co. |  |  | 14/05/2015 | 42285 | 1 Month | 2758223.64 | 6435855.16 | 30 | No | Labours On Site.Incomplete Work,I.E Fencing And Ramping.Poor Workmanship.
7 | Cons Of Waterpan |  | 9206630 | Central | Kalokol | Sacred Ventures | [5 empty] | 2761989 | 6444641 | 80 | No | There Is No Fence.Works Is On Going.Ramping Is Not Done.There Is No Outlet To Avoid Overflow
8 | Cons Of Waterpan |  | 9199680 | Central | Lodwar Township | Kalimapus Co. | [5 empty] | 2759904 | 6439776 | 95 | No | Project Is Complete.It Contains Two Channels For The Inlet.It Is Also Fenced.
9 | Supply And Delivery Of Water Pipes |  | 25853917.25 | Central | Lodwar Township | Irrico International | [5 empty] | 15512350.35 | 10341566.9
10 | Supply Of Kapokor Hand Pump |  | 56399200 | Central | Kalokol | Silale Investment | [5 empty] | 33839520 | 22559680 | 100 | Yes | The Water Is Slightly Saline And The Borehole Is Located By The Road. The Pressure Is Moderate. The Trench Is Shallow Hence Water Overflows It. The Borehole Is Also Located Far From Settlements.
10 | Supply Of Elelea Hand Pump |  | 56399200 |  | Kanamkemer | Silale Investment | [5 empty] | 33839520 | 22559680 | 100 | Yes | Goog Access Of Water.Handpump Is Light.Substertial Pressure.Two Kilometers Radius To The Community.Slightly Saline.
12 | Construction Of Kangirisae/Katiir Water Pan |  | 13578785 | Central | Kerio | Cinoc | [5 empty] | 9505149.5 | 4073635.5 | 70 | No | No Proper Walling Of The Water-Pan.It Can Not Contain Water For Long.There Is Embakment To Prevent Soil Back To The Water-Pan.It Is Fenced.
13 | Construction Of Napuu Irrigation Project |  | 57859814.76 | Central | Kanamkemer | Ortipirro Ltd | [5 empty] | - | 57859814.76 | 50 | No | Works On Going.Fencing Of Poles In Place.Water Channels Underway.Leveling Of The Soil.Uprooting Of Stems.Tanks Stand Installed.
14 | Drilling Of Borehole |  | 2560000 | Central | Kalokol | Turkana Hardware | [5 empty] | 2560000 | - | 100 | No | High Pressure Of Water.Water Sampled For A Test. Water Test Result Not Yet Received.A Located At The River Bank.It Is Not Accessble Or Motorable.
East
1 | Morulem Borehole | N 01◦ 58.406' , E 036◦ 05.213' | 2079500 | Turkana East | Morulem (Lokori Ward) | Parakati Construction Co Ltd | [7 empty] | 0.7 | No | Drilled But They Have Not Done Pump Testing.
Loima
1 | Kabullokor Irrigation Scheme |  | 4900000 | Loima | Lobei/Kotaruk | Katome Enterprises | [5 empty] | 1470000 | 3430000 | 0.7 | Yes | No Water Running Through The Tunnel Towards The Scheme Area,Level Of Water At Turkwel River Has Gone Down
2 | Kotaruk Water Pan |  | 10264202 | Loima | Lobei/Kotaruk | Loima Enterprise | [5 empty] | 6158512.2 | 4105680.8 | 0.2 | No | Works Stalled For 3 Weeks Since End Of August,Excavator Breakdown Due To Battery,A Pan Is Far From The Beneficiries
South
1 | Kainuk Borehole | N:01° 46.796´, E:035° 30.534´ | 2524200 | T.South | Kainuk | Aropa Inv Ltd | [7 empty] | 1 | No | Borehole Drilled And Capped
| Kalapata Borehole | N:02° 19.924´, E:035° 50.742´
9 | Kaputir Water Pan
North
1 | Naduat Borehole |  | 2450000 | North | Nakalale | Ekanyarit Contractors | [7 empty] | 0.5 | No | The Borehole Has Been Drilled And Tested But It Has No Pump
2 | Waterpan Kaeris |  | 8406930 | North | Kaeris | Miebo Constr Co Ltd | [7 empty] | 0.75 | No | Not Fenced, Not Complete
3 | Borehole | 04⁰16.133'n. 035⁰47.542 | 2450000 | North | Lapur | Nabek Constructorand Supply Co Ltd | [7 empty] | 1 | Yes | The Borehole Has Been Drilled And Tested And The Pump Has Been Installed. Its Operational
4 | Waterpan |  | 9120030 | North | Lapur- Liwan | Isobel Marvel | [7 empty] | 0 | No | The Waterpan Does Not Exist According To The Ward Admin
Kibish
1 | Kibish Borehole | N 05°16.434', E 035° 47.920' |  | Kibish | Kibish | Morukoki Construction Co. Ltd | Johnstone Ekamais | [6 empty] | 0.7 | No | Project Complete But Dry Borehole. Project Abandoned.
2 | Kibish Water Pan | N 05° 03.610', E 035° 39.351' | 2534500 | Kibish | Kibish | [6 empty] | 760350 |  | 0.9 | Yes | The Project Completed And It Is In Use Though Sides Have Not Yet Completed. The Project Meets The Required Standards
West
1 | Kanakuring Waterpan | N03°59.039ʼ E034°55.993ʼ | 9120105.6 | T.West | Lopur | Kotome Enterprise | [5 empty] | 2767470 | 6457430 | 40% | No | Not Completed Shallow Tractor Not In Site
2 | Borehole Drilling Ekitela | N04°11.858ʼ E034°22.471ʼ | 2498062.3 | T.West | Lokichoggio | Lorado Const | [5 empty] | 749418.68 | 1748643.61 | 40% | No | Drilled Bt Not Fitted
3 | Borehole Drilling | N04°12.528ʼ E034°33.603ʼ | 2420000 | T.West | Nanam | Sagal Petrol Station | [5 empty] | 726000 | 1694000 | 50% | No | Not In Use Identified But Not Installed
4 | Borehole Drilling | N04°12.632ʼ E034°33.214ʼ |  | T.West | Nanam | [8 empty] | 100% | No | Installed But Not Good Not In Use No Signpost And Animal Trough
5 | Naremeto Waterpan | N04°06.064ʼ E034°22.888ʼ | 9259310 | T.West | Songot | Nawosin Construction | [5 empty] | 2777793 | 6481517 | 50% | No | Not Completed
6 | Letea Borehole | N03°30.882ʼ E034°22.464ʼ | 2560000 | T.West | Letea | Mayanda Kimoja Ent | [5 empty] | 768000 | 1748643.61 | 70% | No | No Signpost

## EDUCATION
Programme Implementation Report For The Period 2014-2015
County Government Entity:
S/No. | Name Of Project | Gps Reading | Project Cost (A) | Sub County | Location (Ward) | Name Of Company Contracted | Name Of Directors | Contacts | Project Start Date (B) | Expected Date Of Completion (C) | Project Lag-Time = (C-B) | Payments Done To Date (D) | Outstanding Amount = (A-D) | Level Of Completeion (%) | Is Project In Use? (Yes/No) | Remarks/Observations
Central
1 | Lodwar Youth Polytechnic |  | 9618200 | Central | Lodwar Township | [6 empty] | 7694560 | 1923640
2 | Turkana Cultural Centre |  | 36150000 | Central | Lodwar Township | [6 empty] | 10845000 | 25305000 | 100 | Yes | The Project Is Complete And Fenced With 3 No Gates. 4 No Main Structures For Shade And 2 No Vip Shades. Several Latrines For Men And Women. The Facility Is Connected To Electricity.
3 | Naotin Ecd |  | 6000000 | Central | Kanamkemer Ward | [6 empty] | 1800000 | 4200000
4 | Construction Of Kakemera Ecd |  | 6000000 | Central | Kanamkemer Ward | [6 empty] | 1800000 | 4200000
5 | Costruction Of Kalokutanyang Ecd |  | 5890600 | Central | Kalokutanyang | [6 empty] | 1767180 | 4123420
6 | Construction Of Impressa Ecd |  | 6000000 | Central | [7 empty] | 1800000 | 4200000
7 | Construction Of Juluk Ecd |  | 5600000 | Central | [7 empty] | 1680060 | 3919940
8 | Construction Of St.Michael Ecd |  | 6000000 | Central | Kanamkemer Ward | [6 empty] | 1800000 | 4200000
9 | Construction Of Nakwamekwi Ecd (Idp Camp) |  | 6000000 | Central | Lodwar Township | [6 empty] | 1800000 | 4200000 | 97 | No | Classroom, Kitchen And Dining Complete. It Is Fenced But With No Gate.
| Construction Of A New Ecd At Napetao |  | 6000000 | Central | Kanamkemer Ward | Gatuzi Co Ltd |  |  |  | 2015-08-15 |  | 1800000 | 4200000 | 70 | No | Works On Going. Contractor On Site. Doors, Windows, Latrines And Painting Not Yet Done.
10 | Construction Of Nakekichok Ecd |  | 6000000 | Central | Kerio Ward | Kerman Const Co Ltd | [5 empty] | 1800000 | 4200000 | 95 | No | Contractor Not On Site. Classroom Dining Latrines And Fencing Done. There Is Need For Repaiting And Construction Of A Ramp In The Dining Hall.
10 | Construction Of Nangolebei Ecd |  | 6000000 | Central | Kerio Ward | [6 empty] | 1800000 | 4200000 | 100 | Yes | Complete Structures. Secured With A Fence And Lockable Gate. The Project Location Was Changed From Nakurio To Nalongebei. The Facility Is Close To The Community.
4 | Construction Of Nameresinyen Ecd |  |  | Central | Kalokol | Kalimapus Const Co Ltd | [7 empty] | 95 | No | Project Is Complete. Black Wall To Be Constructed In The Classroom. There Is Need For The Main Gate To Me Moved Away From The Dining Hall To Creat A Conducive Environment.
10 | Construction Of Nakadukui Ecd |  | 6000000 | Central | Kangatotha Ward | Chap Chap Fishing Industry | [5 empty] | 1800000 | 4200000 | 85 | No | Poor Workmanship. Used 32 Guage Ironsheets. The Facility Is Not Fenced. Incomplete Plainting.
| Renovation Of Turkana County Ecd College |  | 18002596.8 | Central | Lodwar Township | Kerioucon Const Co Ltd |  |  | 2015-05-15 | 2015-10-15 |  |  |  | 85 | Yes | Works On Going. Partly Remaining Works Are Latrines, Drainage, Painting And Rennovation Of Floors. Contractor On Site With Adequate Labour. Fencing Done. Most Of The Works Not Captured In The Boqs.
| Constrcution Of New Ecd At Katula |  | 6000000 | Central | Kangatotha Ward | [6 empty] | 1800000 | 4200000 | 90 | Yes | Classroom, Kitchen And Dining Complete. There Are Ramps Though Not In Good Condition. There Is No Fence And The Wall Plate For The Verandar Is Wooden Hence Not Stable. There Is No Chimney In The Kitchen. Craking On The Floor As Evidence Of Poor Curing.
East
1 | Lokwamosing Ecd | N 01◦ 59.539', E 035◦ 56.201' | 6000000 | Turkana East | Lokwamosing |  |  |  | 2014 | 2015 |  | 1800000 | 4200000 | 0.98 | Yes | 1. Classroom Complete And It's In Use. Dinning Hall Also Is Complete Apart From Kitchen Works That Are On Progress.
2 | Lopeduru Ecd | N 02◦ 14.571', E 036◦ 07.567' | 6000000 | Turkana East | Lopeduru |  |  |  | 2014 | 2015 |  | 1800000 | 4200000 | 1 | No | The Project Is Complete And Not In Use. It' S Well Fenced With A Gate. Cracks On The Outside Walls Of The Dinning, Classroom And The Gate.
3 | Katilia Ecd | N 02◦ 07.432', E 036◦ 07.452' | 6000000 | Turkana East | Katilia |  |  |  | 2014 | 2015 |  | 1800000 | 4200000 | 1 | Yes | Completed Long Time And Already Been Used So Cracks Are All Over On The Floor And Blackboard Has Patches Therefore Cannot Be Written On. Pit Latrines Doors Are In Bad State.
4 | Lokorkor Ecd | N 02◦ 11.247' E 036◦ 07.325' | 6000000 | Turkana East | Lokorkor | Kacheilap Gen. Construction Co. Ltd | 1. Peter Kamais 2. Ann Abei | 720000000 | 2014 | 2015 |  | 1800000 | 4200000 | 0.8 | No | Classroom Complete And It's In Good Standard Because The Contractor As Used Quary Blocks In Construction Of The Ecd. Works At The Dinning Are Still At The Roofing Stage. Pit Latrines Are Complete. Fence And Gate In Progress.
5 | Nakwasinyen Ecd | N 02◦ 01.141' E 036◦ 04.987' | 6000000 | Turkana East | Nakwasinyen |  |  |  | 2014 | 2015 |  | 1800000 | 4200000 | 0.9 | No | Complete And Not In Use Because Kitchen Works Are Still In Progress And Also Dinning Hall And Classroom Windows Are Not Well Fitted.
Loima
1 | Lorugum Youth Polytechnic |  | 9494774 | Loima | Turkwel |  |  |  | 2015-04-15 |  |  | 2848432.2 | 6646341.8 | 55% | No | No Fence, Administration Block And Two Classrooms Complete
2 | Lokiriama Ecd |  | 6000000 | Loima | Lokiriama/Lorengikippi |  |  |  | June, 2015 | September, 2015 | 3 Months | 1800000 | 4200000 | 95% | No | No Chimney In The Kitchen, Windows Are To Be Renovated By The Contractor To Be Open, No Furniture
3 | Nakurio Ecd |  | 6000000 | Loima | Lokiriama/Lorengikippi | Nyati General Construction Limited | [5 empty] | 1800000 | 4200000 | 90% | No | Ecd Structure Not In The Normal Ecd Format. No Chimney In The Kitchen
4 | Sasak Echoke Ecd |  | 6000000 | Loima | Lobei/Kotaruk | [6 empty] | 1800000 | 4200000 | 85% | No | Fence Complete, Ecd Structure Not In The Format Of Other Ecds. Building Complete But Not In Use.
South
1 | Lokapel Ecd | N:02° 22.695´, E:035° 25.900´ | 6000000 | T.South | Katilu | [6 empty] | 1800000 | 4200000 | 100% | No | Construction Is Complete
2 | Kainuk Ecd (Primary) | N:01° 46.515´, E:035° 30.405´ | 5899950 | T.South | Kainuk | Naliapa Co.Ltd | [5 empty] | 1,769.985.00 | 4129965 | 60% | No | Project Is Ongoing
3 | Juluk/Kaputir Ecd | N:02° 09.954´, E:035° 24.558´ | 6000000 | T.South | Kaputir | Kapetangole Eng & Const Co | [5 empty] | 1680060 | 4319940 | 50% | No | Good Workmanship, Project Has Been Stalled
4 | Koputiro Ecd | N:01°46.754´, E:035° 30.054´ | 6000000 | T.South | Kainuk | Lopusky Inv.Co Ltd |  | 728748619 | 2015-04-15 |  |  | 1800000 | 4200000 | 90% | No | Construction Is Ongoing.
5 | Lokichar Youth Polythechnic | N:02° 22.145´, E:035° 38.972´ | 9910135 | T.South | Lokichar | [6 empty] | 2973040.5 | 6937094.5 | 97% | No | Construction Is Complete,No Fencing Done
6 | Lokichar Idp Ecd | N:02° 21.545´, E:035° 37.840´ | 6000000 | T.South | Lokichar | [6 empty] | 1800000 | 4200000 | 70% | No | Accesible To The Community
7 | Kangakipur Ecd | N:02° 22.487´, E:036° 01.745´ | 5899950 | T.South | Kalapata | Kalapata Const & Suppl Ltd | Jacob Akuja | 708900866 | 2015-04-15 |  |  | 1769985 | 4129965 | 80% | No | Construction Is On Finishing Stages,Construction Of The Toilet Is Ongoing
8 | Kakalel Ecd | N:02°27.770´, E:036° 05.213´ | 6000000 | T.South | Kalapata | Kaikoropus Ent Ltd | [5 empty] | 1647231 | 4352769 | 75% | No | Fencing Not Yet Done,Funtionale Lighting System
North
1 | Naduat Ecd | 03⁰30.756'n 035⁰11.966'e | 6000000 | North | Nakalale | Kuchilkuchil | Abdul Ngelecha | 713000000 | 12th March 2015 | 42186 | 2months | 3.6m | 2.4m | 95% | No | Yet To Finish Dining Hall Flour And Classrooms Window Panes
2 | Losajait Ecd | 03⁰37.273'n 035⁰18.645'e | 6000000 | North | Nakalale | Napalakipor |  |  | 42064 | 42186 |  | 3.6m | 2.4m | 100% | No | The Project Is Done And Complete
3 | Ngaurendiria Ecd | 03⁰56.47'n 035⁰15.17'e | 6000000 | North | Kaeris | Musug Const Co Ltd |  |  | 42064 | 42186 |  | 3.6m | 2.4m | 100% | Yes | The Project Is Done And Complete But The Pupils Are Not In Class Coz There Is No Food
4 | Kangakipur Ecd | 04⁰01.966'n 035⁰29.250'e | 5899950 | North | Kaeris |  |  |  | 42064 | 42186 |  |  |  | 100% | Yes | The Project Is Done And Complete
5 | Lochoredome Ecd | 04⁰15.893'n 035⁰40.218'e | 5714631 | North | Lapur |  |  |  | 42064 | 42186 |  |  |  | 100% | Yes | The Pupils Were In High Attendance, The Community Asking For Food
6 | Lochwa Arengan Ecd | 03⁰ | 5330500 | North | Lapur |  | Eregae |  | 2015-03-15 | 2015-07-15 | 3 Months | 1599150 | 3731350 | 30% | No | No Sign Of Any Activity At The Site
7 | Nabeletakoit Ecd | 03⁰ | 6000000 | North | Lakezone | Napeget Co Ltd |  |  | 2015-03-15 | 2015-07-15 | 2 Months | 3600000 | 2400000 | 95% | No
8 | Kalosep Ecd | 03⁰ | 6000000 | North | Lakezone | Nasechabuin Co Ltd |  |  | 2015-03-15 | 2015-07-15 |  | 3600000 | 2400000 | 90% | No
9 | Kataboi Youth Polytechnic | 03⁰ | 9771782 | North | Lakezone |  |  |  | 2015-03-15 |  |  | 2965753.44 | 6920091.36 | 50% |  | The Project Is At The Linthol
Kibish
1 | Koyasa Ecd | N 04 58.156', E 03529.164 |  | Kibish | Kibish |  |  |  | 2013 |  |  |  |  | 40% | No | This Project Was Started And Abandoned By The Contractor
2 | Kibish Ecd | N 05 17.117' , E 035' 49.381' |  | Kibish | Kibish |  |  |  | 2013 | 2014 |  |  |  | 100% | Yes | Project Complete And It Is In Use.
3 | Lokamarinyang Ecd | 0501.042', E 035' | 6000000 | Kibish | Kibish | Lakika Network Ltd | Dismas Abeleto |  |  |  |  | 1800000 | 4200000 | 20% | No | The Project Do Not Meet The Required Standards. Poor Workmaniship. The Project Is Turning To Be A Toilet
4 | Karubarongorok Ecd | N 0426.883' | 6000000 | Kibish | Kibish |  | Abdi Fatah |  |  |  |  | 1800000 | 4200000 | 50% | No | Project Started But Not Yet Completed

## HEALTH
Programme Implementation Report For The Period 2014-2015
County Government Entity:
S/No. | Name Of Project | Gps Reading | Project Cost (A) | Sub County | Location (Ward) | Name Of Company Contracted | Name Of Directors | Contacts | Project Start Date (B) | Expected Date Of Completion (C) | Project Lag-Time = (C-B) | Payments Done To Date (D) | Outstanding Amount = (A-D) | Level Of Completeion (%) | Is Project In Use? (Yes/No) | Remarks/Observations
Central
1 | Construction Of Namakat Dispensary |  | 7219883 | Central |  | Losidok Construction | [5 empty] | 2887953.2 | 4331929.8
2 | Cosntruction Of Louwae Dispensary |  | 7253476.12 | Central | Kerio | Lokone Emporiom | [5 empty] | 2901390.45 | 4352085.67 | 90 | No | Incomplete. Contactor Not In Site. There Is Need For Drainage System In The Staff House. Project Not Fenced.
3 | Chok Chok Dispensary |  | 6793754.6 | Central | Kangatotha | Egong Trading Co-Ltd | [5 empty] | 2717501.84 | 4076252.76 | 80 | No | Poor Workmanship. Incomplete Work. Contractor Not On Site. Project Not Fenced. No Drainage System In The Staff House. No Latrine Doors. Non Galvanized Iron Sheets Used.
4 | Naoting Dispensary |  | 7375090 | Central | Kanamkemer | Lotiruk Building Construction Ltd | [5 empty] | 2950036 | 4425054 | 90 | No | Work On Going. Main Structure Complete (Staff House & Dispensary). Toilet Not Included In The Staff House.
5 | Monti-Dispensary |  | 7429985.6 | Central |  | Lobeyi Construction Co-Ltd | [5 empty] | 2971994 | 4457991.6
6 | Nakiria Dispensary |  | 7400902 | Central | Kalokol | Mt.Loima General Construction |  |  | 2015-08-15 | 2015-09-15 |  | 2960360 | 4440542 | 90 | No | Construction Of Latrines On Going. Staff House Incomplete; No Toilet And Window Panes. Contractor On Site.
7 | Lodoket Engol Dispensary |  | 7500000 | Central | Kerio | Mankos Agencies Ltd | [5 empty] | 3000000 | 4500000 | 70 | No | Works On Going. Contractor On Site. Undone Works; Fencing, Latrines And Painting. Location Of The Staff House Inappropriate.
8 | Supply Of Equipments And Installilation Of Laundry Machine ,Oxgen Plant & X-Ray Machine |  | 85675000 | Central | Lodwar Township | Total Hospital Solution | [5 empty] | 27476759 | 58198241 | 95 | Yes | Oxygen Machine Supplied And Installed In The Oxygen Plant. Piping To Various Wards And Thearter Yet To Be Done. Laundry Machines Are In Use. Mobile X-Ray Machine Supplied And Used In Mobile Station. Ct Scan Machine Suppied And Awaits Installation.
9 | Administration Block |  | 38756050 | Central | Kanamkemer | Amata Civil Engeenering Ltd | [5 empty] | 15502420 | 23253630
| Construction Of Lolupe Dispensary |  |  | Central | Kanamkemer | Lochakai Const Co Ltd | Haji Bilal Lochakai | 727070769 | 2015-05-15 | 2015-08-15 | 1 Month |  |  | 78 | No | Works On Going. Contractor On Site. Superstructure Complete. Impressive Work.
| Construction Of Kangagete Dispensary |  |  | Central | Kangatotha | Jenalo Entreprise Ltd | [7 empty] | 85 | No | Incomplete. Contactor Not In Site.Project Not Fenced. No Latrines. Staff House Drainage Not Yet Done.
| Rennovation Works At Turkana County Hospital |  | 64577548 | Central | Lodwar Township | Lopii Construction Company Ltd | [7 empty] | 85 | Yes | The Hospital Is In Use While Rennovations Are Underway. Work On Going. Contractor On Site. Steel Doors Replaced And Painting Done. Acs And Roofing Replaced. Drainage Done And Effective.
| Construction Of Akatuman Dispensary |  | 6817133 | Central | Kangatotha | Logolei Co Ltd |  |  | 2015-05-15 |  |  |  |  | 80 | No | Incomplete Work. Contractor Not On Site. Incomplete Windows And Painting Done Partly. The Project Is Not Fenced And There Are No Latrines. No Drainage System In The Staff House. Contractor Has Not Paid Local Labourers. Type Of Iron Sheet Used Are Of Low Quality Compared With Similar Projects (Not Galvanized).
| Contruction Of Mortuary Block In Turkana County Hospital | N 05 17.142' E 35 49.441' | 37950633.8 | Central | Lodwar Township | Naita Const Co Ltd | [7 empty] | 100 | No | Project Complete Awaiting Hand Over To Clients. Parking Lot, Chapel And Fencing Done..
East
1 | Lotubae Dispensary | N 02◦ 01.507' , E 036◦ 07.544' | 7396473 | Turkana East | Lotubae | Logistic Team Investment Ltd | [5 empty] | 2958589.2 | 4437883.8 | 50% | No | It Has Not Been Completed But On Process.
2 | Elelea Construction | N 02◦ 06.883' , E 036◦ 09.178' | 10575000 | Turkana East | Elelea | Ibus Turkan Contractor | [5 empty] | 4230000 | 6345000 | 97% | No | Complete But Been Painted. Cracks On The Outside Walls And Floors
3 | Lomunyen Akwaan Dispensary | N 03◦ 07.379' , E 035◦ 36.452' | 7438585 | Turkana East | Lomunyen Akwaan (Katilia Ward) | Kakali General Supplies Ltd | [5 empty] | 2975434 | 4463151 | 10% | No | Not Started Though Few Materials On Site. Temporary Store For Construction Materials.
4 | Nakatongwa Dispensary | N 02◦ 18.791' , E 036◦ 09.576' | 7650600 | Turkana East | Nakatongwa | Joeli Build And Construction | [7 empty] | 50% | No | It Has Not Been Completed But On Process. Pit Latrines Not Constructed.
5 | Kaaruko Dispensary | N 02◦ 05.773' , E 036◦ 02.491' | 7514762 | Turkana East | Kaaruko | Natorube Co.Ltd | [7 empty] | 65% | No | It Has Not Been Completed But On Process.
Loima
1 | Turkwel Health Centre |  | 9854200 | Loima | Turkwel | Lymas Cleaning Services | [7 empty] | 40% | No | Project On-Going With An Outpatient Block,1 Staff House Already Raised.2 Pit Latrines Not Started Yet
2 | Lochor-Alomala Dispensary |  | 7332699 | Loima | Lokiriama/Lorengikippi | Perro Investment Limited | [7 empty] | 85% | No | No Fence,No Furniture And Equipment,No Electricity And Good Structure.
3 | Nakorimunyen Dispensary |  | 7350910 | Loima | Lokiriama/Lorengikippi | Aminit Suppliers & Construction | John Ekal Tioko | 728527555 | May,2015 |  |  | 2940364 | 4410546 | 40% | No | Still On-Going,No Fence And Stalled Because Of Financial Constraints
4 | Lorengkippi Dispensary |  | 7494060 | Loima | Lokiriama/Lorengikippi | Namuyan Enterprises Ltd |  |  | 7th May,2015 | 2015-07-15 | 2 Months | 7494060 |  |  | No | No Furnitures And Equipments,Staff House Complete,Good Structure
5 | Lokipetot Arengan Dispensary |  | 7459865 | Loima | Lobei/Kotaruk | Lorugum Medical Services Ltd. | [5 empty] | 7459865 |  | 90% | No | Building Complete,No Fence
6 | Lorugum Sub-District Hospital |  | 9727362 | Loima | Turkwel | Puch Building And Construction Ltd. | John Ekal Tioko | 728527555 | 2015-07-15 | 2015-12-15 | 6 Months |  |  | 70% | No | Construction Ongoing
South
1 | Kangitankori Dispensary | N:02° 26.024´, E:035° 25.667´ | 7206535 | T.South | Katilu | Nadome Const. | [6 empty] | 7206535 | 0.9 | No | Construction Is Complete,Windows Poor Done, Septic Tank Is Incomplete
2 | Lorogon Dispensary | N:01° 56 .008´, E:035° 21.690´ | 7438524 | T.South | Kaputir | Loine Inv. Ltd |  |  | 22/08/2015 |  |  |  | 7438524 | 0.4 | No | Project Is Ongoing
3 | Kakong Maternity Wing | N:02° 01.323´, E:035° 31.584´ | 7171735 | T.South | Kainuk | Kotamarukon Inv | [6 empty] | 7988967.8 | 0.8 | No | Good Workmanship, Project Has Been Stalled
4 | Loyapat Dispensary | N:01°50.187´, E:035° 28.741´ | 7988967.8 | T.South | Kainuk/ Lobokat | Adukon Trans Supplied Ltd | [6 empty] | 7988967.8 | 0.7 | No | Construction Is Ongoing.
5 | Lokichar Drug Store | N:02° 22.148´, E:035° 38.970´ | 9777327 | T.South | Lokichar | Morcat Ltd |  | 720098495 | 42125 |  |  | 3910930 | 5866397 | 0.95 | No | Construction Is Complete,No Fencing Done
6 | Lochwaa Dispensary | N:02° 34.084´, E:035° 49.615´ | 7998967 | T.South | Lokichar | Secure Africa Yok Ltd |  | 713220841 | [5 empty] | 0.65 | No
7 | Namakat Dispensary | N:02° 09.742´, E:035° 27.025´ | 7219833 | T.South | Katilu | Losidok Const. Co Ltd |  |  | 42125 | 42248 |  |  |  | 1 | No | Construction Is Complete,Good Workmanship,Finishing To Be Done
8 | Lomeleku Disp | N:02°21.807´, E:035° 56.538´ | 7438926 | T.South | Kalapata | Lokichada Const. | [7 empty] | 0.6 | No | Construction Is Ongoing.
9 | Kakalel Disp | N:02°27.071´, E:036° 04.786´ | 7438926 | T.South | Kalapata | Lokichada Const. | [7 empty] | 0.5 | No | Stalled
10 | Kekorisogol Disp | N:02°34.085´, E:035° 49.619´ | 7433118 | T.South | Lokichar | South Turkana Dev. Agency | [7 empty] | 0.6 | No | Construction Is Ongoing. Fencing Not Done.
North
1 | Lolupe Dispensary | 03⁰32.225'n 035⁰14.384'e | 7904114 | North | Nakalale | Be-Lochakai Contractors | Bilal |  | April,2015 | July,2015 | 2 Month | 3161645 | 4742469 | 0.5 | No | Not Yet Complete. No Sign Of Any Activity At The Site
2 | Kaeris Dispensary | 03⁰58.799'n. 035⁰28.938'e | 7131600 | North | Kaeris | Alsamo Ent And Contractors Co Ltd | Mohammed Ali | 711138244 | March, 2015 | July, 2015 | 2 Months |  |  | 0.95 | No | They Are Doing Wiring And Plastering The Doctors Quarters
3 | Nakitoekakumon Dispensery | 0412.22'n. 035⁰21.614'e | 7485526 | North | Kaeris | Turkana Hardware And Contractors Co | Andrew Lodio | 712759131 | May, 2015 | September, 2015 | 1 Month | 2994210.56 | 4491315.44 | 0.9 | No | Yet To Complete Plastering
4 | Karebur Dispensary | 04⁰26.123'n. 035⁰43.371'e | 7067290 | North | Lapur | Jonice Co Ltd | Eunice Ateyo |  | April, 2015 | July, 2015 | 2 Months | 2826916 | 4240374 | 80% | No
5 | Riokomor Dispensary | 04⁰06.944'n. 035⁰43.246'e | 7500000 | North | Lake Zone | Riokomor Investment Ltd | Jafer Hassan | 711205887 | April, 2015 | July, 2015 | 2 Months | 6000000 | 1500000 | 75% | No | Not Yet Complete. The Projectis At The Roofing Stage, Yet To Roof The Verandah And Fit Door And Windows And Do Plastering.
| Lokitaung Sub-County Hospital | 04⁰15.747'n. 035⁰45.260'e | 11957674 | North | Lapur | Tilak Hardware | Clement Ndiragu | 710744655 | Drug Store And Kitchen June And Renovations Mid Of May 2015 | October, 2015 |  |  |  | 70% | No | There Is So Much In Progress: Drug Store Being Constructed 60% D.One, Kicthen A About 80% Done. Renovation Of The Sub County Hospital; Repainting, Replacement Of Windows, Ceiling Boards And Door Locks
Kibish
1 | Lokamarinyang Dispensary | N 05°01.036', E 035°35675' |  | Kibish | Lokamarinyang,Kibish | [8 empty] | 40% | No | Project Started But Not Complete. Poor Workmanship
2 | Napak Dispensary | N 04°51.928', E 035°23.630' |  | Kibish | Napak,Kibish | [8 empty] | 55% | No | Project Started But The Doctor's House Has Collapsed. Poor Workmaniship
3 | Kaaleng Dispensary | N 03°07.079', E 035°36 |  | Kibish | Kaaleng | Kabarait Builders & Contractors | Eyangan Lazaro |  | 2013 | 2014 |  |  |  | 100% | Yes | Complete, In Use But It Has Not Been Officially Opened. The Project Meets The Required Standards
4 | Ekicheles Dispensary | N 04°28.675', E 035° 26. 959' | 7500000 | Kibish | Kaikor,Kibish |  | Morukori Abeleto |  | 2nd Of May 2015 |  |  | 3000000 | 4500000 | 30% | No | Project Started But Not Completed. Poor Workmaniship

## TTI
Programme Implementation Report For The Period 2014-2015
County Government Entity:
S/No. | Name Of Project | Gps Reading | Project Cost (A) | Sub County | Location (Ward) | Name Of Company Contracted | Name Of Directors | Contacts | Project Start Date (B) | Expected Date Of Completion (C) | Project Lag-Time = (C-B) | Payments Done To Date (D) | Outstanding Amount = (A-D) | Level Of Completeion (%) | Is Project In Use? (Yes/No) | Remarks/Observations
CENTRAL
| Market Stall And Toilet Project |  | 10337827.2 | Central | Lodwar Township | Seansapps Co.Ltd | [5 empty] | 3101348.1 | 7236479.1
| Construction Office Building Block |  | 19683605 | Central | Lodwar Township | Lelar Investment Ltd. | [5 empty] | 5905081.5 | 13778523.5 | 40 | No | Contactor On Site. Work Is On Going. Coulumns Have Been Done. Construction Of A Ring Beam Is Underway. Delayed Payments Are Crippling Work.
| Refurbishment Of Office Building | N 03 07.035' E 035 36.162 Elevatio 516 | 4542583 | Central | Lodwar Township | Kakurio Contractor | [5 empty] | 4542582.9 | 0.1 | 100 | Yes | 04 No Of Ac Installed. A Waiting Bay And 2 Parking Lots Constructed. Repainting Of The Office Block Done. The Office With Office Furniture. Windows, Doors And Ceiling Replaced. Thfacility Was Fenced And A Gate Erected.
| Market Stall And Toilet Project |  | 9806672 | Central | Kerio Ward | Parakati Constraction | [5 empty] | 6147140.9 | 3659531.1 | 90 | No | Market Stall Done But No Latrines. The Floor Is Rough (Finishing Not Done). Contractor Not On Site.
| Renovation Work Lodwar Market |  | 2266760 | Central | Lodwar Township | Mamren Civil And Building Const. | [5 empty] | 1360760 | 906704
| Turkwood Film Projects |  | 366797 | Central | Lodwar Township | Dopetei Systems And Design | [5 empty] | 0 | 366797
| Turkwood Film Projects |  | 843200 | Central | Lodwar Township | Northlink Productions | [5 empty] | 0 | 843200
| Co-Operatives Development Fund |  | 30000000 | Central | Lodwar Township | [6 empty] | 0 | 30000000
| Construction Of Market Stalls And Toilets |  | 10337827.2 | Central | Kalokol | Seansapps Co.Ltd | [6 empty] | 10337827.2 | 80 | No | Maket Stalls And Latrines Done. The Fence Is Not Yet Done. There Is Need For A Ramp To The Stall. The Lockable Doors Are Falling Off Hence A Need For Repair.
EAST
1 | Lokori Market Stalls | N 01◦ 57.050' , E 036◦ 01.820' | 10453259 | Turkana East | Lokori | Lelar Investments Ltd | [5 empty] | 9407933.1 | 1045325.9 | 100% | No | It Has Been Completed But Not In Use. No Pit Latrines And Not Also Fenced.
LOIMA
1 | Turkwel Market Stalls And Toilet |  | 9812539 | Loima | Turkwel | Marekai Building & Construction Ltd. |  |  | 2nd June 2015 |  |  |  |  | 95% | No | Project Complete With Stalls And Toilet,Not In Use,No Fence,Good Stalls With Tiles
2 | Renovation Work Lokiriama Market |  | 4000000 | Loima | Lokiriama/Lorengikippi | Nyati General Construction |  |  | 10th May,2015 | 10th July,2015 | 2 Months | 2400000 | 1600000 | 99% | No | Market Officially Opened On 10th September,2015 By H.E The Governor Of Turkana County,Fence Complete,Markert Structure Complete
NORTH
1 | Market Stalls And Toilet Project At Lowoarengk | 04⁰16.794'n 035⁰53.541'e | 9889006 | North | Lakezone | Lapur Trading And Investment Ltd | Hamphrey Amoni | 729000000 |  |  |  | 2966719 | 6922344.7 | 80% | No | Project At Finishing Atages, Doing Some Welding, And Yet To Paint
2 | Eco Lodge Project Kataboi | 03⁰40.644'n 035⁰49.919'e | 66389746 | North | Lakezone | Kacheilap Gen Contractors | Peter Kamais Esinyen | 720000000 | 2015-11-14 | 2015-08-15 | 6 Months | 53111797 | 13277948 | 70% | No | The Contractor Says The Challenge Is The Nature Of Soil… They Had To Take A Lot Of Time Build From Deeper Int The Ground

## PEF
Programme Implementation Report For The Period 2014-2015
County Government Entity:
S/No. | Name Of Project | Gps Reading | Project Cost (A) | Sub County | Location (Ward) | Name Of Company Contracted | Name Of Directors | Contacts | Project Start Date (B) | Expected Date Of Completion (C) | Project Lag-Time = (C-B) | Payments Done To Date (D) | Outstanding Amount = (A-D) | Level Of Completeion (%) | Is Project In Use? (Yes/No) | Remarks/Observations
Central
1 | Construction Of Feed Stores (Lodwar) |  | 9460620 | Central | Lodwar Township | Galoma Construction Ltd | [5 empty] | 2838186 | 6622434
2 | Revival Of Turkana Fisheries Cooperative Society(Tfcs) |  | 7000000 | Central | Kalokol | Kalokol Engineering | Ekai Nayam |  |  |  |  | 4200000 | 2800000 | 65 | No | Project Incomplete. Raised Walls And Roofing Done. Contractor On Site. The Facility Is Fenced With A Gate.
3 | Construction Of Fresh Fish Market |  | 9456640 | Central |  | Nakiria Co. Ltd | [6 empty] | 9456640 | 80 | No | The Project Is Incomplete And Not Yet Fenced. Contractor Not On Site.
4 | Preliminaries Of Establishment Of Lake Turkana Management Authority |  | 12153000 | Central |  | Centre For Consultancy And Training In Pastoralism | [5 empty] | 6076500 | 6076500
5 | Construction Of Multiplication And Breeding Centre |  | 29002257 | Central | Kerio | Lotulia Kor Contractors |  |  | 26/08/2015 | 2015-12-15 |  | 20301579.9 | 8700677.1 | 40 | No | Work On Going. Contractor On Site. Walls Erected For Manager House And Confrence Building. Adequate Labour.
6 | Renovation Of Kangatotha Sale Yard |  | 2449076.66 | Central | Kangatotha | Lobei Const Co Ltd | [5 empty] | 2449076.66 | 0 | 100 | Yes | Project Complete. The Community Expressed A Need Of Shade And Piping Of Water. The Space In The Gate Grills Are Too Wide To Allow Goats And Sheep Escape From The Sale Yard.
Loima
1 | Establisment Of Holding Grounds - Napeililim |  | 48774520 | Loima | Turkwel | Puch Building Construction | John Tioko Ekal | 729000000 |  |  |  | 34142164 | 14632356 | 30% | No | Project Ongoing,Project Stalled,Residents Who Worked At The Site Complained Of Delayed Payments,No Fence

## PSDDM
Programme Implementation Report For The Period 2014-2015
County Government Entity:
S/No. | Name Of Project | Gps Reading | Project Cost (A) | Sub County | Location (Ward) | Name Of Company Contracted | Name Of Directors | Contacts | Project Start Date (B) | Expected Date Of Completion (C) | Project Lag-Time = (C-B) | Payments Done To Date (D) | Outstanding Amount = (A-D) | Level Of Completeion (%) | Is Project In Use? (Yes/No) | Remarks/Observations
Central
1 | Kalokol Ward Admimistrators Office |  | 11528958 |  | Kalokol | Amana Suppliers Ltd | [5 empty] | 3458687.4 | 8070270.6 | 100 | No | The Project Is Complete With Fence And A Gate. Solar Pannels Installed And Functional.
2 | Town Ward Administrators Office |  | 10800000 |  | Lodwar Township | Ekori Kapana Investment Ltd | [5 empty] | 3240000 | 7560000 | 60 | No | Project Incomplete. Placement Of Windows And Doors Not Done Yet. Painting And Ceiling Also Not Done. Contractor Not On Site. Latrine Dug But The Structure Not Done. The Facility Has Not Been Fenced.
3 | Kanamkemer Ward Administrators Office |  | 9843272 |  | Kanamkemer | Natoot Building Construction Co Ltd |  |  | 28/04/2015 | 2015-01-07 | 2 Months | 2952981.6 | 6890290.4 | 60 | No | Works On Going. Roofing And Platering In Progress. Contractor Is On Site. Partitioning Of Rooms Done Using Blocks.
East
1 | Lokori/Kochodin Ward Admin Office | N 01◦ 57.358' , E 036◦ 02.307' | 13628214 | Turkana East | Lokori | Touchlife Co Ltd | [5 empty] | 4088464.2 | 9539749.8 | 80% | No | It Has Not Been Completed Yet. Pit Latrines Works In Progress. Fence And Gate Are Complete. Septic Tank Works In Progress
Loima
1 | Turkwel Ward Admin Office |  | 12000000.6 | Loima | Turkwel | Narina Investment Company | [5 empty] | 3600000.18 | 8400000.42 | 95% | No | Fence Is Too Short,Pit Latrines And Offices Complete,Good Structures,Project Complete
2 | Lobei/Kataruk Ward Admin.Office |  | 10028908 | Loima | Lobei/Kotaruk | Sasak Construction Co.Ltd |  |  | April,2015 |  |  | 3008672.4 | 7020235.6 | 40% | No | Fence Complete,Office Ongoing,Expected To Be Complete On Mid-October
South
1 | Kaptir Ward Admin Office | N:02° 03.639´, E:035° 25.788´ |  | T.South | Kaputir | [8 empty] | 1 | No | Construction Is Complete
2 | Kainuk Ward Office | N:01° 47.045´, E:035° 30.884´ | 9991760 | T.South | Kainuk | Echuk Contractors Co | [5 empty] | 2997528 | 6,994.232.00 | 0.4 | No | Project Has Been Stalled
3 | Kalapata Ward Office | N:02° 22.738´, E:036°01.970´ | 13209338 | T.South | Kalapata | Kodekode Cons Ltd | [7 empty] | 0.9 | No | Construction Is Complete,Plumbing Works Is Ongoing
4 | Katilu Ward Office | N:02°15.715´, E:035° 25.828´ | 11732021 | T.South | Katilu | Katilu Eng. Company | [7 empty] | 0.6 | No | Project Has Been Stalled
5 | Lokichar Ward Office | N:02° 21.802´, E:035° 38.226´ | 12052947 | T.South | Lokichar | Kasuroi Ward Office | [5 empty] | 3615884 |  | 0.8 | No | Construction Is Complete,No Fencing Done.Finishing Stages
6 | Lokichar Feed Store | N:02° 31.992´, E:036° 07.370´ | 9658280 | T.South | Lokichar | Itwan Investment Co Ltd | [7 empty] | 0.95 | No | Fencing Not Yet Done,Finishing Is Ongoing
North
1 | Nakalale Ward Admin Office | 03⁰30.907'n 035⁰13.528'e | 12228947 | North | Nakalale | Furthergur Gei Merchants | Bruno |  | 42036 | 42125 | 4months | 3668684 | 8560262.9 | 0.3 | No | There Is No Activity At The Site The Project Below The Linthol
2 | Ward Admin Office Lapur Ward | 04⁰16.013'n 035⁰45.401'e | 12900075.8 | North | Lapur | Salnel Const Ltd |  |  | 2015-02-15 | 2015-05-15 | 4 Months |  |  | 50% | No | There Is No Activity At The Site The Project At The Linthol.. There Is Material On Site
3 | Ward Admin Office Lakezone | 04⁰16.793'n 035⁰53.519'e | 13671516 | North | Lakezone | Lapur Trading & Investment Co Ltd | Humphrey Amoni |  | 2015-02-15 | 2015-05-15 | 4months | 4101454 | 9570061.9 | 80% | No | The Projectalmost Done, They Are Painting And Wiring The Building Nd Yet To Put The Tiles On Flour
Kibish
1 | Kaikor Ward Administrators Office | N 04°28.670', E 035°26.965' |  | Kibish | Kaikor | Abunyai Contractors | Abunyai |  | 2014 | 2015 |  |  |  | 100% | Yes | Complete But Not In Use. The Project Has Not Been Officially Opened
2 | Ward Adminstrators Office Napak | N 04°51.997', E 035°23.614' | 16656521 | Kibish | Napak,Kibish | Al-Sheikh Ent. Ltd | Mohammed |  |  |  |  | 4996956 |  | 60% | 60 | Project Started But Not Completed. Do Not Meet The Required Standards. Poor Workmaniship
West
1 | Kakuma Ward Administrator Office | N03°42.609ʼ E034°52.033ʼ | 11585001 | T.West | Kakuma | Rasabana Ent. Co. Ltd | [5 empty] | 3475500.3 | 8560262.9 | 0.5 | No | No Ceiling No Windows/Door No Paint No Toilet Materials On Site No Personel On Site,No Signpost And Fence
2 | Lopur Ward Administrators Office | N03°51.454ʼ E034°49.638ʼ | 11425340 | T.West | Lopur | Ekisil Co. Ltd |  |  | 27/6/2015 | 27/9/2015 |  | 3427602 | 7997738 | 0.6 | No | Signpost Not Fixed But On Site
3 | Lokichoggio Ward Administrators Office | N04°11.332ʼ E034°21.929ʼ | 13352191 | T.West | Lokichoggio | Lojam Luqa Energy Co. Ltd | [5 empty] | 4005657.3 | 9346533.7 | 0.7 | No | No Signpost Poorly Designed No Windows,Glasses,Floor Tiles,And Ceiling Plumbing,Fencingwas Done And Contractors On Site
4 | Nanam Ward Administrators Office | N04°13.003ʼ E034°33.717ʼ |  | T.West | Nanam | [8 empty] | 1 | Yes | Piping Done But No Water Source Near The Office Well Furnised Rooms, Seedling Available But Not Planted There Is No Signpost,Toilets Are Out Of Fenced Area,Good Fence And Construction Materials On Site
5 | Songot Ward Administrators Office | N04°03.097ʼ E034°31.658ʼ | 12544947 | T.West | Aposta(Songot) | Tiwae | [5 empty] | 3763484.1 | 8781462.9 | 0.5 | No | No Fence No Toilet Materials On Site Contractors Not On Site
6 | Kalobeyei Ward Administrators Office | N03°45.657ʼ E034°37.946ʼ | 12488900 | T.West | Kalobeyei | Akanpich Builders Ltd | [5 empty] | 3746670 | 8742230 | 0.6 | No | Windows/Doors To Be Fixed But On Site No Fence Materials On Site No Signpost
7 | Letea Ward Administrators Office | N03°31.312ʼ E034°48.536ʼ |  | T.West | Letea | [8 empty] | 1 | Yes | Good Fence

## ENERGY
Programme Implementation Report For The Period 2014-2015
County Government Entity:
S/No. | Name Of Project | Gps Reading | Project Cost (A) | Sub County | Location (Ward) | Name Of Company Contracted | Name Of Directors | Contacts | Project Start Date (B) | Expected Date Of Completion (C) | Project Lag-Time = (C-B) | Payments Done To Date (D) | Outstanding Amount = (A-D) | Level Of Completeion (%) | Is Project In Use? (Yes/No) | Remarks/Observations
Centrl
1 | Turkana Central Solar Project - Kapua Primary |  | 18879540 | Central | Kalokol | Turkana Salama |  |  | 2015-05-15 | 2015-05-15 |  | 7561611.99 | 11317928.01 | 100 | Yes | Pannels Installed In Boys Dorm - 4 Pannels. Staff Room - 6 Pannels. Class 5 - 2 Pannels. All Functioning.
1 | Turkana Central Solar Project - Kangirisae Primary |  | 18879540 | Central | Kerio | Turkana Salama | [5 empty] | 7561611.99 | 11317928.01 | 100 | Yes | Pannels Installed In; Class 5, 6 & 7- 8 Pannels. Girls Dorm - 2 Pannels. All Functioning
1 | Turkana Central Solar Project - Naipa Primary |  | 18879540 | Central | Kangatotha | Turkana Salama | [5 empty] | 7561611.99 | 11317928.01 | 100 | Yes | Pannels Installed In; Class 1- 2 Pannels, Class 5 - 4 Pannels. All Functioning
1 | Turkana Central Solar Project - Naoros Primary |  | 18879540 | Central | Kangatotha | Turkana Salama | [5 empty] | 7561611.99 | 11317928.01 | 100 | Yes | Pannels Installed In; Class 3- 8 Pannels And Are In Use. No Sign Post Indicating The Project.
2 | Arboretum Levelling,Waterpiping |  | 2100000 | Central | Lodwar Township | Jibu Langu Construction | [5 empty] | 1542704 | 557296
3 | Construction Of Office Block |  | 19999600 | Central | Kanamkemer | Naita Construction |  |  | 2015-06-15 | 2015-08-15 |  | 6896414 | 13103186 | 100 | No | Job Well Done
Loima
1 | Loima Solar Projects-Kotela Pry.School |  | 13524800 | Loima | Lobei/Kotaruk | Magee Construction |  | 726000000 |  |  |  | 5416937.59 | 9277180.34 | 80% | Yes | Solar Panels Have Failed To Work. Invertors Not Working Too
2 | Loima Solar Projects-Urum Primary |  | 13524800 | Loima | Lobei/Kotaruk | Magee Construction |  | 726000000 |  |  |  | 5416937.59 | 9277180.34 | 90% | Yes | The Lighting System Is Operational,The Solar Panels Have Been Fitted On One Side Of The Classroom
3 | Loima Solar Projects-Namoruputh Boys Sec |  | 13524800 | Loima | Loima | Magee Construction |  | 726000000 |  |  |  | 5416937.59 | 9277180.34 | 80% | Yes | Teachers Quarters Were Fitted With Only One Solar Panel Which Is Insufficient To Supply Electricity. Headteacher Has Requested The County Government To Supply Some More Solar Panels.
South
1 | Solar Electrification At Nakwamoru Dispensary | N:02° 03.250´, E:035° 25.874´ |  | T.South | Kaputir | Pizonas International |  |  | 2015-09-06 |  |  |  |  | 100% | Yes | Functional Solar Panels
North
1 | Solar Pv System Installation At Naduat Pry School | 03⁰30.710'n. 035⁰12.121'e |  | North | Nakalale | Lokitaung Contractors | Mark | [6 empty] | 100% | Yes | No Remarks
2 | Solar Pv System Installation At Kaeris Girls Pry School | 03⁰59.079'n. 035⁰28.812'e |  | North | Kaeris | Lokitaung Contractors Ltd | [7 empty] | 100% | Yes
3 | Solar Pv System Installation At Nariokomor Pry School. | 04⁰06.098'n. 035⁰43.147'e |  | North | Lake Zone | Lokitaung Contractors | Mark | [6 empty] | 100% | Yes
4 | Solar Pv Installation At Lomekwi Pry School | 03⁰54.796'n. 035⁰50.271'e |  | North | Lake Zone | Lokitaung Contractors | Mark | [6 empty] | 100% | Yes
West
1 | Solar System Installation | N03°53.140ʼ E034°33.665ʼ |  | T.West | Kalobeyei-Natiira | Olam Building&Supplies | [7 empty] | 100% | Yes | Solar System To Be Moved From Old Building To New
2 | Solar System Installation | N03°56.441ʼ E034°33.732ʼ |  | T.West | Kalobeyei-Lokwanyia | Olam Building&Supplies | [7 empty] | 100% | Yes | Solar System To Be Moved From Old Building To New
3 | Solar System Installation St Patrick Lomidat | N04°09.396ʼ E034°25.908ʼ |  | T.West | Songot | Olam Building&Supplies | [7 empty] | 100% | Yes | Complete And Working
4 | Solar System Installation Letea Pry School | N03°31.314ʼ E034°48.912ʼ |  | T.West | Letea | Olam Building&Supplies | [7 empty] | 100% | Yes | Complete And Working
5 | Pokotom Pry Sch Solar Installation System | N04°11.809ʼ E034°53.367ʼ |  | T.West | Kakuma | Olam Building&Supplies | [7 empty] | 100% | Yes | Complete And Working Placed Near From Trees
6 | Solar System Installation(Ecd St Mathew Nadome) | N04°06.401ʼ E034°23.351ʼ |  | T.West | Nanam | Olam Building&Supplies | [7 empty] | 50% | No | Toilet Dug But Not Constructed Materials On The Site No Solar On The Dining Hall Roofing Is Ongoing
7 | Solar System Installation Napopongoit Pry School | N04°11.720ʼ E034°23.849ʼ |  | T.West | Nanam | Olam Building&Supplies | [7 empty] | 100% | Yes | Solar System Working,No Signpost

## ROADS
Programme Implementation Report For The Period 2014-2015
County Government Entity:
S/No. | Name Of Project | Gps Reading | Project Cost (A) | Sub County | Location (Ward) | Name Of Company Contracted | Name Of Directors | Contacts | Project Start Date (B) | Expected Date Of Completion (C) | Project Lag-Time = (C-B) | Payments Done To Date (D) | Outstanding Amount = (A-D) | Level Of Completeion (%) | Is Project In Use? (Yes/No) | Remarks/Observations
Central
1 | Proposed Office Block For The Ministy |  | 27805505 | Central | Lodwar Township | Loki Builders & Const. Co Ltd | [5 empty] | 19352631.5 | 8452873.5
2 | Proposed Construction And Equiping Of Mechanical Workshop |  | 38157556.2 | Central | Lodwar Township | Sheikh Baksh Ltd | [5 empty] | 9000000 | 29157556.2
3 | Upgrading To Bitumen Standards Of Lodwar Town Roads |  | 297607727 | Central | Lodwar Township | Frontier Engineering Ltd | [5 empty] | 152532787.3 | 145074939.7
4 | Eliye Springs – Katula Routine Maintenance |  | 1590220.8 | Central | Kangatotha | Nados Construction Co.Ltd | [5 empty] | 1590220.8 | 0 | 100 | Yes | The Road Is Motorable. Substancial Work Done.
5 | Monti – Namerisinyen - Lokatukon |  | 3090281.76 | Central | Lodwar Township | Ashmmartna Constructor Co. Ltd | [5 empty] | 3090281.76 | 0
6 | Light Grading Of Kerio-Ekwar |  | 7168800 | Central | Kerio | Turkana South Com Ag Ltd | [5 empty] | 5018160 | 2150640 | 100 | Yes | Project Complete. The Road Is Motorable.
| Heavy Grading And Bush Clearing Of Nabwel-Ekorot Road |  | 2690980 | Central | Kalokol | Muruongor Const And General Supplies Ltd | [6 empty] | 2690980 | 100 | Yes | Project Complete. The Road Is Motorable. Good Workmanship.
| Bush Clearing And Light Grading Of Nabuskal-Kairiama Road |  | 3580290 | Central | Kalokol | Kablade Invest Ltd | [7 empty] | 100 | Yes | Project Complete. The Road Is Motorable.
| Heavy Grading And Bush Clearing Of Kalotum-Nachamai-Nanukumeri Road |  |  | Central | Kalokol | [8 empty] | 100 | Yes | The Road Is Motorable. Distance Not Included In The Sign Post.
| Bush Clearing And Light Grading Of Akatorongot-Kangirisae Road |  | 11910000 | Central | Kerio | Ngakomwam Contr Ltd | [7 empty] | 100 | Yes | Project Complete. The Road Is Motorable.
| Heavy Grading And Bush Clearing Of Kalokol-Airstrip Junction-Namukse Road |  | 2,545,620,00 | Central | Kalokol | Nados Construction Co.Ltd | [6 empty] | 2,545,620,00 | 100 | Yes | Project Is Complete. The Road Is Motorable.
| Spot Improvement Works At Lodwar-Kalokol-Eliye Springs Road |  | 5689800 | Central | Kangatotha | Natamakarua Eng Ltd | [7 empty] | 100 | Yes | Project Is Complete. The Road Is Motorable.
East
1 | Lopii - Kaaruko - Lokori Road | N 02◦ 03.826' , E 035◦ 52.419' | 3700700 | Turkana East | Lokori Ward | Lowatat Contractors & Suppliees Ltd | [7 empty] | 100% | Yes | It Has Been Completed. It's Well Done With Sign Post.
2 | Elelea Drift | N 02◦ 06.068' , E 036◦ 09.154' | 9628000 | Turkana East | Elelea (Katilia Ward) | Natorube Company Limited | [7 empty] | 100% | Yes | Complete And In Use. Height Level Of The Drift Is Almost The Same Level With The Sand.
3 | Spot Improvement Lokori - Napeitom Road | N 01◦ 54.892' , E 036◦ 00.380' | 23960087 | Turkana East | Lokor-Napeitom | Kataboi Investment Ltd | [5 empty] | 7188026.13 | 16772060.97 | 100% | Yes | It's Complete And In Use. No Sign Post Showing It.
4 | Lotubae-Kaesamalit Road | N 02◦ 01.186' , E 036◦ 07.722' | 3125040 | Turkana East | Lokori And Katilia Ward | Jekanas Co. Ltd | [7 empty] | 100% | Yes | Complete And In Use But No Sign Post
Loima
1 | Urum-Namoruarengan Road |  | 3800980 | Loima | Lokiriama/Lorengikippi | Apuco Holdings Group Co.Ltd |  |  | 23rd June,2015 | 10th July,2015 | 1 Month |  |  | 100% | Yes | The Road Is In Good Condition, Its Complete.
2 | Urum-Tapaik-Nacharakan Road |  | 3644256 | Loima | Lokiriama/Lorengikippi | Havana Builders Company Limited |  |  | June, 2015 | July, 2015 | 1 Month | 3279830.4 | 364425.6 | 80% | Yes | The Junction From Lokiriama-Urum Road Is Not Well Levelled. Gravelling Towards Tapaik Is Well Maintained
3 | Maintenance Of Lokwatuba-Kopetakinei Road |  | 2702800 | Loima | Lokiriama/Lorengikippi | Silale Moonlight Investment Limited |  |  | June, 2015 | July, 2015 | 1 Month |  |  | 95% | Yes | Road Has Been Maintained Well, Its Passable.
4 | Lobei-Kalapata Road |  |  | Loima | Lobei/Lotaruk | Almond Air & Logistics Limited |  |  | June, 2015 | July, 2015 | 1 Month |  |  | 90% | Yes | Road Maintenance Complete
5 | Routine Maintenance Of Nakurio-Keemanik Road |  |  | Loima | Lokiriama/Lorengikippi | Rikinei Construction Company Limited |  |  | 15th June, 2015 | 15th July, 2015 | 1 Month |  |  | 80% | Yes | Good At The Start From Lobei-Lorengikippi Road. Maintenance Towards Keemanik Centre Not Done Well.
6 | Naipa-Moruong'or Junction |  |  | Loima | Lobei/Lotaruk | Apen Investment Company |  |  | 23rd June, 2015 | 10th July, 2015 | 1 Month |  |  | 90% | Yes | Bush Clearing, Grading And Gravelling Done Well.
7 | Lorugum-Nakwasinyen-Kopeta Road |  | 7123101 | Loima | Loima Ward | Lilmark Company Limited |  |  | June, 2015 | July, 2015 | 1 Month |  |  | 75% | Yes | No Sign Post To Show The Details Of The Road Works. A Challenge Of Rivers Pose Diffuculty In Gravelling Of The Road.
8 | Napeililim-Nasogol-Lopur Road |  | 3070000 | Loima | Turkwel | Kabarait Builders & Contractors |  |  | June, 2015 | July, 2015 | 1 Month |  |  | 90% | Yes | Road Is Passable,Geavelled Well
South
1 | Lokapel Lomonyang Nakabosan Road | N:02° 22.020´, E:035° 25.484´ | 2763120 | T.South | Katilu | Katilu Engineering And Const | [5 empty] | 2486808 | 276312 | 100% | Yes | Road Completed , Well Done
2 | Kaputir Katilu Road | N:02° 05.411´, E:035° 27.578´ |  | T.South | Kaputir | [8 empty] | 100% | Yes | Road Completed , Well Done
3 | Kainuk Forest | N:01° 46.162´, E:035° 29.546´ | 1552312 | T.South | Kainuk | Ngilopechek Investment Ltd | [5 empty] | 1552312 |  | 70% | Yes | Light Grading Done
4 | Sopel-Lochwaa Road | N:02°49.039´, E:035° 36.875´ | 2107407 | T.South | Lokichar | Natotoo Ent.Limited | [7 empty] | 100% | Yes | Light Grading Done
5 | Nakaalei-Kaatir Road | N:02° 31.984´, E:036° 09.370´ | 5171280 | T.South | Kalapata | Philona Constractor |  |  | 22-06-2015 | 30-08-2015 |  |  |  | 100% | No | Heavy Grading,Gravelling And Patching
6 | Nawoiyaregae Bridge | N:02° 06.089´, E:035° 26.171´ | 95062884 | T.South | Kaptir | Naipa Building Construction |  |  | 42125 | [5 empty] | No | Building Materials Have Been Brought To The Site,Bush Clearing Done
7 | Kaekunyuk-Korinyang Road | N:02° 14.770´, E:035° 26.074´ | 2696652 | T.South | Katilu | Epae Company Limited |  |  | 22-6-2015 | 30-06-2015 |  |  |  | 100% | Yes | Road Completed , Well Done
8 | Kainuk Astu -Namambu Road | N:01°47.178´, E:035° 31.055´ | 3258150 | T.South | Kainuk | Ekobakin Co Ltd | [7 empty] | 90% | No | Light Grading Done
| Karoge Lotunguna Lokaburu | N:02°24.650´, E:035° 33.141´ | 2820120 | T.South | Lokichar | West Mint |  |  | 23-6-2015 | 2015-10-07 |  |  |  | 100% | Yes | Heavy Grading,Road Has Been Completed
9 | Lokaburu Kanaodon Road | N:02°23.656´, E:035° 25.489´ | 2635200 | T.South | Lokichar | Kaile Investment Co Ltd | [8 empty] | Yes | Light Grading Done
North
1 | Spot Improvement Makutano-Lokitaung |  | 24985820 | North | Nakalale-Lapur-Kaeris | Kare Construction Co Ltd | Francis Ethuron | 714000000 | [5 empty] | 100% | Yes | There Are Sign Posts Erected But The Road Has Been Done At Some Places And At Other Places Is Not
2 | Naurugori Losajait Road |  | 1641740 | North | Nakalale Word | Natedelim Construction Co Ltd |  |  | 2015-07-15 | 2015-10-15 |  |  |  | 100% | Yes | The Road Had Been Graded But The Soil Is Very Loose And Dusty
3 | Nakapelikuruk-Nadunga Road |  | 2847800 | North | Kaeris Ward | Moru- Edou Invest |  |  | 2015-07-15 | 2015-10-15 |  |  |  | 100% | Yes | The Road Has Been Done But Its Very Dusty….Not Passable By Vehicle That Are Not Four Wheeled
4 | Kaeris-Kalopeta Road | 03⁰37.27'n 035⁰18.645'e | 2744400 | North | Kaeris Ward | Sena Gen Construction & Supp Co Ltd |  |  | 2015-07-15 | 2015-10-15 |  |  |  | 100% | Yes | The Sign Post Is Erected And The Road Is Like It Nwas Graded Along Time Ago
5 | Sesame-Kabulkok-Karioreng Road | 04⁰30.866'n 035⁰44.843'e | 1936620 | North | Lapur Ward | Jonice Investment Ltd | Eunice |  | 2015-07-15 | 2015-10-15 |  |  |  | 5% | Yes | Nothing Has Been Done On The Road At All Except For The Signpost Erected
6 | Spot Improvement Narengewoi- Riokomor Road | 04⁰06.382'n 035⁰43.222'e | 2265480 | North | Lakezone | Nangorikitoe Inv Ltd |  |  | 2015-07-15 | 2015-10-15 |  |  |  | 100% | Yes | The Road Is Completely Done But Very Poorly Done
7 | Kachoda- Riokomor Road | 04⁰07.639'n 035⁰43.123'e | 2272788 | North | Lapur Ward | Jerman Contractors |  |  | 2015-07-15 | 2015-10-15
Kibish
1 | Kaikor- Kangakala- Lobur Road | N 04°27.987', E 035°27.786' | 3557996.8 | Kibish | Kaikor | [6 empty] | 3220197.12 | 357799.68 | 1oo% | Yes | Complete And In Use. Well Levelled.
2 | Kaikor-Lokiyoto-Loruth Road | N 04°27.237', E 035°21.058' | 3641889.8 | Kibish | Kaikor | Synchtolyte Gen. Contractors Ltd | [5 empty] | 3227701 | 364189 | 100% | Yes | Project Completed And It Is In Use. It Has Been Well Levelled.
3 | Napak- Lokulan- Natelo Road | N 04°51.851', E 035°23.238' |  | Kibish | Kibish | Lokaingole Contractors Ltd |  |  | 2014 | 12th Of Sept 2015 |  |  |  | 100% | Yes | Project Completed And It Is In Use. It Has Been Well Levelled.
4 | Lokamarinyang - Soya Road | N 05°01.140, ',E 035°35.490' |  | Kibish | Kibish | Inyang Gen. Contractors |  |  | 2014/2015 | 12th Sep 2015 |  |  |  | 30% | No | Project Started But Not Yet Completed.
West
1 | Lorengsinyon Drift | N 03°32.733ʼ E 034°48.216 |  | T.West | Letea | Nanam Construction Ltd |  |  | 28/7/2015 | 28/10/2015 |  |  |  | 40% | No | Signpost Present But Not Fixed Trenches Done And Gabion Structures Made But Not Filled
2 | Kakuma-Komudei | N 03°42.616ʼ E 034°52.069́ʼ |  | T.West | Kakuma | [8 empty] | 100% | Yes | Complete
3 | Kangitesiroi-Kanakuriny | N 03 °52.267ʼ E 034°56.105ʼ |  | T.West | Lopur | [8 empty] | 100% | Yes | No Signpost Not Well Done
4 | Lopur-Kangitesiroi | N 03°51.325́́ E 034°49.453ʼ |  | T.West | Lopur | [8 empty] | 100% | Yes | No Signpost
5 | Lomidat-Ekaburu | N04°08.144ʼ E034°26.803ʼ |  | T.West | Songot | Kaliou Contractors Ltd | [9 empty] | Not Complete Not Per Specification
6 | Teremukus-Naremeto | N04°06.269ʼ E034°27.784ʼ |  | T.West | Songot | [8 empty] | 100% | Yes | Complete
7 | Loki- Lokichar-Ekope | N04°12.386ʼ E 034°20.460ʼ | 7900000 | T.West | Lokichoggio | Lorado Contractors Ltd | [7 empty] | 100% | Yes | Insecurity
8 | Lokichar-Loruth Maintenance | N03°37.414ʼ E035°02.748 |  | T.West |  | East Africa Co. Ltd |  |  |  | 31/7/2015 |  |  |  | 100 | Yes | Clearance/No Murram/Gravel
9 | Aposta Lokangae | N04°01.046ʼ E034°32.901 |  | T.West | Songot | Lele Inv Co. Ltd |  |  | 15/11/2014 | 2015-02-02 |  | 2129760 | 1419840 | 100% | Yes
10 | Nanam-Nakaleso | N04°12.747ʼ E034°33.679ʼ |  | T.West | Nanam | Rabbi Building Cont |  |  | 2015-01-07 | 31/7/2015 |  |  |  | 100% | Yes
11 | Oropoi-Uganda Road | N03°50.900ʼ E034°34.824ʼ |  | T.West | Songot | Akajere Gen Const&Supp |  |  | 13/7/2015 | 2015-10-10 |  |  |  | 100% | Yes

## LANDS
Programme Implementation Report For The Period 2014-2015
County Government Entity:
S/No. | Name Of Project | Gps Reading | Project Cost (A) | Sub County | Location (Ward) | Name Of Company Contracted | Name Of Directors | Contacts | Project Start Date (B) | Expected Date Of Completion (C) | Project Lag-Time = (C-B) | Payments Done To Date (D) | Outstanding Amount = (A-D) | Level Of Completeion (%) | Is Project In Use? (Yes/No) | Remarks/Observations
1 | Technical Equipments For Survey And Mapping |  | 8000000 | [8 empty] | Awaiting Supply Of Survey Equipments | 8000000
2 | Establishment Of Recreational Parks And Street Naming |  | 19935371.4 | [8 empty] | Due For 30%Payment Before May,015 | 19935371.4
3 | Fencing Of Ministry Offices |  | 4930638 | [8 empty] | Due For 30%Payment Before May,015 | 4930638
4 | Establishment Of Bus Park/Terminal And Pavements |  | 14574095 | [8 empty] | Due For 30%Payment Before May,015 | 14574095
5 | Street Lights-Lodwar Town |  | 19010000 | [8 empty] | 19010000 | 0