## Sheet1
Name Of Project | Sector | Financial Year | Gps Reading | Project Cost (A) | Ward | Subcounty | Site | Contracted Company | Contacts | Project Start Date | Expected Date Of Completion | Project Lag-Time | Payments Done To Date (D) | Outstanding Amount = (A-D) | Level Of Completeion (%) | Is Project In Use? (Yes/No) | Remarks/Observations
Lokori/Kochodin Water Pan | WIA | 2014/15 | N02⁰09.194' E035⁰49.535' |  | Lokori/Kochodin | Turkana East | Katamanak | Akide | [5 empty] | 0 | 0.7 | Yes | The pan has water 30% its volume. There is evidence of silting from earlier rains. The project is not fenced.
Lokori AIC Borehole | WIA | 2013/14 | N01⁰56.620' E036⁰01.964' | 2715386 | Lokori/Kochodin | Turkana East | Lokori AIC | African B/H Company | [5 empty] | 2715386 | 1 | No | Drilling and testing done. Output 12 M³/Hr. Transferred from Katamanak. The project is to benefit Kang'itit Girls Secondary, Polytechnic, Lokori Primary School, Health Centre and part of Town.
Rehabilitation of Lokori Borehole | WIA | 2015/16 | N01⁰57.067' E036⁰01.601' |  | Lokori/Kochodin | Turkana East | Lokori | [6 empty] | 0 | 1 | No | Solar panels and pumps installed, The Bore Hole collapsed, The pannels were taken back for storage
Rehabilitation of Lokri main Borehole | WIA | 2015/16 | N01⁰57.425' E036⁰02.721' |  | Lokori/Kochodin | Turkana East | Lokori | [6 empty] | 0 | 1 | Yes | Pump and controller supplied. Solar pannels installed. Output is 12 M³/Hr. The borehole serves Lokori town.
Katilia Ward Water Pan | WIA | 2015/16 | N02⁰18.072' E036⁰07.927' |  | Katilia | Turkana East | Lopeduru | Natorube Co Ltd | [5 empty] | 0 | 1 | No | Presipitation low. Need for more inlet channels to feed the water pan. The facility is fenced with barbed wire.
Equiping of Elelea Borehole | WIA | 2015/16 | N02⁰06.659' E036⁰09.974' |  | Katilia | Turkana East | Elelea | [6 empty] | 0 | 1 | Yes | Installation of solar pump and 34 solar pannels done. Output is 15 M³/Hr. Drilling and fencing had earlier been done by World Vision. There is need for another fence. 3 solar pannels were recently stollen.
Lokori/Kochodin Borehole | WIA | 2014/15 | N01⁰58.104' E036⁰06.105' | 2473905 | Lokori/Kochodin | Turkana East | Lokwii | Parakati Con Co Ltd | [5 empty] | 2473905 | 0.8 | No | Drilling and testing done. Output 4.5 M³/Hr. Solar pump and solar pannels installed. Four pannels were recently stollen. There is need for fencing and securing the pannels with angle lines & raising them higher.
Lokori Borehole | WIA | 2015/16 | N01⁰58.411' E036⁰05.209' |  | Lokori/Kochodin | Turkana East | Nadoto | [6 empty] | 0 | 1 | No | Drilling and testing done. Output 2.2 M³/Hr.
Ngeu Borehole | WIA | 2013/14 |  | 2859150 | Katilia | Turkana East | [7 empty] | 2859150
Site No. 1 | WIA | 2013/14 |  | 2359000.35 | Katilia | Turkana East | [7 empty] | 2359000.35
Kamuge Borehole | WIA | 2013/14 |  | 2549000.4 | Lomelo/Napeitom | Turkana East | [7 empty] | 2549000.4 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Kakitei Borehole | WIA | 2013/14 |  | 2481700 | Lomelo/Napeitom | Turkana East | [7 empty] | 2481700 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Lomelo/Napeitom Water Pan | WIA | 2014/15 |  | 9622084 | Lomelo/Napeitom | Turkana East |  | Bellaack General Con & Suppliers Ltd | [5 empty] | 9622084 | 0.5 | No | The team could not visit the site for security reasons. Information from water department states that the pan stalled at 50% intended volume of work due to breaking down of the doozer. The committee rocommended the team to visit the projects.
Equiping of AIC Mission compound borehole | WIA | 2015/16 |  | 7-8 Million (Estimates) | Lokori/Kochodin | Turkana East | Lokori AIC Mission | In Tender | N/A | N/A | N/A | N/A | N/A | N/A | 0 | No | Tender advertised and opened. Evaluation and awarding to be done before 2015 Christmas break (Information from the Department of Water).
Flushing and testing of Lomelo and Napeitom Boreholes | WIA | 2015/16 |  | 2500000 | Lomelo/Napeitom | Turkana East | Lomelo and Kapedo | Bon Drillers | [7 empty] | No | Samples taken to laboratory. Survey/consultancy work on-going to inform the construction of desalination plants in both Lomelo and Kapedo. Intended beneficiaries are 4,000 (Information from the Department of Water).
Supply of water tanks at Lomelo | WIA | 2015/16 |  | 624000 | Lomelo/Napeitom | Turkana East | Lomelo | Koibos General Contractors | [7 empty] | No | 2No. 10M³ plastic tanks supplied and installed. 500No. 20-Ltrs Jeericans and 500 Kg Chlorine were to be supplied.(Information from the Department of Water).
Drilling of boreholes | WIA | 2015/16 |  | 16-17 Million (Estimates) | Lokori/Kochodin, Lomelo/Napeitom and Katilia | Turkana East |  | In Tender | N/A | N/A | N/A | N/A | N/A | N/A | 0 | No | Tender advertised and opened. Evaluation and awarding to be done before 2015 Christmas break (Information from the Department of Water).
Drilling and equiping of Napeitom borehole. | WIA | 2015/16 |  | 2465000 | Lomelo/Napeitom | Turkana East | Ngatieket | Echami Turkana Company | [8 empty] | Equiping is subject to water quality report which has not been supplied by the contractor. (Information from the Department of Water).
Equiping of Morulem Secondary Borehole with Solar Pump. | WIA | 2015/16 |  | 1928000 | Lokori/Kochodin | Turkana East | Morulem | Fountain VENT | [8 empty] | Solar pump installed. Piping and construction of the water was to be done and LSO had already been issued. (Information from the Department of Water).
Drilling and equiping of Kamuge Borehole | WIA | 2015/16 |  | 2549000 | Lomelo/Napeitom | Turkana East | Kamuge | Silale Investment Co Ltd | N/A | N/A | N/A | N/A | N/A | N/A | 0 | No | Not yet drilled. Rig failed to reach site because of steep hill. Contractor requested to source capable driller. (Information from the Department of Water).
Drilling and equiping of Nadoto Borehole | WIA | 2015/16 |  | 2473905 | Lokori/Kochodin | Turkana East | Nadoto | Parakati Con Co Ltd | [8 empty] | Borehole drilled but dry. Contractor requested to look for an alternative site. (Information from the Department of Water).
(Information from the Department of Water).
Construction of Lokicheda ECD | Education | 2013/14 | N02⁰05.814' E035⁰35.518' | 3500000 | Lokori/Kochodin | Turkana East | Lokicheda | Etich Bon Co Ltd |  | 41640 | 41730 |  | 3500000 | 0 | 0.9 | Yes | Classroom, Dining Hall and Kitchen complete. Need for supply of furniture. Floor needs rescreeding. Latrines 40% complete (Walling on going). Need for water connection to the ECD (Water tank within the school compound). Client to follow up with the project manager.
Construction of Lokwamosing ECD | Education | 2014/15 | N01⁰59.544' E035⁰56.215' | 6000000 | Lokori/Kochodin | Turkana East | Lokwamosing | Ummatul Rahma Const |  | 42125 | 42401 |  | 6000000 | 0 | 1 | Yes | Construction of main structures complete. One more coat of paint needed. Fencing done. Project not yet handed over. The ECD is within a school compound and there is need for a urinal & more latrines for girls.
Construction of Lopeduru ECD | Education | 2014/15 | N02⁰14.520' E036⁰07.586' | 6000000 | Katilia | Turkana East | Lopeduru | Lochar Emayan Contractors |  | 42125 | 42401 |  | 3600000 | 2400000 | 1 | Yes | Classroom, Dining Hall, Kitchen and Toilets done. The facility also has a gated fence. There need of clearing the site after construction to minimise injuries on pupils. The sinks for hand washing at the latrines well done. There is need for applying red oxide and ramping the strucutres to allow accessibility for all. It is located close to Lopeduru primary school. The contractor should clear the project site.
Construction of Lokorkor ECD | Education | 2014/15 | N02⁰14.519' E036⁰07.582' | 6000000 | Katilia | Turkana East | Lokorkor | Kachilap Co Ltd |  | 42125 | 42401 |  | 6000000 | 0 | 1 | Yes | Classroom, Dining Hall, Kitchen and Toilets done. Need for running water in the facility. The classroom windows do not meet the safety standards. Need for ventilation louvres.
Construction of Katilia ECD | Education | 2013/14 | N02⁰11.246' E036⁰07.324' | 3500000 | Katilia | Turkana East | Katilia |  |  | 41640 | 41730 |  | 3500000 | 0 | 1 | Yes | Classroom, Dining Hall, Kitchen and Toilets done. There is evidence of poor workmanship (paint falling off and floor scrapped). The Dinning Hall is not child friendly. There is need for repairs. Class in use but the Dinning is not functional (used as a dormitory for Katilia primary school). The facility is recomended for additional works.
Construction of Elelea ECD | Education | 2013/14 | N02⁰06.427' E036⁰09.795' | 3500000 | Katilia | Turkana East | Elelea | Katilu Builders & Construction |  | 41640 | 41730 |  |  | 3500000 | 1 | Yes | Classroom, Dining Hall, Kitchen and Toilets done. The Dinning Hall floor is pealling off. There is need for equiping the facility with furniture. The classroom needs ceilling. The facility is also not fenced and there is no running water within. The client to forward the project to project manager for follow up.
Construction of Morulem ECD | Education | 2014/15 | N02⁰01.143' E036⁰04.994' | 6000000 | Lokori/Kochodin | Turkana East | Nakwasinyen | Etau Build & Const Ltd |  | 42125 | 42401 |  | 6000000 | 0 | 1 | Yes | Project is complete and ready for commisioning. Poor accessibilty to the facility.
Construction of Nayanae Katon ECD | Education | 2013/14 | N02⁰03.013' E036⁰07.829' | 3500000 | Katilia | Turkana East | Nayanae Katwan | Etich Bon Co Ltd |  | 41640 | 41730 |  |  | 3500000 | 1 | Yes | Project is complete and ready for commisioning.
Construction of Napeitom ECD | Education | 2013/14 |  | 3500000 | Kapedo/Napeitom | Turkana East |  |  |  | 41640 | 41730 |  |  | 3500000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Construction of Kapedo ECD | Education | 2013/14 |  | 3500000 | Kapedo/Napeitom | Turkana East | Kapedo | Silale Investment Ltd |  | 41640 | 41730 |  |  | 3500000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Construction of Lokidongoi ECD | Education | 2014/15 |  | 6000000 | Kapedo/Napeitom | Turkana East |  |  |  | 42125 | 42401 |  |  | 6000000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Construction of Silale ECD | Education | 2014/15 |  | 6000000 | Kapedo/Napeitom | Turkana East |  |  |  | 42125 | 42401 |  |  | 6000000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Lokori Market Stalls | TTI | 2015/16 | N01⁰57.051' E035⁰01.830' | 10453259 | Lokori/Kochodin | Turkana East | Lokori Town | Lelar Inv Ltd |  |  |  |  | 10453259 | 0 | 1 | No | Project complete. Recommended for water connection, fencing, gate, toilet and a rubbish pit. Need for a revenue collection and revenue enforcement offices.
Lokori Ward Administrator's Office | PSDDM | 2015/16 | N01⁰57.106' E036⁰01.530' |  | Lokori/Kochodin | Turkana East | Lokori Town | [7 empty] | 0.75 | No | Main works with undercoat paint done. Fencing and drainage also done. Placing of floor tiles on going.
Katilia Ward Administrator's Office | PSDDM | 2015/16 | N02⁰07.428' E036⁰07.459' |  | Katilia | Turkana East | Katilia Town | Touchlife Co Ltd | [6 empty] | 1 | No | Construction complete. Furniture supplied. The office is ready for use. There is need for clearing of site.
Turkana East
Construction of Lopeduru Dispensary | Health | 2013/14 | N01⁰57.106' E036⁰01.530' | 6900000 | Katilia | Turkana East | Lopeduru | Achuma Contractors Ltd |  | 41791 | 42125 |  | 6900000 | 0 | 1 | Yes | Construction complete and serves an average of 25 patients per day. The medical staff include 2 nurses and 1 volunteer. There is need for equiping the facility with requisite equipments, running water and a fence. Notable defects; veranndar steel pillars are not holding the roof, poor ventilation in the maternity. Client to correct the defects.
Construction of staff quarters at Elelea Sub County Hospital | Health | 2014/15 | N02⁰06.887' E036⁰09.171' | 10575000 | Katilia | Turkana East | Elelea | Ibus Turkan |  |  |  |  | 7402500 | 3172500 | 0.9 | No | 4 units staff houses complete with 2 units of latrines. Piping for water connection on going. There is need for fencing the facility. There is also a pressing need for more staff houses to accommodate the 12 staff members serving the facility.
Lotubae Dispensary | Health | 2014/15 | N02⁰01.514' E036⁰07.541' | 7396473 | Lokori/Kochodin | Turkana East | Lotubae | Logistics Team Int Ltd |  |  |  |  | 5177531.1 | 2218941.9 | 0.8 | No | Part roofing for the dispensary done. Roofing for staff house complete. Steel windows and doors fitted. Escavation of the latrine done. The contractor was not on site. Project manager to follow up
Construction of Lokwii Dispensary | Health | 2013/14 | N01⁰58.637' E036⁰06.327' | 9800000 | Lokori/Kochodin | Turkana East | Lokwii | Kodekode Contractors |  | 41791 | 42125 |  | 9800000 | 0 | 1 | Yes | The project is complete and commissioned. Maternity, Antenatal and Postnatal wings are in use. The facility is powered with solar energy and serves an average of 5-50 patients per day. The staff members comprise of 1 In Charge, 1 Clinical Officer, 2 Nurses and 1 CHEW.
Elelea Sub County Hospital | Health | 2013/14 | N02⁰06.903' E036⁰09.111' | 2900000 | Katilia | Turkana East | Elelea |  |  | 41791 | 42125 |  | 2900000 | 0 | 1 | Yes | Completion works to the ESP modle Health centre. The hospital attends to an average of 30 patients per day. Staff members comprises of 3 Nurses, 2 Clinical Officers, 1 Medical Officers, 1 CHEW, 1 Volunteer and 2 Personal Assistants. By the time of the visit, the outreach programme had stopped for a month and the effect had already been felt.
Lomelo Dispensary | Health | 2013/14 |  | 9800000 | Lomelo/Napeitom | Turkana East |  |  |  | 41791 | 42125 |  |  | 9800000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the project.
Napeitom Dispensary | Health | 2014/15 |  | 7400902 | Lomelo/Napeitom | Turkana East | [7 empty] | 7400902 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the project.
Nakatongwa Dispensary | Health | 2015/16 |  | 7650600 |  | Turkana East |  | Joeli Contractors | [5 empty] | 7650600 |  |  | The team could not trace exact location of the dispensary.
Kikeunae Dispensary | Health | 2015/16 |  | 7411320 |  | Turkana East |  | Ngapenderee | [5 empty] | 7411320
Lomunyan Akwaan Dispensary | Health | 2015/16 |  |  |  | Turkana East | [7 empty] | 0
Turkana East
Construction of Elelea - Katilia Road | Roads | 2014/15 | N02⁰07.831' E036⁰07.040' | 9628000 | Katilia | Turkana East | Katilia - Elelea | Natoot Co Ltd |  |  |  |  | 6739600 | 2888400 | 1 | Yes | Project complete and the road is motorable.
Construction of Elelea Drift | Roads | 2014/15 | N02⁰06.073' E036⁰09.149' | 6239988 | Katilia | Turkana East | Elelea | Natorobee Co Ltd |  |  |  |  | 4367991.6 | 1871996.4 | 1 | Yes | Project complete. There is need for embarkment down stream.
Routine maintenance of Lokwamosing/Kakongu Road | Roads | 2014/15 | N02⁰00.628' E035⁰55.296' | 5868440 | Lokori/Kochodin | Turkana East | Lokwamosing - Kakongu | Turkana General Co Ltd |  |  |  |  | 4107908 | 1760532 | 1 | Yes | Project complete and the road is motorable.
Routine maintenance of Lopii - Kaaruko - Lokori Road | Roads | 2014/15 | N02⁰03.820' E035⁰52.421' | 4200000 | Lokori/Kochodin | Turkana East | Lopii-Kaaruko-Lokori | Lowatat Contractors & Supplies Ltd |  |  |  |  | 2940000 | 1260000 | 1 | Yes | Project complete and the road is motorable.
Lotudae-Kaesamalit Road | Roads | 2014/15 |  | 3125040 | Katilia | Turkana East | Lotudae-Kaesamalit | Jekanas Contractors & Supplies Company Ltd. |  |  |  |  | 2187528 | 937512 | 1 | Yes | The team could not locate the road but the information from the Department states that the project is complete.
Kamuge Drift | Roads | 2014/15 |  | 7004399 | Lomelo/Napeitom | Turkana East | Kamuge | Suguta Building Contractors & Transporters Co Ltd |  |  |  |  | 2101319.7 | 4903079.3 |  |  | The team could not visit the site for security reasons. However, information from the department states that the project is on-going.
Kamuge - Baragoi | Roads | 2014/15 |  | 12876400 | Lomelo/Napeitom | Turkana East | Kamuge - Baragoi | [6 empty] | 12876400 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Lokori - Paragati | Roads | 2014/15 |  | 7934400 | Lokori/Kochodin | Turkana East | Lokori - Paragati | [6 empty] | 7934400 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Lomelo - Kamuge | Roads | 2014/15 |  | 11564040 | Lomelo/Napeitom | Turkana East | Lomelo - Kamuge | [6 empty] | 11564040 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Kamuge - Baragoi | Roads | 2014/15 |  | 4902160 | Lomelo/Napeitom | Turkana East | Kamuge - Baragoi | Nakuru Machinery |  |  |  |  | 1960864 | 2941296 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Construction Of Namakat Dispensary | Health | 2014/15 |  | 7219883 |  | Central |  | Losidok Construction |  |  |  |  | 2887953.2 | 4331929.8
Cosntruction Of Louwae Dispensary | Health | 2014/15 |  | 7253476.12 | Kerio | Central |  | Lokone Emporiom |  |  |  |  | 2901390.45 | 4352085.67 | 90 | No | Incomplete. Contactor Not In Site. There Is Need For Drainage System In The Staff House. Project Not Fenced.
Chok Chok Dispensary | Health | 2014/15 |  | 6793754.6 | Kangatotha | Central |  | Egong Trading Co-Ltd |  |  |  |  | 2717501.84 | 4076252.76 | 80 | No | Poor Workmanship. Incomplete Work. Contractor Not On Site. Project Not Fenced. No Drainage System In The Staff House. No Latrine Doors. Non Galvanized Iron Sheets Used.
Naoting Dispensary | Health | 2014/15 |  | 7375090 | Kanamkemer | Central |  | Lotiruk Building Construction Ltd |  |  |  |  | 2950036 | 4425054 | 90 | No | Work On Going. Main Structure Complete (Staff House & Dispensary). Toilet Not Included In The Staff House.
Monti-Dispensary | Health | 2014/15 |  | 7429985.6 |  | Central |  | Lobeyi Construction Co-Ltd |  |  |  |  | 2971994 | 4457991.6
Nakiria Dispensary | Health | 2014/15 |  | 7400902 | Kalokol | Central |  | Mt.Loima General Construction |  | 42231 | 42262 |  | 2960360 | 4440542 | 90 | No | Construction Of Latrines On Going. Staff House Incomplete; No Toilet And Window Panes. Contractor On Site.
Lodoket Engol Dispensary | Health | 2014/15 |  | 7500000 | Kerio | Central |  | Mankos Agencies Ltd |  |  |  |  | 3000000 | 4500000 | 70 | No | Works On Going. Contractor On Site. Undone Works; Fencing, Latrines And Painting. Location Of The Staff House Inappropriate.
Supply Of Equipments And Installilation Of Laundry Machine ,Oxgen Plant & X-Ray Machine | Health | 2014/15 |  | 85675000 | Lodwar Township | Central |  | Total Hospital Solution |  |  |  |  | 27476759 | 58198241 | 95 | Yes | Oxygen Machine Supplied And Installed In The Oxygen Plant. Piping To Various Wards And Thearter Yet To Be Done. Laundry Machines Are In Use. Mobile X-Ray Machine Supplied And Used In Mobile Station. Ct Scan Machine Suppied And Awaits Installation.
Administration Block | Health | 2014/15 |  | 38756050 | Kanamkemer | Central |  | Amata Civil Engeenering Ltd |  |  |  |  | 15502420 | 23253630
Construction Of Lolupe Dispensary | Health | 2014/15 |  |  | Kanamkemer | Central |  | Lochakai Const Co Ltd | 727070769 | 42139 | 42231 | 1 Month |  |  | 78 | No | Works On Going. Contractor On Site. Superstructure Complete. Impressive Work.
Construction Of Kangagete Dispensary | Health | 2014/15 |  |  | Kangatotha | Central |  | Jenalo Entreprise Ltd | [6 empty] | 85 | No | Incomplete. Contactor Not In Site.Project Not Fenced. No Latrines. Staff House Drainage Not Yet Done.
Rennovation Works At Turkana County Hospital | Health | 2014/15 |  | 64577548 | Lodwar Township | Central |  | Lopii Construction Company Ltd | [6 empty] | 85 | Yes | The Hospital Is In Use While Rennovations Are Underway. Work On Going. Contractor On Site. Steel Doors Replaced And Painting Done. Acs And Roofing Replaced. Drainage Done And Effective.
Construction Of Akatuman Dispensary | Health | 2014/15 |  | 6817133 | Kangatotha | Central |  | Logolei Co Ltd |  | 42139 |  |  |  |  | 80 | No | Incomplete Work. Contractor Not On Site. Incomplete Windows And Painting Done Partly. The Project Is Not Fenced And There Are No Latrines. No Drainage System In The Staff House. Contractor Has Not Paid Local Labourers. Type Of Iron Sheet Used Are Of Low Quality Compared With Similar Projects (Not Galvanized).
Contruction Of Mortuary Block In Turkana County Hospital | Health | 2014/15 | N 05 17.142' E 35 49.441' | 37950633.8 | Lodwar Township | Central |  | Naita Const Co Ltd | [6 empty] | 100 | No | Project Complete Awaiting Hand Over To Clients. Parking Lot, Chapel And Fencing Done..
| Health | 2014/15
Lotubae Dispensary | Health | 2014/15 | N 02◦ 01.507' , E 036◦ 07.544' | 7396473 | Lotubae | Turkana East |  | Logistic Team Investment Ltd |  |  |  |  | 2958589.2 | 4437883.8 | 0.5 | No | It Has Not Been Completed But On Process.
Elelea Construction | Health | 2014/15 | N 02◦ 06.883' , E 036◦ 09.178' | 10575000 | Elelea | Turkana East |  | Ibus Turkan Contractor |  |  |  |  | 4230000 | 6345000 | 0.97 | No | Complete But Been Painted. Cracks On The Outside Walls And Floors
Lomunyen Akwaan Dispensary | Health | 2014/15 | N 03◦ 07.379' , E 035◦ 36.452' | 7438585 | Lomunyen Akwaan (Katilia Ward) | Turkana East |  | Kakali General Supplies Ltd |  |  |  |  | 2975434 | 4463151 | 0.1 | No | Not Started Though Few Materials On Site. Temporary Store For Construction Materials.
Nakatongwa Dispensary | Health | 2014/15 | N 02◦ 18.791' , E 036◦ 09.576' | 7650600 | Nakatongwa | Turkana East |  | Joeli Build And Construction | [6 empty] | 0.5 | No | It Has Not Been Completed But On Process. Pit Latrines Not Constructed.
Kaaruko Dispensary | Health | 2014/15 | N 02◦ 05.773' , E 036◦ 02.491' | 7514762 | Kaaruko | Turkana East |  | Natorube Co.Ltd | [6 empty] | 0.65 | No | It Has Not Been Completed But On Process.
| Health | 2014/15
Turkwel Health Centre | Health | 2014/15 |  | 9854200 | Turkwel | Loima |  | Lymas Cleaning Services | [6 empty] | 0.4 | No | Project On-Going With An Outpatient Block,1 Staff House Already Raised.2 Pit Latrines Not Started Yet
Lochor-Alomala Dispensary | Health | 2014/15 |  | 7332699 | Lokiriama/Lorengikippi | Loima |  | Perro Investment Limited | [6 empty] | 0.85 | No | No Fence,No Furniture And Equipment,No Electricity And Good Structure.
Nakorimunyen Dispensary | Health | 2014/15 |  | 7350910 | Lokiriama/Lorengikippi | Loima |  | Aminit Suppliers & Construction | 728527555 | May,2015 |  |  | 2940364 | 4410546 | 0.4 | No | Still On-Going,No Fence And Stalled Because Of Financial Constraints
Lorengkippi Dispensary | Health | 2014/15 |  | 7494060 | Lokiriama/Lorengikippi | Loima |  | Namuyan Enterprises Ltd |  | 7th May,2015 | 42200 | 2 Months | 7494060 |  |  | No | No Furnitures And Equipments,Staff House Complete,Good Structure
Lokipetot Arengan Dispensary | Health | 2014/15 |  | 7459865 | Lobei/Kotaruk | Loima |  | Lorugum Medical Services Ltd. |  |  |  |  | 7459865 |  | 0.9 | No | Building Complete,No Fence
Lorugum Sub-District Hospital | Health | 2014/15 |  | 9727362 | Turkwel | Loima |  | Puch Building And Construction Ltd. | 728527555 | 42200 | 42353 | 6 Months |  |  | 0.7 | No | Construction Ongoing
| Health | 2014/15
Kangitankori Dispensary | Health | 2014/15 | N:02° 26.024´, E:035° 25.667´ | 7206535 | Katilu | Turkana South |  | Nadome Const. | [5 empty] | 7206535 | 0.9 | No | Construction Is Complete,Windows Poor Done, Septic Tank Is Incomplete
Lorogon Dispensary | Health | 2014/15 | N:01° 56 .008´, E:035° 21.690´ | 7438524 | Kaputir | Turkana South |  | Loine Inv. Ltd |  | 22/08/2015 |  |  |  | 7438524 | 0.4 | No | Project Is Ongoing
Kakong Maternity Wing | Health | 2014/15 | N:02° 01.323´, E:035° 31.584´ | 7171735 | Kainuk | Turkana South |  | Kotamarukon Inv | [5 empty] | 7988967.8 | 0.8 | No | Good Workmanship, Project Has Been Stalled
Loyapat Dispensary | Health | 2014/15 | N:01°50.187´, E:035° 28.741´ | 7988967.8 | Kainuk/ Lobokat | Turkana South |  | Adukon Trans Supplied Ltd | [5 empty] | 7988967.8 | 0.7 | No | Construction Is Ongoing.
Lokichar Drug Store | Health | 2014/15 | N:02° 22.148´, E:035° 38.970´ | 9777327 | Lokichar | Turkana South |  | Morcat Ltd | 720098495 | 42125 |  |  | 3910930 | 5866397 | 0.95 | No | Construction Is Complete,No Fencing Done
Lochwaa Dispensary | Health | 2014/15 | N:02° 34.084´, E:035° 49.615´ | 7998967 | Lokichar | Turkana South |  | Secure Africa Yok Ltd | 713220841 | [5 empty] | 0.65 | No
Namakat Dispensary | Health | 2014/15 | N:02° 09.742´, E:035° 27.025´ | 7219833 | Katilu | Turkana South |  | Losidok Const. Co Ltd |  | 42125 | 42248 |  |  |  | 1 | No | Construction Is Complete,Good Workmanship,Finishing To Be Done
Lomeleku Disp | Health | 2014/15 | N:02°21.807´, E:035° 56.538´ | 7438926 | Kalapata | Turkana South |  | Lokichada Const. | [6 empty] | 0.6 | No | Construction Is Ongoing.
Kakalel Disp | Health | 2014/15 | N:02°27.071´, E:036° 04.786´ | 7438926 | Kalapata | Turkana South |  | Lokichada Const. | [6 empty] | 0.5 | No | Stalled
Kekorisogol Disp | Health | 2014/15 | N:02°34.085´, E:035° 49.619´ | 7433118 | Lokichar | Turkana South |  | South Turkana Dev. Agency | [6 empty] | 0.6 | No | Construction Is Ongoing. Fencing Not Done.
| Health | 2014/15
Lolupe Dispensary | Health | 2014/15 | 03⁰32.225'n 035⁰14.384'e | 7904114 | Nakalale | Turkana North |  | Be-Lochakai Contractors |  | April,2015 | July,2015 | 2 Month | 3161645 | 4742469 | 0.5 | No | Not Yet Complete. No Sign Of Any Activity At The Site
Kaeris Dispensary | Health | 2014/15 | 03⁰58.799'n. 035⁰28.938'e | 7131600 | Kaeris | Turkana North |  | Alsamo Ent And Contractors Co Ltd | 711138244 | March, 2015 | July, 2015 | 2 Months |  |  | 0.95 | No | They Are Doing Wiring And Plastering The Doctors Quarters
Nakitoekakumon Dispensery | Health | 2014/15 | 0412.22'n. 035⁰21.614'e | 7485526 | Kaeris | Turkana North |  | Turkana Hardware And Contractors Co | 712759131 | May, 2015 | September, 2015 | 1 Month | 2994210.56 | 4491315.44 | 0.9 | No | Yet To Complete Plastering
Karebur Dispensary | Health | 2014/15 | 04⁰26.123'n. 035⁰43.371'e | 7067290 | Lapur | Turkana North |  | Jonice Co Ltd |  | April, 2015 | July, 2015 | 2 Months | 2826916 | 4240374 | 0.8 | No
Riokomor Dispensary | Health | 2014/15 | 04⁰06.944'n. 035⁰43.246'e | 7500000 | Lake Zone | Turkana North |  | Riokomor Investment Ltd | 711205887 | April, 2015 | July, 2015 | 2 Months | 6000000 | 1500000 | 0.75 | No | Not Yet Complete. The Projectis At The Roofing Stage, Yet To Roof The Verandah And Fit Door And Windows And Do Plastering.
Lokitaung Sub-County Hospital | Health | 2014/15 | 04⁰15.747'n. 035⁰45.260'e | 11957674 | Lapur | Turkana North |  | Tilak Hardware | 710744655 | Drug Store And Kitchen June And Renovations Mid Of May 2015 | October, 2015 |  |  |  | 0.7 | No | There Is So Much In Progress: Drug Store Being Constructed 60% D.One, Kicthen A About 80% Done. Renovation Of The Sub County Hospital; Repainting, Replacement Of Windows, Ceiling Boards And Door Locks
| Health | 2014/15
Lokamarinyang Dispensary | Health | 2014/15 | N 05°01.036', E 035°35675' |  | Lokamarinyang,Kibish | Kibish | [8 empty] | 0.4 | No | Project Started But Not Complete. Poor Workmanship
Napak Dispensary | Health | 2014/15 | N 04°51.928', E 035°23.630' |  | Napak,Kibish | Kibish | [8 empty] | 0.55 | No | Project Started But The Doctor's House Has Collapsed. Poor Workmaniship
Kaaleng Dispensary | Health | 2014/15 | N 03°07.079', E 035°36 |  | Kaaleng | Kibish |  | Kabarait Builders & Contractors |  | 2013 | 2014 |  |  |  | 1 | Yes | Complete, In Use But It Has Not Been Officially Opened. The Project Meets The Required Standards
Ekicheles Dispensary | Health | 2014/15 | N 04°28.675', E 035° 26. 959' | 7500000 | Kaikor,Kibish | Kibish |  |  |  | 2nd Of May 2015 |  |  | 3000000 | 4500000 | 0.3 | No | Project Started But Not Completed. Poor Workmaniship
| F$P | 2014/15
County Treasury Building | F$P | 2014/15 |  | 44545369 | Kanamkemer | Central |  | Lomia Energy |  |  |  |  | 26726426 | 17818943
Citizen Resource Centre-Kerio | F$P | 2014/15 |  | 34613328 | Kerio | Central |  | Edou Akide Const |  |  |  |  | 24229329 | 10383999
Revenue Networking | F$P | 2014/15 |  | 35930979 | Lodwar Township | Central |  | Sense Network Consultants |  |  |  |  | 25151685 | 10779294
Lorugum Citizen Resource Centre | F$P | 2014/15 |  | 46769510 | Turkwel | Loima |  | Loima Development Limited | 726000000 | 3rd March,2015 |  |  | 32738657 | 14030853 | 0.9 | No | Building Complete But No No Office Furniture. Basketball And Lawn Tennis Court Almost Complete, Awaiting Raising Of Reems And Lawn Tennis Posts. Fence Complete.
Lokiriama Revenue Generating Centre | F$P | 2014/15 |  | 57966872 | Lokiriama/Lorengikippi | Loima |  | Ekori Agete Enterprise |  | April, 2015 |  |  | 32565456 | 25401416 | 0.2 | No | Fence And Washrooms Almost Complete. No Building Constructed
4 Blocks, 2 Units Each, Un Lokichogio Compound | F$P | 2014/15 | N '04°12.452' E034°21.930' |  | Lokichogio | West |  | Rudolf Construction Co Ltd |  | 42200 | 42292 |  |  |  | 0.1 | No | Materials And Laborers On Site
Construction Of Governor's Residence | OOG | 2014/15 | N 03° 06.330´ E 035° 37.045' | 141856817 | Kanamkemer | Central |  | Mazeng & Const Co. Ltd |  |  |  |  | 65184757 | 76672060 | 30 | No | Work On Going, Foundation And Erection Of Pilaars Done. Concrete Fencing Done. Contractor Not On Site.
2014/15
Drilling Of B/Hole | WIA | 2014/15 |  | 2429600 | Lodwar Township | Central |  | Lake Turkana Supply |  |  |  |  | 728880 | 1700720
Drilling Of B/Hole | WIA | 2014/15 |  | 2826560 | Kangatotha | Central |  | Lopirpira Const |  |  |  |  | 847968 | 1978592
Drilling Of Lolupe B/Hole | WIA | 2014/15 |  | 2586900 | Kanamkemer | Central |  | Turkana B Group Link |  |  |  |  | 776070 | 1810830 | 100 | No | Drilled Water Tested And Not Salite.A Waiting For Handpump.High Pressure Of Water.It Is Accessble.
Drilling Of Nakalale B/Hole | WIA | 2014/15 |  | 2263000 | Kerio Delta | Central |  | Magee Const |  |  |  |  | 678900 | 1584100 | 0 | No
Cons Of Waterpan | WIA | 2014/15 |  | 9213474 | Kanamkemer | Central |  | Aluru Co. |  |  |  |  | 2764042.2 | 6449431.8
Cons Of Waterpan | WIA | 2014/15 |  | 9194078.8 | Kangatosa | Central |  | Urum Lose Co. |  | 14/05/2015 | 42285 | 1 Month | 2758223.64 | 6435855.16 | 30 | No | Labours On Site.Incomplete Work,I.E Fencing And Ramping.Poor Workmanship.
Cons Of Waterpan | WIA | 2014/15 |  | 9206630 | Kalokol | Central |  | Sacred Ventures |  |  |  |  | 2761989 | 6444641 | 80 | No | There Is No Fence.Works Is On Going.Ramping Is Not Done.There Is No Outlet To Avoid Overflow
Cons Of Waterpan | WIA | 2014/15 |  | 9199680 | Lodwar Township | Central |  | Kalimapus Co. |  |  |  |  | 2759904 | 6439776 | 95 | No | Project Is Complete.It Contains Two Channels For The Inlet.It Is Also Fenced.
Supply And Delivery Of Water Pipes | WIA | 2014/15 |  | 25853917.25 | Lodwar Township | Central |  | Irrico International |  |  |  |  | 15512350.35 | 10341566.9
Supply Of Kapokor Hand Pump | WIA | 2014/15 |  | 56399200 | Kalokol | Central |  | Silale Investment |  |  |  |  | 33839520 | 22559680 | 100 | Yes | The Water Is Slightly Saline And The Borehole Is Located By The Road. The Pressure Is Moderate. The Trench Is Shallow Hence Water Overflows It. The Borehole Is Also Located Far From Settlements.
Supply Of Elelea Hand Pump | WIA | 2014/15 |  | 56399200 | Kanamkemer |  |  | Silale Investment |  |  |  |  | 33839520 | 22559680 | 100 | Yes | Goog Access Of Water.Handpump Is Light.Substertial Pressure.Two Kilometers Radius To The Community.Slightly Saline.
Construction Of Kangirisae/Katiir Water Pan | WIA | 2014/15 |  | 13578785 | Kerio | Central |  | Cinoc |  |  |  |  | 9505149.5 | 4073635.5 | 70 | No | No Proper Walling Of The Water-Pan.It Can Not Contain Water For Long.There Is Embakment To Prevent Soil Back To The Water-Pan.It Is Fenced.
Construction Of Napuu Irrigation Project | WIA | 2014/15 |  | 57859814.76 | Kanamkemer | Central |  | Ortipirro Ltd |  |  |  |  | - | 57859814.76 | 50 | No | Works On Going.Fencing Of Poles In Place.Water Channels Underway.Leveling Of The Soil.Uprooting Of Stems.Tanks Stand Installed.
Drilling Of Borehole | WIA | 2014/15 |  | 2560000 | Kalokol | Central |  | Turkana Hardware |  |  |  |  | 2560000 | - | 100 | No | High Pressure Of Water.Water Sampled For A Test. Water Test Result Not Yet Received.A Located At The River Bank.It Is Not Accessble Or Motorable.
| WIA | 2014/15
Morulem Borehole | WIA | 2014/15 | N 01◦ 58.406' , E 036◦ 05.213' | 2079500 | Morulem (Lokori Ward) | Turkana East |  | Parakati Construction Co Ltd | [6 empty] | 0.7 | No | Drilled But They Have Not Done Pump Testing.
| WIA | 2014/15
Kabullokor Irrigation Scheme | WIA | 2014/15 |  | 4900000 | Lobei/Kotaruk | Loima |  | Katome Enterprises |  |  |  |  | 1470000 | 3430000 | 0.7 | Yes | No Water Running Through The Tunnel Towards The Scheme Area,Level Of Water At Turkwel River Has Gone Down
Kotaruk Water Pan | WIA | 2014/15 |  | 10264202 | Lobei/Kotaruk | Loima |  | Loima Enterprise |  |  |  |  | 6158512.2 | 4105680.8 | 0.2 | No | Works Stalled For 3 Weeks Since End Of August,Excavator Breakdown Due To Battery,A Pan Is Far From The Beneficiries
| WIA | 2014/15
Kainuk Borehole | WIA | 2014/15 | N:01° 46.796´, E:035° 30.534´ | 2524200 | Kainuk | T.South |  | Aropa Inv Ltd | [6 empty] | 1 | No | Borehole Drilled And Capped
Kalapata Borehole | WIA | 2014/15 | N:02° 19.924´, E:035° 50.742´
Kaputir Water Pan | WIA | 2014/15
| WIA | 2014/15
Naduat Borehole | WIA | 2014/15 |  | 2450000 | Nakalale | North |  | Ekanyarit Contractors | [6 empty] | 0.5 | No | The Borehole Has Been Drilled And Tested But It Has No Pump
Waterpan Kaeris | WIA | 2014/15 |  | 8406930 | Kaeris | North |  | Miebo Constr Co Ltd | [6 empty] | 0.75 | No | Not Fenced, Not Complete
Borehole | WIA | 2014/15 | 04⁰16.133'n. 035⁰47.542 | 2450000 | Lapur | North |  | Nabek Constructorand Supply Co Ltd | [6 empty] | 1 | Yes | The Borehole Has Been Drilled And Tested And The Pump Has Been Installed. Its Operational
Waterpan | WIA | 2014/15 |  | 9120030 | Lapur- Liwan | North |  | Isobel Marvel | [6 empty] | 0 | No | The Waterpan Does Not Exist According To The Ward Admin
| WIA | 2014/15
Kibish Borehole | WIA | 2014/15 | N 05°16.434', E 035° 47.920' |  | Kibish | Kibish |  | Morukoki Construction Co. Ltd | [6 empty] | 0.7 | No | Project Complete But Dry Borehole. Project Abandoned.
Kibish Water Pan | WIA | 2014/15 | N 05° 03.610', E 035° 39.351' | 2534500 | Kibish | Kibish | [6 empty] | 760350 |  | 0.9 | Yes | The Project Completed And It Is In Use Though Sides Have Not Yet Completed. The Project Meets The Required Standards
| WIA | 2014/15
| WIA | 2014/15
Kanakuring Waterpan | WIA | 2014/15 | N03°59.039ʼ E034°55.993ʼ | 9120105.6 | Lopur | T.West |  | Kotome Enterprise |  |  |  |  | 2767470 | 6457430 | 0.4 | No | Not Completed Shallow Tractor Not In Site
Borehole Drilling Ekitela | WIA | 2014/15 | N04°11.858ʼ E034°22.471ʼ | 2498062.3 | Lokichoggio | T.West |  | Lorado Const |  |  |  |  | 749418.68 | 1748643.61 | 0.4 | No | Drilled Bt Not Fitted
Borehole Drilling | WIA | 2014/15 | N04°12.528ʼ E034°33.603ʼ | 2420000 | Nanam | T.West |  | Sagal Petrol Station |  |  |  |  | 726000 | 1694000 | 0.5 | No | Not In Use Identified But Not Installed
Borehole Drilling | WIA | 2014/15 | N04°12.632ʼ E034°33.214ʼ |  | Nanam | T.West | [8 empty] | 1 | No | Installed But Not Good Not In Use No Signpost And Animal Trough
Naremeto Waterpan | WIA | 2014/15 | N04°06.064ʼ E034°22.888ʼ | 9259310 | Songot | T.West |  | Nawosin Construction |  |  |  |  | 2777793 | 6481517 | 0.5 | No | Not Completed
Letea Borehole | WIA | 2014/15 | N03°30.882ʼ E034°22.464ʼ | 2560000 | Letea | T.West |  | Mayanda Kimoja Ent |  |  |  |  | 768000 | 1748643.61 | 0.7 | No | No Signpost
| Education | 2014/15
Lodwar Youth Polytechnic | Education | 2014/15 |  | 9618200 | Lodwar Township | Central | [6 empty] | 7694560 | 1923640
Turkana Cultural Centre | Education | 2014/15 |  | 36150000 | Lodwar Township | Central | [6 empty] | 10845000 | 25305000 | 100 | Yes | The Project Is Complete And Fenced With 3 No Gates. 4 No Main Structures For Shade And 2 No Vip Shades. Several Latrines For Men And Women. The Facility Is Connected To Electricity.
Naotin Ecd | Education | 2014/15 |  | 6000000 | Kanamkemer Ward | Central | [6 empty] | 1800000 | 4200000
Construction Of Kakemera Ecd | Education | 2014/15 |  | 6000000 | Kanamkemer Ward | Central | [6 empty] | 1800000 | 4200000
Costruction Of Kalokutanyang Ecd | Education | 2014/15 |  | 5890600 | Kalokutanyang | Central | [6 empty] | 1767180 | 4123420
Construction Of Impressa Ecd | Education | 2014/15 |  | 6000000 |  | Central | [6 empty] | 1800000 | 4200000
Construction Of Juluk Ecd | Education | 2014/15 |  | 5600000 |  | Central | [6 empty] | 1680060 | 3919940
Construction Of St.Michael Ecd | Education | 2014/15 |  | 6000000 | Kanamkemer Ward | Central | [6 empty] | 1800000 | 4200000
Construction Of Nakwamekwi Ecd (Idp Camp) | Education | 2014/15 |  | 6000000 | Lodwar Township | Central | [6 empty] | 1800000 | 4200000 | 97 | No | Classroom, Kitchen And Dining Complete. It Is Fenced But With No Gate.
Construction Of A New Ecd At Napetao | Education | 2014/15 |  | 6000000 | Kanamkemer Ward | Central |  | Gatuzi Co Ltd |  |  | 42231 |  | 1800000 | 4200000 | 70 | No | Works On Going. Contractor On Site. Doors, Windows, Latrines And Painting Not Yet Done.
Construction Of Nakekichok Ecd | Education | 2014/15 |  | 6000000 | Kerio Ward | Central |  | Kerman Const Co Ltd |  |  |  |  | 1800000 | 4200000 | 95 | No | Contractor Not On Site. Classroom Dining Latrines And Fencing Done. There Is Need For Repaiting And Construction Of A Ramp In The Dining Hall.
Construction Of Nangolebei Ecd | Education | 2014/15 |  | 6000000 | Kerio Ward | Central | [6 empty] | 1800000 | 4200000 | 100 | Yes | Complete Structures. Secured With A Fence And Lockable Gate. The Project Location Was Changed From Nakurio To Nalongebei. The Facility Is Close To The Community.
Construction Of Nameresinyen Ecd | Education | 2014/15 |  |  | Kalokol | Central |  | Kalimapus Const Co Ltd | [6 empty] | 95 | No | Project Is Complete. Black Wall To Be Constructed In The Classroom. There Is Need For The Main Gate To Me Moved Away From The Dining Hall To Creat A Conducive Environment.
Construction Of Nakadukui Ecd | Education | 2014/15 |  | 6000000 | Kangatotha Ward | Central |  | Chap Chap Fishing Industry |  |  |  |  | 1800000 | 4200000 | 85 | No | Poor Workmanship. Used 32 Guage Ironsheets. The Facility Is Not Fenced. Incomplete Plainting.
Renovation Of Turkana County Ecd College | Education | 2014/15 |  | 18002596.8 | Lodwar Township | Central |  | Kerioucon Const Co Ltd |  | 42139 | 42292 |  |  |  | 85 | Yes | Works On Going. Partly Remaining Works Are Latrines, Drainage, Painting And Rennovation Of Floors. Contractor On Site With Adequate Labour. Fencing Done. Most Of The Works Not Captured In The Boqs.
Constrcution Of New Ecd At Katula | Education | 2014/15 |  | 6000000 | Kangatotha Ward | Central | [6 empty] | 1800000 | 4200000 | 90 | Yes | Classroom, Kitchen And Dining Complete. There Are Ramps Though Not In Good Condition. There Is No Fence And The Wall Plate For The Verandar Is Wooden Hence Not Stable. There Is No Chimney In The Kitchen. Craking On The Floor As Evidence Of Poor Curing.
| Education | 2014/15
Lokwamosing Ecd | Education | 2014/15 | N 01◦ 59.539', E 035◦ 56.201' | 6000000 | Lokwamosing | Turkana East |  |  |  | 2014 | 2015 |  | 1800000 | 4200000 | 0.98 | Yes | 1. Classroom Complete And It's In Use. Dinning Hall Also Is Complete Apart From Kitchen Works That Are On Progress.
Lopeduru Ecd | Education | 2014/15 | N 02◦ 14.571', E 036◦ 07.567' | 6000000 | Lopeduru | Turkana East |  |  |  | 2014 | 2015 |  | 1800000 | 4200000 | 1 | No | The Project Is Complete And Not In Use. It' S Well Fenced With A Gate. Cracks On The Outside Walls Of The Dinning, Classroom And The Gate.
Katilia Ecd | Education | 2014/15 | N 02◦ 07.432', E 036◦ 07.452' | 6000000 | Katilia | Turkana East |  |  |  | 2014 | 2015 |  | 1800000 | 4200000 | 1 | Yes | Completed Long Time And Already Been Used So Cracks Are All Over On The Floor And Blackboard Has Patches Therefore Cannot Be Written On. Pit Latrines Doors Are In Bad State.
Lokorkor Ecd | Education | 2014/15 | N 02◦ 11.247' E 036◦ 07.325' | 6000000 | Lokorkor | Turkana East |  | Kacheilap Gen. Construction Co. Ltd | 720000000 | 2014 | 2015 |  | 1800000 | 4200000 | 0.8 | No | Classroom Complete And It's In Good Standard Because The Contractor As Used Quary Blocks In Construction Of The Ecd. Works At The Dinning Are Still At The Roofing Stage. Pit Latrines Are Complete. Fence And Gate In Progress.
Nakwasinyen Ecd | Education | 2014/15 | N 02◦ 01.141' E 036◦ 04.987' | 6000000 | Nakwasinyen | Turkana East |  |  |  | 2014 | 2015 |  | 1800000 | 4200000 | 0.9 | No | Complete And Not In Use Because Kitchen Works Are Still In Progress And Also Dinning Hall And Classroom Windows Are Not Well Fitted.
| Education | 2014/15
Lorugum Youth Polytechnic | Education | 2014/15 |  | 9494774 | Turkwel | Loima |  |  |  | 42109 |  |  | 2848432.2 | 6646341.8 | 0.55 | No | No Fence, Administration Block And Two Classrooms Complete
Lokiriama Ecd | Education | 2014/15 |  | 6000000 | Lokiriama/Lorengikippi | Loima |  |  |  | June, 2015 | September, 2015 | 3 Months | 1800000 | 4200000 | 0.95 | No | No Chimney In The Kitchen, Windows Are To Be Renovated By The Contractor To Be Open, No Furniture
Nakurio Ecd | Education | 2014/15 |  | 6000000 | Lokiriama/Lorengikippi | Loima |  | Nyati General Construction Limited |  |  |  |  | 1800000 | 4200000 | 0.9 | No | Ecd Structure Not In The Normal Ecd Format. No Chimney In The Kitchen
Sasak Echoke Ecd | Education | 2014/15 |  | 6000000 | Lobei/Kotaruk | Loima | [6 empty] | 1800000 | 4200000 | 0.85 | No | Fence Complete, Ecd Structure Not In The Format Of Other Ecds. Building Complete But Not In Use.
| Education | 2014/15
Lokapel Ecd | Education | 2014/15 | N:02° 22.695´, E:035° 25.900´ | 6000000 | Katilu | T.South | [6 empty] | 1800000 | 4200000 | 1 | No | Construction Is Complete
Kainuk Ecd (Primary) | Education | 2014/15 | N:01° 46.515´, E:035° 30.405´ | 5899950 | Kainuk | T.South |  | Naliapa Co.Ltd |  |  |  |  | 1,769.985.00 | 4129965 | 0.6 | No | Project Is Ongoing
Juluk/Kaputir Ecd | Education | 2014/15 | N:02° 09.954´, E:035° 24.558´ | 6000000 | Kaputir | T.South |  | Kapetangole Eng & Const Co |  |  |  |  | 1680060 | 4319940 | 0.5 | No | Good Workmanship, Project Has Been Stalled
Koputiro Ecd | Education | 2014/15 | N:01°46.754´, E:035° 30.054´ | 6000000 | Kainuk | T.South |  | Lopusky Inv.Co Ltd | 728748619 | 42109 |  |  | 1800000 | 4200000 | 0.9 | No | Construction Is Ongoing.
Lokichar Youth Polythechnic | Education | 2014/15 | N:02° 22.145´, E:035° 38.972´ | 9910135 | Lokichar | T.South | [6 empty] | 2973040.5 | 6937094.5 | 0.97 | No | Construction Is Complete,No Fencing Done
Lokichar Idp Ecd | Education | 2014/15 | N:02° 21.545´, E:035° 37.840´ | 6000000 | Lokichar | T.South | [6 empty] | 1800000 | 4200000 | 0.7 | No | Accesible To The Community
Kangakipur Ecd | Education | 2014/15 | N:02° 22.487´, E:036° 01.745´ | 5899950 | Kalapata | T.South |  | Kalapata Const & Suppl Ltd | 708900866 | 42109 |  |  | 1769985 | 4129965 | 0.8 | No | Construction Is On Finishing Stages,Construction Of The Toilet Is Ongoing
Kakalel Ecd | Education | 2014/15 | N:02°27.770´, E:036° 05.213´ | 6000000 | Kalapata | T.South |  | Kaikoropus Ent Ltd |  |  |  |  | 1647231 | 4352769 | 0.75 | No | Fencing Not Yet Done,Funtionale Lighting System
| Education | 2014/15
Naduat Ecd | Education | 2014/15 | 03⁰30.756'n 035⁰11.966'e | 6000000 | Nakalale | North |  | Kuchilkuchil | 713000000 | 12th March 2015 | 42186 | 2months | 3.6m | 2.4m | 0.95 | No | Yet To Finish Dining Hall Flour And Classrooms Window Panes
Losajait Ecd | Education | 2014/15 | 03⁰37.273'n 035⁰18.645'e | 6000000 | Nakalale | North |  | Napalakipor |  | 42064 | 42186 |  | 3.6m | 2.4m | 1 | No | The Project Is Done And Complete
Ngaurendiria Ecd | Education | 2014/15 | 03⁰56.47'n 035⁰15.17'e | 6000000 | Kaeris | North |  | Musug Const Co Ltd |  | 42064 | 42186 |  | 3.6m | 2.4m | 1 | Yes | The Project Is Done And Complete But The Pupils Are Not In Class Coz There Is No Food
Kangakipur Ecd | Education | 2014/15 | 04⁰01.966'n 035⁰29.250'e | 5899950 | Kaeris | North |  |  |  | 42064 | 42186 |  |  |  | 1 | Yes | The Project Is Done And Complete
Lochoredome Ecd | Education | 2014/15 | 04⁰15.893'n 035⁰40.218'e | 5714631 | Lapur | North |  |  |  | 42064 | 42186 |  |  |  | 1 | Yes | The Pupils Were In High Attendance, The Community Asking For Food
Lochwa Arengan Ecd | Education | 2014/15 | 03⁰ | 5330500 | Lapur | North |  |  |  | 42078 | 42200 | 3 Months | 1599150 | 3731350 | 0.3 | No | No Sign Of Any Activity At The Site
Nabeletakoit Ecd | Education | 2014/15 | 03⁰ | 6000000 | Lakezone | North |  | Napeget Co Ltd |  | 42078 | 42200 | 2 Months | 3600000 | 2400000 | 0.95 | No
Kalosep Ecd | Education | 2014/15 | 03⁰ | 6000000 | Lakezone | North |  | Nasechabuin Co Ltd |  | 42078 | 42200 |  | 3600000 | 2400000 | 0.9 | No
Kataboi Youth Polytechnic | Education | 2014/15 | 03⁰ | 9771782 | Lakezone | North |  |  |  | 42078 |  |  | 2965753.44 | 6920091.36 | 0.5 |  | The Project Is At The Linthol
| Education | 2014/15
Koyasa Ecd | Education | 2014/15 | N 04 58.156', E 03529.164 |  | Kibish | Kibish |  |  |  | 2013 |  |  |  |  | 0.4 | No | This Project Was Started And Abandoned By The Contractor
Kibish Ecd | Education | 2014/15 | N 05 17.117' , E 035' 49.381' |  | Kibish | Kibish |  |  |  | 2013 | 2014 |  |  |  | 1 | Yes | Project Complete And It Is In Use.
Lokamarinyang Ecd | Education | 2014/15 | 0501.042', E 035' | 6000000 | Kibish | Kibish |  | Lakika Network Ltd |  |  |  |  | 1800000 | 4200000 | 0.2 | No | The Project Do Not Meet The Required Standards. Poor Workmaniship. The Project Is Turning To Be A Toilet
Karubarongorok Ecd | Education | 2014/15 | N 0426.883' | 6000000 | Kibish | Kibish | [6 empty] | 1800000 | 4200000 | 0.5 | No | Project Started But Not Yet Completed
Market Stall And Toilet Project | TTI | 2014/15 |  | 10337827.2 | Lodwar Township | Central |  | Seansapps Co.Ltd |  |  |  |  | 3101348.1 | 7236479.1
Construction Office Building Block | TTI | 2014/15 |  | 19683605 | Lodwar Township | Central |  | Lelar Investment Ltd. |  |  |  |  | 5905081.5 | 13778523.5 | 40 | No | Contactor On Site. Work Is On Going. Coulumns Have Been Done. Construction Of A Ring Beam Is Underway. Delayed Payments Are Crippling Work.
Refurbishment Of Office Building | TTI | 2014/15 | N 03 07.035' E 035 36.162 Elevatio 516 | 4542583 | Lodwar Township | Central |  | Kakurio Contractor |  |  |  |  | 4542582.9 | 0.1 | 100 | Yes | 04 No Of Ac Installed. A Waiting Bay And 2 Parking Lots Constructed. Repainting Of The Office Block Done. The Office With Office Furniture. Windows, Doors And Ceiling Replaced. Thfacility Was Fenced And A Gate Erected.
Market Stall And Toilet Project | TTI | 2014/15 |  | 9806672 | Kerio Ward | Central |  | Parakati Constraction |  |  |  |  | 6147140.9 | 3659531.1 | 90 | No | Market Stall Done But No Latrines. The Floor Is Rough (Finishing Not Done). Contractor Not On Site.
Renovation Work Lodwar Market | TTI | 2014/15 |  | 2266760 | Lodwar Township | Central |  | Mamren Civil And Building Const. |  |  |  |  | 1360760 | 906704
Turkwood Film Projects | TTI | 2014/15 |  | 366797 | Lodwar Township | Central |  | Dopetei Systems And Design |  |  |  |  | 0 | 366797
Turkwood Film Projects | TTI | 2014/15 |  | 843200 | Lodwar Township | Central |  | Northlink Productions |  |  |  |  | 0 | 843200
Co-Operatives Development Fund | TTI | 2014/15 |  | 30000000 | Lodwar Township | Central | [6 empty] | 0 | 30000000
Construction Of Market Stalls And Toilets | TTI | 2014/15 |  | 10337827.2 | Kalokol | Central |  | Seansapps Co.Ltd | [5 empty] | 10337827.2 | 80 | No | Maket Stalls And Latrines Done. The Fence Is Not Yet Done. There Is Need For A Ramp To The Stall. The Lockable Doors Are Falling Off Hence A Need For Repair.
| TTI | 2014/15
Lokori Market Stalls | TTI | 2014/15 | N 01◦ 57.050' , E 036◦ 01.820' | 10453259 | Lokori | Turkana East |  | Lelar Investments Ltd |  |  |  |  | 9407933.1 | 1045325.9 | 1 | No | It Has Been Completed But Not In Use. No Pit Latrines And Not Also Fenced.
| TTI | 2014/15
Turkwel Market Stalls And Toilet | TTI | 2014/15 |  | 9812539 | Turkwel | Loima |  | Marekai Building & Construction Ltd. |  | 2nd June 2015 |  |  |  |  | 0.95 | No | Project Complete With Stalls And Toilet,Not In Use,No Fence,Good Stalls With Tiles
Renovation Work Lokiriama Market | TTI | 2014/15 |  | 4000000 | Lokiriama/Lorengikippi | Loima |  | Nyati General Construction |  | 10th May,2015 | 10th July,2015 | 2 Months | 2400000 | 1600000 | 0.99 | No | Market Officially Opened On 10th September,2015 By H.E The Governor Of Turkana County,Fence Complete,Markert Structure Complete
| TTI | 2014/15
Market Stalls And Toilet Project At Lowoarengk | TTI | 2014/15 | 04⁰16.794'n 035⁰53.541'e | 9889006 | Lakezone | North |  | Lapur Trading And Investment Ltd | 729000000 |  |  |  | 2966719 | 6922344.7 | 0.8 | No | Project At Finishing Atages, Doing Some Welding, And Yet To Paint
Eco Lodge Project Kataboi | TTI | 2014/15 | 03⁰40.644'n 035⁰49.919'e | 66389746 | Lakezone | North |  | Kacheilap Gen Contractors | 720000000 | 42322 | 42231 | 6 Months | 53111797 | 13277948 | 0.7 | No | The Contractor Says The Challenge Is The Nature Of Soil… They Had To Take A Lot Of Time Build From Deeper Int The Ground
Construction Of Feed Stores (Lodwar) | PEF | 2014/15 |  | 9460620 | Lodwar Township | Central |  | Galoma Construction Ltd |  |  |  |  | 2838186 | 6622434
Revival Of Turkana Fisheries Cooperative Society(Tfcs) | PEF | 2014/15 |  | 7000000 | Kalokol | Central |  | Kalokol Engineering |  |  |  |  | 4200000 | 2800000 | 65 | No | Project Incomplete. Raised Walls And Roofing Done. Contractor On Site. The Facility Is Fenced With A Gate.
Construction Of Fresh Fish Market | PEF | 2014/15 |  | 9456640 |  | Central |  | Nakiria Co. Ltd | [5 empty] | 9456640 | 80 | No | The Project Is Incomplete And Not Yet Fenced. Contractor Not On Site.
Preliminaries Of Establishment Of Lake Turkana Management Authority | PEF | 2014/15 |  | 12153000 |  | Central |  | Centre For Consultancy And Training In Pastoralism |  |  |  |  | 6076500 | 6076500
Construction Of Multiplication And Breeding Centre | PEF | 2014/15 |  | 29002257 | Kerio | Central |  | Lotulia Kor Contractors |  | 26/08/2015 | 42353 |  | 20301579.9 | 8700677.1 | 40 | No | Work On Going. Contractor On Site. Walls Erected For Manager House And Confrence Building. Adequate Labour.
Renovation Of Kangatotha Sale Yard | PEF | 2014/15 |  | 2449076.66 | Kangatotha | Central |  | Lobei Const Co Ltd |  |  |  |  | 2449076.66 | 0 | 100 | Yes | Project Complete. The Community Expressed A Need Of Shade And Piping Of Water. The Space In The Gate Grills Are Too Wide To Allow Goats And Sheep Escape From The Sale Yard.
| PEF | 2014/15
Establisment Of Holding Grounds - Napeililim | PEF | 2014/15 |  | 48774520 | Turkwel | Loima |  | Puch Building Construction | 729000000 |  |  |  | 34142164 | 14632356 | 0.3 | No | Project Ongoing,Project Stalled,Residents Who Worked At The Site Complained Of Delayed Payments,No Fence
Kalokol Ward Admimistrators Office | PSDDM | 2014/15 |  | 11528958 | Kalokol |  |  | Amana Suppliers Ltd |  |  |  |  | 3458687.4 | 8070270.6 | 100 | No | The Project Is Complete With Fence And A Gate. Solar Pannels Installed And Functional.
Town Ward Administrators Office | PSDDM | 2014/15 |  | 10800000 | Lodwar Township |  |  | Ekori Kapana Investment Ltd |  |  |  |  | 3240000 | 7560000 | 60 | No | Project Incomplete. Placement Of Windows And Doors Not Done Yet. Painting And Ceiling Also Not Done. Contractor Not On Site. Latrine Dug But The Structure Not Done. The Facility Has Not Been Fenced.
Kanamkemer Ward Administrators Office | PSDDM | 2014/15 |  | 9843272 | Kanamkemer |  |  | Natoot Building Construction Co Ltd |  | 28/04/2015 | 42011 | 2 Months | 2952981.6 | 6890290.4 | 60 | No | Works On Going. Roofing And Platering In Progress. Contractor Is On Site. Partitioning Of Rooms Done Using Blocks.
| PSDDM | 2014/15
Lokori/Kochodin Ward Admin Office | PSDDM | 2014/15 | N 01◦ 57.358' , E 036◦ 02.307' | 13628214 | Lokori | Turkana East |  | Touchlife Co Ltd |  |  |  |  | 4088464.2 | 9539749.8 | 0.8 | No | It Has Not Been Completed Yet. Pit Latrines Works In Progress. Fence And Gate Are Complete. Septic Tank Works In Progress
| PSDDM | 2014/15
Turkwel Ward Admin Office | PSDDM | 2014/15 |  | 12000000.6 | Turkwel | Loima |  | Narina Investment Company |  |  |  |  | 3600000.18 | 8400000.42 | 0.95 | No | Fence Is Too Short,Pit Latrines And Offices Complete,Good Structures,Project Complete
Lobei/Kataruk Ward Admin.Office | PSDDM | 2014/15 |  | 10028908 | Lobei/Kotaruk | Loima |  | Sasak Construction Co.Ltd |  | April,2015 |  |  | 3008672.4 | 7020235.6 | 0.4 | No | Fence Complete,Office Ongoing,Expected To Be Complete On Mid-October
| PSDDM | 2014/15
Kaptir Ward Admin Office | PSDDM | 2014/15 | N:02° 03.639´, E:035° 25.788´ |  | Kaputir | T.South | [8 empty] | 1 | No | Construction Is Complete
Kainuk Ward Office | PSDDM | 2014/15 | N:01° 47.045´, E:035° 30.884´ | 9991760 | Kainuk | T.South |  | Echuk Contractors Co |  |  |  |  | 2997528 | 6,994.232.00 | 0.4 | No | Project Has Been Stalled
Kalapata Ward Office | PSDDM | 2014/15 | N:02° 22.738´, E:036°01.970´ | 13209338 | Kalapata | T.South |  | Kodekode Cons Ltd | [6 empty] | 0.9 | No | Construction Is Complete,Plumbing Works Is Ongoing
Katilu Ward Office | PSDDM | 2014/15 | N:02°15.715´, E:035° 25.828´ | 11732021 | Katilu | T.South |  | Katilu Eng. Company | [6 empty] | 0.6 | No | Project Has Been Stalled
Lokichar Ward Office | PSDDM | 2014/15 | N:02° 21.802´, E:035° 38.226´ | 12052947 | Lokichar | T.South |  | Kasuroi Ward Office |  |  |  |  | 3615884 |  | 0.8 | No | Construction Is Complete,No Fencing Done.Finishing Stages
Lokichar Feed Store | PSDDM | 2014/15 | N:02° 31.992´, E:036° 07.370´ | 9658280 | Lokichar | T.South |  | Itwan Investment Co Ltd | [6 empty] | 0.95 | No | Fencing Not Yet Done,Finishing Is Ongoing
| PSDDM | 2014/15
Nakalale Ward Admin Office | PSDDM | 2014/15 | 03⁰30.907'n 035⁰13.528'e | 12228947 | Nakalale | North |  | Furthergur Gei Merchants |  | 42036 | 42125 | 4months | 3668684 | 8560262.9 | 0.3 | No | There Is No Activity At The Site The Project Below The Linthol
Ward Admin Office Lapur Ward | PSDDM | 2014/15 | 04⁰16.013'n 035⁰45.401'e | 12900075.8 | Lapur | North |  | Salnel Const Ltd |  | 42050 | 42139 | 4 Months |  |  | 0.5 | No | There Is No Activity At The Site The Project At The Linthol.. There Is Material On Site
Ward Admin Office Lakezone | PSDDM | 2014/15 | 04⁰16.793'n 035⁰53.519'e | 13671516 | Lakezone | North |  | Lapur Trading & Investment Co Ltd |  | 42050 | 42139 | 4months | 4101454 | 9570061.9 | 0.8 | No | The Projectalmost Done, They Are Painting And Wiring The Building Nd Yet To Put The Tiles On Flour
| PSDDM | 2014/15
Kaikor Ward Administrators Office | PSDDM | 2014/15 | N 04°28.670', E 035°26.965' |  | Kaikor | Kibish |  | Abunyai Contractors |  | 2014 | 2015 |  |  |  | 1 | Yes | Complete But Not In Use. The Project Has Not Been Officially Opened
Ward Adminstrators Office Napak | PSDDM | 2014/15 | N 04°51.997', E 035°23.614' | 16656521 | Napak,Kibish | Kibish |  | Al-Sheikh Ent. Ltd |  |  |  |  | 4996956 |  | 0.6 | 60 | Project Started But Not Completed. Do Not Meet The Required Standards. Poor Workmaniship
| PSDDM | 2014/15
Kakuma Ward Administrator Office | PSDDM | 2014/15 | N03°42.609ʼ E034°52.033ʼ | 11585001 | Kakuma | T.West |  | Rasabana Ent. Co. Ltd |  |  |  |  | 3475500.3 | 8560262.9 | 0.5 | No | No Ceiling No Windows/Door No Paint No Toilet Materials On Site No Personel On Site,No Signpost And Fence
Lopur Ward Administrators Office | PSDDM | 2014/15 | N03°51.454ʼ E034°49.638ʼ | 11425340 | Lopur | T.West |  | Ekisil Co. Ltd |  | 27/6/2015 | 27/9/2015 |  | 3427602 | 7997738 | 0.6 | No | Signpost Not Fixed But On Site
Lokichoggio Ward Administrators Office | PSDDM | 2014/15 | N04°11.332ʼ E034°21.929ʼ | 13352191 | Lokichoggio | T.West |  | Lojam Luqa Energy Co. Ltd |  |  |  |  | 4005657.3 | 9346533.7 | 0.7 | No | No Signpost Poorly Designed No Windows,Glasses,Floor Tiles,And Ceiling Plumbing,Fencingwas Done And Contractors On Site
Nanam Ward Administrators Office | PSDDM | 2014/15 | N04°13.003ʼ E034°33.717ʼ |  | Nanam | T.West | [8 empty] | 1 | Yes | Piping Done But No Water Source Near The Office Well Furnised Rooms, Seedling Available But Not Planted There Is No Signpost,Toilets Are Out Of Fenced Area,Good Fence And Construction Materials On Site
Songot Ward Administrators Office | PSDDM | 2014/15 | N04°03.097ʼ E034°31.658ʼ | 12544947 | Aposta(Songot) | T.West |  | Tiwae |  |  |  |  | 3763484.1 | 8781462.9 | 0.5 | No | No Fence No Toilet Materials On Site Contractors Not On Site
Kalobeyei Ward Administrators Office | PSDDM | 2014/15 | N03°45.657ʼ E034°37.946ʼ | 12488900 | Kalobeyei | T.West |  | Akanpich Builders Ltd |  |  |  |  | 3746670 | 8742230 | 0.6 | No | Windows/Doors To Be Fixed But On Site No Fence Materials On Site No Signpost
Letea Ward Administrators Office | PSDDM | 2014/15 | N03°31.312ʼ E034°48.536ʼ |  | Letea | T.West | [8 empty] | 1 | Yes | Good Fence
Turkana Central Solar Project - Kapua Primary | Energy | 2014/15 |  | 18879540 | Kalokol | Central |  | Turkana Salama |  | 42139 | 42139 |  | 7561611.99 | 11317928.01 | 100 | Yes | Pannels Installed In Boys Dorm - 4 Pannels. Staff Room - 6 Pannels. Class 5 - 2 Pannels. All Functioning.
Turkana Central Solar Project - Kangirisae Primary | Energy | 2014/15 |  | 18879540 | Kerio | Central |  | Turkana Salama |  |  |  |  | 7561611.99 | 11317928.01 | 100 | Yes | Pannels Installed In; Class 5, 6 & 7- 8 Pannels. Girls Dorm - 2 Pannels. All Functioning
Turkana Central Solar Project - Naipa Primary | Energy | 2014/15 |  | 18879540 | Kangatotha | Central |  | Turkana Salama |  |  |  |  | 7561611.99 | 11317928.01 | 100 | Yes | Pannels Installed In; Class 1- 2 Pannels, Class 5 - 4 Pannels. All Functioning
Turkana Central Solar Project - Naoros Primary | Energy | 2014/15 |  | 18879540 | Kangatotha | Central |  | Turkana Salama |  |  |  |  | 7561611.99 | 11317928.01 | 100 | Yes | Pannels Installed In; Class 3- 8 Pannels And Are In Use. No Sign Post Indicating The Project.
Arboretum Levelling,Waterpiping | Energy | 2014/15 |  | 2100000 | Lodwar Township | Central |  | Jibu Langu Construction |  |  |  |  | 1542704 | 557296
Construction Of Office Block | Energy | 2014/15 |  | 19999600 | Kanamkemer | Central |  | Naita Construction |  | 42170 | 42231 |  | 6896414 | 13103186 | 100 | No | Job Well Done
| Energy | 2014/15
Loima Solar Projects-Kotela Pry.School | Energy | 2014/15 |  | 13524800 | Lobei/Kotaruk | Loima |  | Magee Construction | 726000000 |  |  |  | 5416937.59 | 9277180.34 | 0.8 | Yes | Solar Panels Have Failed To Work. Invertors Not Working Too
Loima Solar Projects-Urum Primary | Energy | 2014/15 |  | 13524800 | Lobei/Kotaruk | Loima |  | Magee Construction | 726000000 |  |  |  | 5416937.59 | 9277180.34 | 0.9 | Yes | The Lighting System Is Operational,The Solar Panels Have Been Fitted On One Side Of The Classroom
Loima Solar Projects-Namoruputh Boys Sec | Energy | 2014/15 |  | 13524800 | Loima | Loima |  | Magee Construction | 726000000 |  |  |  | 5416937.59 | 9277180.34 | 0.8 | Yes | Teachers Quarters Were Fitted With Only One Solar Panel Which Is Insufficient To Supply Electricity. Headteacher Has Requested The County Government To Supply Some More Solar Panels.
| Energy | 2014/15
Solar Electrification At Nakwamoru Dispensary | Energy | 2014/15 | N:02° 03.250´, E:035° 25.874´ |  | Kaputir | Turkana South |  | Pizonas International |  | 42253 |  |  |  |  | 1 | Yes | Functional Solar Panels
| Energy | 2014/15
Solar Pv System Installation At Naduat Pry School | Energy | 2014/15 | 03⁰30.710'n. 035⁰12.121'e |  | Nakalale | Turkana North |  | Lokitaung Contractors | [6 empty] | 1 | Yes | No Remarks
Solar Pv System Installation At Kaeris Girls Pry School | Energy | 2014/15 | 03⁰59.079'n. 035⁰28.812'e |  | Kaeris | Turkana North |  | Lokitaung Contractors Ltd | [6 empty] | 1 | Yes
Solar Pv System Installation At Nariokomor Pry School. | Energy | 2014/15 | 04⁰06.098'n. 035⁰43.147'e |  | Lake Zone | Turkana North |  | Lokitaung Contractors | [6 empty] | 1 | Yes
Solar Pv Installation At Lomekwi Pry School | Energy | 2014/15 | 03⁰54.796'n. 035⁰50.271'e |  | Lake Zone | Turkana North |  | Lokitaung Contractors | [6 empty] | 1 | Yes
| Energy | 2014/15
Solar System Installation | Energy | 2014/15 | N03°53.140ʼ E034°33.665ʼ |  | Kalobeyei-Natiira | Turkana West |  | Olam Building&Supplies | [6 empty] | 1 | Yes | Solar System To Be Moved From Old Building To New
Solar System Installation | Energy | 2014/15 | N03°56.441ʼ E034°33.732ʼ |  | Kalobeyei-Lokwanyia | Turkana West |  | Olam Building&Supplies | [6 empty] | 1 | Yes | Solar System To Be Moved From Old Building To New
Solar System Installation St Patrick Lomidat | Energy | 2014/15 | N04°09.396ʼ E034°25.908ʼ |  | Songot | Turkana West |  | Olam Building&Supplies | [6 empty] | 1 | Yes | Complete And Working
Solar System Installation Letea Pry School | Energy | 2014/15 | N03°31.314ʼ E034°48.912ʼ |  | Letea | Turkana West |  | Olam Building&Supplies | [6 empty] | 1 | Yes | Complete And Working
Pokotom Pry Sch Solar Installation System | Energy | 2014/15 | N04°11.809ʼ E034°53.367ʼ |  | Kakuma | Turkana West |  | Olam Building&Supplies | [6 empty] | 1 | Yes | Complete And Working Placed Near From Trees
Solar System Installation(Ecd St Mathew Nadome) | Energy | 2014/15 | N04°06.401ʼ E034°23.351ʼ |  | Nanam | Turkana West |  | Olam Building&Supplies | [6 empty] | 0.5 | No | Toilet Dug But Not Constructed Materials On The Site No Solar On The Dining Hall Roofing Is Ongoing
Solar System Installation Napopongoit Pry School | Energy | 2014/15 | N04°11.720ʼ E034°23.849ʼ |  | Nanam | Turkana West |  | Olam Building&Supplies | [6 empty] | 1 | Yes | Solar System Working,No Signpost
Proposed Office Block For The Ministy | Roads | 2014/15 |  | 27805505 | Lodwar Township | Central |  | Loki Builders & Const. Co Ltd |  |  |  |  | 19352631.5 | 8452873.5
Proposed Construction And Equiping Of Mechanical Workshop | Roads | 2014/15 |  | 38157556.2 | Lodwar Township | Central |  | Sheikh Baksh Ltd |  |  |  |  | 9000000 | 29157556.2
Upgrading To Bitumen Standards Of Lodwar Town Roads | Roads | 2014/15 |  | 297607727 | Lodwar Township | Central |  | Frontier Engineering Ltd |  |  |  |  | 152532787.3 | 145074939.7
Eliye Springs – Katula Routine Maintenance | Roads | 2014/15 |  | 1590220.8 | Kangatotha | Central |  | Nados Construction Co.Ltd |  |  |  |  | 1590220.8 | 0 | 100 | Yes | The Road Is Motorable. Substancial Work Done.
Monti – Namerisinyen - Lokatukon | Roads | 2014/15 |  | 3090281.76 | Lodwar Township | Central |  | Ashmmartna Constructor Co. Ltd |  |  |  |  | 3090281.76 | 0
Light Grading Of Kerio-Ekwar | Roads | 2014/15 |  | 7168800 | Kerio | Central |  | Turkana South Com Ag Ltd |  |  |  |  | 5018160 | 2150640 | 100 | Yes | Project Complete. The Road Is Motorable.
Heavy Grading And Bush Clearing Of Nabwel-Ekorot Road | Roads | 2014/15 |  | 2690980 | Kalokol | Central |  | Muruongor Const And General Supplies Ltd | [5 empty] | 2690980 | 100 | Yes | Project Complete. The Road Is Motorable. Good Workmanship.
Bush Clearing And Light Grading Of Nabuskal-Kairiama Road | Roads | 2014/15 |  | 3580290 | Kalokol | Central |  | Kablade Invest Ltd | [6 empty] | 100 | Yes | Project Complete. The Road Is Motorable.
Heavy Grading And Bush Clearing Of Kalotum-Nachamai-Nanukumeri Road | Roads | 2014/15 |  |  | Kalokol | Central | [8 empty] | 100 | Yes | The Road Is Motorable. Distance Not Included In The Sign Post.
Bush Clearing And Light Grading Of Akatorongot-Kangirisae Road | Roads | 2014/15 |  | 11910000 | Kerio | Central |  | Ngakomwam Contr Ltd | [6 empty] | 100 | Yes | Project Complete. The Road Is Motorable.
Heavy Grading And Bush Clearing Of Kalokol-Airstrip Junction-Namukse Road | Roads | 2014/15 |  | 2,545,620,00 | Kalokol | Central |  | Nados Construction Co.Ltd | [5 empty] | 2,545,620,00 | 100 | Yes | Project Is Complete. The Road Is Motorable.
Spot Improvement Works At Lodwar-Kalokol-Eliye Springs Road | Roads | 2014/15 |  | 5689800 | Kangatotha | Central |  | Natamakarua Eng Ltd | [6 empty] | 100 | Yes | Project Is Complete. The Road Is Motorable.
| Roads | 2014/15
Lopii - Kaaruko - Lokori Road | Roads | 2014/15 | N 02◦ 03.826' , E 035◦ 52.419' | 3700700 | Lokori Ward | Turkana East |  | Lowatat Contractors & Suppliees Ltd | [6 empty] | 1 | Yes | It Has Been Completed. It's Well Done With Sign Post.
Elelea Drift | Roads | 2014/15 | N 02◦ 06.068' , E 036◦ 09.154' | 9628000 | Elelea (Katilia Ward) | Turkana East |  | Natorube Company Limited | [6 empty] | 1 | Yes | Complete And In Use. Height Level Of The Drift Is Almost The Same Level With The Sand.
Spot Improvement Lokori - Napeitom Road | Roads | 2014/15 | N 01◦ 54.892' , E 036◦ 00.380' | 23960087 | Lokor-Napeitom | Turkana East |  | Kataboi Investment Ltd |  |  |  |  | 7188026.13 | 16772060.97 | 1 | Yes | It's Complete And In Use. No Sign Post Showing It.
Lotubae-Kaesamalit Road | Roads | 2014/15 | N 02◦ 01.186' , E 036◦ 07.722' | 3125040 | Lokori And Katilia Ward | Turkana East |  | Jekanas Co. Ltd | [6 empty] | 1 | Yes | Complete And In Use But No Sign Post
| Roads | 2014/15
Urum-Namoruarengan Road | Roads | 2014/15 |  | 3800980 | Lokiriama/Lorengikippi | Loima |  | Apuco Holdings Group Co.Ltd |  | 23rd June,2015 | 10th July,2015 | 1 Month |  |  | 1 | Yes | The Road Is In Good Condition, Its Complete.
Urum-Tapaik-Nacharakan Road | Roads | 2014/15 |  | 3644256 | Lokiriama/Lorengikippi | Loima |  | Havana Builders Company Limited |  | June, 2015 | July, 2015 | 1 Month | 3279830.4 | 364425.6 | 0.8 | Yes | The Junction From Lokiriama-Urum Road Is Not Well Levelled. Gravelling Towards Tapaik Is Well Maintained
Maintenance Of Lokwatuba-Kopetakinei Road | Roads | 2014/15 |  | 2702800 | Lokiriama/Lorengikippi | Loima |  | Silale Moonlight Investment Limited |  | June, 2015 | July, 2015 | 1 Month |  |  | 0.95 | Yes | Road Has Been Maintained Well, Its Passable.
Lobei-Kalapata Road | Roads | 2014/15 |  |  | Lobei/Lotaruk | Loima |  | Almond Air & Logistics Limited |  | June, 2015 | July, 2015 | 1 Month |  |  | 0.9 | Yes | Road Maintenance Complete
Routine Maintenance Of Nakurio-Keemanik Road | Roads | 2014/15 |  |  | Lokiriama/Lorengikippi | Loima |  | Rikinei Construction Company Limited |  | 15th June, 2015 | 15th July, 2015 | 1 Month |  |  | 0.8 | Yes | Good At The Start From Lobei-Lorengikippi Road. Maintenance Towards Keemanik Centre Not Done Well.
Naipa-Moruong'or Junction | Roads | 2014/15 |  |  | Lobei/Lotaruk | Loima |  | Apen Investment Company |  | 23rd June, 2015 | 10th July, 2015 | 1 Month |  |  | 0.9 | Yes | Bush Clearing, Grading And Gravelling Done Well.
Lorugum-Nakwasinyen-Kopeta Road | Roads | 2014/15 |  | 7123101 | Loima Ward | Loima |  | Lilmark Company Limited |  | June, 2015 | July, 2015 | 1 Month |  |  | 0.75 | Yes | No Sign Post To Show The Details Of The Road Works. A Challenge Of Rivers Pose Diffuculty In Gravelling Of The Road.
Napeililim-Nasogol-Lopur Road | Roads | 2014/15 |  | 3070000 | Turkwel | Loima |  | Kabarait Builders & Contractors |  | June, 2015 | July, 2015 | 1 Month |  |  | 0.9 | Yes | Road Is Passable,Geavelled Well
| Roads | 2014/15
Lokapel Lomonyang Nakabosan Road | Roads | 2014/15 | N:02° 22.020´, E:035° 25.484´ | 2763120 | Katilu | Turkana South |  | Katilu Engineering And Const |  |  |  |  | 2486808 | 276312 | 1 | Yes | Road Completed , Well Done
Kaputir Katilu Road | Roads | 2014/15 | N:02° 05.411´, E:035° 27.578´ |  | Kaputir | Turkana South | [8 empty] | 1 | Yes | Road Completed , Well Done
Kainuk Forest | Roads | 2014/15 | N:01° 46.162´, E:035° 29.546´ | 1552312 | Kainuk | Turkana South |  | Ngilopechek Investment Ltd |  |  |  |  | 1552312 |  | 0.7 | Yes | Light Grading Done
Sopel-Lochwaa Road | Roads | 2014/15 | N:02°49.039´, E:035° 36.875´ | 2107407 | Lokichar | Turkana South |  | Natotoo Ent.Limited | [6 empty] | 1 | Yes | Light Grading Done
Nakaalei-Kaatir Road | Roads | 2014/15 | N:02° 31.984´, E:036° 09.370´ | 5171280 | Kalapata | Turkana South |  | Philona Constractor |  | 22-06-2015 | 30-08-2015 |  |  |  | 1 | No | Heavy Grading,Gravelling And Patching
Nawoiyaregae Bridge | Roads | 2014/15 | N:02° 06.089´, E:035° 26.171´ | 95062884 | Kaptir | Turkana South |  | Naipa Building Construction |  | 42125 | [5 empty] | No | Building Materials Have Been Brought To The Site,Bush Clearing Done
Kaekunyuk-Korinyang Road | Roads | 2014/15 | N:02° 14.770´, E:035° 26.074´ | 2696652 | Katilu | Turkana South |  | Epae Company Limited |  | 22-6-2015 | 30-06-2015 |  |  |  | 1 | Yes | Road Completed , Well Done
Kainuk Astu -Namambu Road | Roads | 2014/15 | N:01°47.178´, E:035° 31.055´ | 3258150 | Kainuk | Turkana South |  | Ekobakin Co Ltd | [6 empty] | 0.9 | No | Light Grading Done
Karoge Lotunguna Lokaburu | Roads | 2014/15 | N:02°24.650´, E:035° 33.141´ | 2820120 | Lokichar | Turkana South |  | West Mint |  | 23-6-2015 | 42284 |  |  |  | 1 | Yes | Heavy Grading,Road Has Been Completed
Lokaburu Kanaodon Road | Roads | 2014/15 | N:02°23.656´, E:035° 25.489´ | 2635200 | Lokichar | Turkana South |  | Kaile Investment Co Ltd | [7 empty] | Yes | Light Grading Done
| Roads | 2014/15
Spot Improvement Makutano-Lokitaung | Roads | 2014/15 |  | 24985820 | Nakalale-Lapur-Kaeris | Turkana North |  | Kare Construction Co Ltd | 714000000 | [5 empty] | 1 | Yes | There Are Sign Posts Erected But The Road Has Been Done At Some Places And At Other Places Is Not
Naurugori Losajait Road | Roads | 2014/15 |  | 1641740 | Nakalale Word | Turkana North |  | Natedelim Construction Co Ltd |  | 42200 | 42292 |  |  |  | 1 | Yes | The Road Had Been Graded But The Soil Is Very Loose And Dusty
Nakapelikuruk-Nadunga Road | Roads | 2014/15 |  | 2847800 | Kaeris Ward | Turkana North |  | Moru- Edou Invest |  | 42200 | 42292 |  |  |  | 1 | Yes | The Road Has Been Done But Its Very Dusty….Not Passable By Vehicle That Are Not Four Wheeled
Kaeris-Kalopeta Road | Roads | 2014/15 | 03⁰37.27'n 035⁰18.645'e | 2744400 | Kaeris Ward | Turkana North |  | Sena Gen Construction & Supp Co Ltd |  | 42200 | 42292 |  |  |  | 1 | Yes | The Sign Post Is Erected And The Road Is Like It Nwas Graded Along Time Ago
Sesame-Kabulkok-Karioreng Road | Roads | 2014/15 | 04⁰30.866'n 035⁰44.843'e | 1936620 | Lapur Ward | Turkana North |  | Jonice Investment Ltd |  | 42200 | 42292 |  |  |  | 0.05 | Yes | Nothing Has Been Done On The Road At All Except For The Signpost Erected
Spot Improvement Narengewoi- Riokomor Road | Roads | 2014/15 | 04⁰06.382'n 035⁰43.222'e | 2265480 | Lakezone | Turkana North |  | Nangorikitoe Inv Ltd |  | 42200 | 42292 |  |  |  | 1 | Yes | The Road Is Completely Done But Very Poorly Done
Kachoda- Riokomor Road | Roads | 2014/15 | 04⁰07.639'n 035⁰43.123'e | 2272788 | Lapur Ward | Turkana North |  | Jerman Contractors |  | 42200 | 42292
| Roads | 2014/15
Kaikor- Kangakala- Lobur Road | Roads | 2014/15 | N 04°27.987', E 035°27.786' | 3557996.8 | Kaikor | Kibish | [6 empty] | 3220197.12 | 357799.68 | 1oo% | Yes | Complete And In Use. Well Levelled.
Kaikor-Lokiyoto-Loruth Road | Roads | 2014/15 | N 04°27.237', E 035°21.058' | 3641889.8 | Kaikor | Kibish |  | Synchtolyte Gen. Contractors Ltd |  |  |  |  | 3227701 | 364189 | 1 | Yes | Project Completed And It Is In Use. It Has Been Well Levelled.
Napak- Lokulan- Natelo Road | Roads | 2014/15 | N 04°51.851', E 035°23.238' |  | Kibish | Kibish |  | Lokaingole Contractors Ltd |  | 2014 | 12th Of Sept 2015 |  |  |  | 1 | Yes | Project Completed And It Is In Use. It Has Been Well Levelled.
Lokamarinyang - Soya Road | Roads | 2014/15 | N 05°01.140, ',E 035°35.490' |  | Kibish | Kibish |  | Inyang Gen. Contractors |  | 2014/2015 | 12th Sep 2015 |  |  |  | 0.3 | No | Project Started But Not Yet Completed.
| Roads | 2014/15
Lorengsinyon Drift | Roads | 2014/15 | N 03°32.733ʼ E 034°48.216 |  | Letea | Turkana West |  | Nanam Construction Ltd |  | 28/7/2015 | 28/10/2015 |  |  |  | 0.4 | No | Signpost Present But Not Fixed Trenches Done And Gabion Structures Made But Not Filled
Kakuma-Komudei | Roads | 2014/15 | N 03°42.616ʼ E 034°52.069́ʼ |  | Kakuma | Turkana West | [8 empty] | 1 | Yes | Complete
Kangitesiroi-Kanakuriny | Roads | 2014/15 | N 03 °52.267ʼ E 034°56.105ʼ |  | Lopur | Turkana West | [8 empty] | 1 | Yes | No Signpost Not Well Done
Lopur-Kangitesiroi | Roads | 2014/15 | N 03°51.325́́ E 034°49.453ʼ |  | Lopur | Turkana West | [8 empty] | 1 | Yes | No Signpost
Lomidat-Ekaburu | Roads | 2014/15 | N04°08.144ʼ E034°26.803ʼ |  | Songot | Turkana West |  | Kaliou Contractors Ltd | [8 empty] | Not Complete Not Per Specification
Teremukus-Naremeto | Roads | 2014/15 | N04°06.269ʼ E034°27.784ʼ |  | Songot | Turkana West | [8 empty] | 1 | Yes | Complete
Loki- Lokichar-Ekope | Roads | 2014/15 | N04°12.386ʼ E 034°20.460ʼ | 7900000 | Lokichoggio | Turkana West |  | Lorado Contractors Ltd | [6 empty] | 1 | Yes | Insecurity
Lokichar-Loruth Maintenance | Roads | 2014/15 | N03°37.414ʼ E035°02.748 |  |  | Turkana West |  | East Africa Co. Ltd |  |  | 31/7/2015 |  |  |  | 100 | Yes | Clearance/No Murram/Gravel
Aposta Lokangae | Roads | 2014/15 | N04°01.046ʼ E034°32.901 |  | Songot | Turkana West |  | Lele Inv Co. Ltd |  | 15/11/2014 | 42037 |  | 2129760 | 1419840 | 1 | Yes
Nanam-Nakaleso | Roads | 2014/15 | N04°12.747ʼ E034°33.679ʼ |  | Nanam | Turkana West |  | Rabbi Building Cont |  | 42011 | 31/7/2015 |  |  |  | 1 | Yes
Oropoi-Uganda Road | Roads | 2014/15 | N03°50.900ʼ E034°34.824ʼ |  | Songot | Turkana West |  | Akajere Gen Const&Supp |  | 13/7/2015 | 42287 |  |  |  | 1 | Yes
Renovation of UN camp Lokichogio | F$P | 2013/2014 | N04⁰12.465' E034⁰21.908' ELV 626m |  | Lokichogio | Turkana West | Lokichogio UN Camp | [5 empty] | 1 | Yes | Project complete and operational
Renovation- 4 blocks of 2 units each | F$P | 2014/2015 | N04⁰12.465' E034⁰21.908' ELV 626m | 36263314.23 | Lokichogio | Turkana West | Lokichogio Un Camp | Rudolf construction co LTD | [5 empty] | NO | The team didn’t find renovation project. There was a new construction of 4 blocks 2 units each. The project manager was not involved. The client to provide committee with information on payment regarding the project.
Construction of Lokichogio Slaughter House | F$P | 2013/2014 | N04⁰12.644' E034⁰21.225' ELV 660m |  | Lokichogio | Turkana West | Lokichogio | [5 empty] | 1 | yes
Construction of Kakuma Slaughter House | F$P | 2013/2014 |  |  | Kakuma | Turkana West | [6 empty] | 0 | NO | The team could not find the project in kakuma
Installation and Fabrication of Cess Barriers | F$P | 2013/2014 |  |  | Kakuma | Turkana West | Kakuma
Lokori Slaughter House | F$P | 2013/2014 | N01⁰57.108' E035⁰01.526' |  | Lokori/Kochodin | Turkana East | Lokori Town | [5 empty] | 1 | No | Main structure complete. Latrines done. Water tanks supplied but not installed. The facility needs labeling.
Nanam Borehole | WIA |  | N04⁰12.528' E034⁰33.603' EL 559m | 1694000 | Nanam |  | Nanam Village | Sagal Petrol Station |  |  |  |  | 0.5 | No | The borehole has been drilled but havent been equipped
Nanam Waterpan | WIA |  |  |  | Nanam |  | Nanam Village | [5 empty] | 0 | No | Nothing has been done up to now
Nanam Borehole | WIA |  | N04⁰12.631' E034⁰33.218' EL 566m |  | Nanam |  | Nanam Village | [5 empty] | 1 | No | The borehole was drilled but thre is no water
Songot Waterpan | WIA |  | N04⁰12.631' E034⁰33.218' EL 566m | 9259310 | Songot |  | Naremeto | Nawasin Co Ltd |  |  |  |  | 0.5 | No | The project is stalled
Songot Borehole | WIA |  | N04⁰01.028' E034⁰32.687' | 2608000 | Songot |  | Lokudule | Turkana Quarry Services |  |  |  |  | 1 | Yes | The project is complete and there is water and a water trough
Lookulan Waterpan | WIA | [13 empty] | NOT DONE
Atiir Borehole | WIA | [13 empty] | NOT DONE
Namon (Kanakuring) Waterpan | WIA |  |  |  | Songot |  | Kanakuring | [6 empty] | No | Incomplete
Letea Waterpan | WIA |  |  |  | Letea |  | Lomosing Ekori | [6 empty] | No | Incomplete
Lomukur Waterpan | WIA |  |  |  | Letea |  | Lomukor | [6 empty] | No | Yet to be done
Letea Borehole | WIA |  | N03⁰30.884' E034⁰48.463' EL 654m |  | Letea |  | Letea Village | [5 empty] | 0.5 | No | Drilled and capped equipment not installed
Loita Sonyok Borehole | WIA |  |  |  | Letea |  | Loita Sonyok Village | [5 empty] | 0.5 | No | Drilled and capped equipment not installed
Nakitongo Borehole | WIA |  |  |  | Letea |  | Nakitongo | [7 empty] | Was drilled but water wasn’t found
Lokichogio W/S Kakuma W/S Oropoi, Lomidat, Lopiding,Kalobeyei | WIA |  |  |  | Songot, Lokichosio And Kalobeyei |  |  | Mwia | [5 empty] | No | Ongoing
Komunyaate Borehole | WIA |  |  |  | Lopur |  | Kamunyaate | Ministry Satff And Lokichogio Water Providers | [5 empty] | No | Drilling complete yet to equip the borehole
Kakuma Water Supply | WIA |  |  | 13524010 | Kakuma |  |  | To Be Sourced After Evaluation | [5 empty] | No | Tendering stage
Lokichogio Water Pan | WIA |  |  | 9238240 | Lokichogio |  | Lokichogio | Yedida Investment Contractors | [5 empty] | No | Stalled
Nataparelim Waterpan | WIA |  |  | 9125600 | Kalobeyei |  | Nataparelim | Morutena Investment Ltd | [5 empty] | No | Stalled at 59% complete, dozer not on site
Kakuma Water Pan | WIA |  |  | 9120105 | Kakuma |  | Kakuma | Kaliou Enterprise Ltd | [5 empty] | No | Stalled at 31%, dozer not on site
Lopur Waterpan | WIA |  |  | 9224900 | Lopur |  | Lopur | Kotome Building And Enterprise Ltd | [5 empty] | No | Contractor yet to request for assessment to be done
Lomosingekori Waterpan | WIA |  |  | 9408760 | Letea |  | Letea Village | Kochodae Building Construction Ltd |  |  |  |  | 0.6 | No | The contractor is yet to make arrangement for assessment to be done.
Nataparelim Waterpan | WIA |  |  | 9125600 | Kalobeyei |  | Nataparelim | Morutena Investment Ltd |  |  |  |  | 0.59 | No | Stalled, dozer not on site
Nariemeto Waterpan | WIA |  |  | 9259310 | Songot |  | Naremeto | Nawasin Co Ltd |  |  |  |  | 0.38 | No | Stalled, dozer on site but believed to be spoilt and not in working condition.
Kapetadie Water Supply | WIA |  |  | 20000 | Nanam |  | Nanam Village | Ministry Staff | [5 empty] | No | Not operational, insecurity
Arengoit Borehole | WIA |  |  | 2229990 | Lokichogio |  |  | Bon Borehole Drillers | [6 empty] | Another site has been surveyed, the office to support the contractor to drill a replacement.
Naiperkar Borehole | WIA |  |  | 2700000 | Songot |  | Naiperkar | Tiwae Investment Co Ltd | [5 empty] | No | The borehole equiped with handpump but will be equiped with agenset. Design works complete
Natir-Lokangae Borehole | WIA |  |  | 2620800 | Songot |  | Lokangae | Ekanyarit Cons Supplies | [5 empty] | No | Another site has been surveyed, the office to support the contractor to drill a replacement.
Lokabuk Borehole | WIA |  |  | 2538900 | Kalobeyei |  | Lokabuk | Eitanit Consultancy And Drilling | [5 empty] | No | Another site has been surveyed, the office to support the contractor to drill a replacement.
Lopuski Borehole | WIA |  |  | 2291100 | Lopur |  | Lopur | Hussen Hand Pumps Repairs | [5 empty] | No | Bore hole collapsed. The office to support the contractor to drill a replacement borehole
Nakoyo Borehole | WIA |  |  | 2620800 | Lopur |  | Nakoyo | Solar Tech Company | [5 empty] | No | Dry, the contractor supported to drill a replacement borehole where the office has surveyed
Nakiteng,O Borehole | WIA |  |  | 2635269 | Letea |  | Nakiteng,O | Baraka Contractors | [5 empty] | No | The office has planned to equip the boreholes in the first and second week of december
Loitasonyok Borehole | WIA |  |  | 2620800 | Letea |  | Loita Sonyok Village | Mt Pelekech Contractors | [5 empty] | No | The office has planned to equip the borhole in december 2015
Natiir Nadung,A Borehole | WIA |  |  | 2700000 | Kakuma |  | Natiir | Lopiding Building And Construction Ltd | [5 empty] | No | Drilling complete yet to equip the borehole
Natiir Asekon Borehole | WIA |  |  | 2457630 | Kakuma |  | Natiirasekon | Rasabana Enterprise Ltd | [5 empty] | No | Drilling complete. The office is planning to equip the borehole in december 2015
Kalobeyei Borehole | WIA |  |  | 2175000 | Kalobeyei |  | Kalobeyei | Lorengesinyen Company Ltd | [5 empty] | No | Drilling complete. The office is planning to equip the borehole in december 2015
Letea Borehole | WIA |  |  | 2560000 | Letea |  | Letea Village | Mayandakimonent | [5 empty] | No | Drilling complete. The office is planning to equip the borehole in december 2015
Kipeto Borehole | WIA |  |  | 2206000 | Songot |  | Kipeto | Turkana Quarry Services | [5 empty] | No | Drilling on going
Mogilla Borehole | WIA |  |  | 2240000 | Nanam |  | Nanam Village | Sagal Petrol Station | [5 empty] | No | Drilling complete. The office is planning to equip the borehole in december 2015
Lopur (Komunyaate) Borehole | WIA |  |  | 2250000 | Lopur |  | Komunyaate | Nabek Const And Supplies Ltd | [5 empty] | No | Ongoing, the office has planned to equip the borehole in december
Naporoto Sand Dam | WIA |  |  | 9669516 | Kalobeyei |  | Naporoto | Lomidat Constr Co Ltd | [5 empty] | No | Stalled, the office has served the contractor with a difault notice
Kochomin Rock Catchment | WIA |  |  | 6284300 | Lokichogio |  | Kochomin | Ngilopechek Inv Co Ltd | [5 empty] | No | Stalled, the office has served the contractor with a difault notice
Lomidat Rock Catchment | WIA |  |  | 8114380 | Songot |  | Lomidat | Ekaburu Construction Co Ltd | [5 empty] | No | Stalled, the office has served the contractor with a difault notice
Improvement Of Kalobeyei Water Supply | WIA |  |  | 500000 | Kalobeyei |  | Kalobeyei | To Be Sourced After Evaluation
Construction Of Napeikar Water Supply | WIA |  |  | 7000000 | Songot |  | Napeikar | To Be Sourced After Evaluation
Lokori/Kochodin Water Pan Fy 2014/15 | WIA |  | N02⁰09.194' E035⁰49.535' |  | Lokori/Kochodin |  | Katamanak | Akide |  |  |  | - | 0.7 | Yes | The pan has water 30% its volume. There is evidence of silting from earlier rains. The project is not fenced.
Lokori Aic Borehole Fy 2013/14 | WIA |  | N01⁰56.620' E036⁰01.964' | 2715386 | Lokori/Kochodin |  | Lokori Aic | African B/H Company |  |  |  | 2715386 | 1 | No | Drilling and testing done. Output 12 M³/Hr. Transferred from Katamanak. The project is to benefit Kang'itit Girls Secondary, Polytechnic, Lokori Primary School, Health Centre and part of Town.
Rehabilitation Of Lokori Borehole | WIA |  | N01⁰57.067' E036⁰01.601' |  | Lokori/Kochodin |  | Lokori |  |  |  |  | - | 1 | No | Solar panels and pumps installed, The Bore Hole collapsed, The pannels were taken back for storage
Rehabilitation Of Lokri Main Borehole | WIA |  | N01⁰57.425' E036⁰02.721' |  | Lokori/Kochodin |  | Lokori |  |  |  |  | - | 1 | Yes | Pump and controller supplied. Solar pannels installed. Output is 12 M³/Hr. The borehole serves Lokori town.
Katilia Ward Water Pan | WIA |  | N02⁰18.072' E036⁰07.927' |  | Katilia |  | Lopeduru | Natorube Co Ltd |  |  |  | - | 1 | No | Presipitation low. Need for more inlet channels to feed the water pan. The facility is fenced with barbed wire.
Equiping Of Elelea Borehole | WIA |  | N02⁰06.659' E036⁰09.974' |  | Katilia |  | Elelea |  |  |  |  | - | 1 | Yes | Installation of solar pump and 34 solar pannels done. Output is 15 M³/Hr. Drilling and fencing had earlier been done by World Vision. There is need for another fence. 3 solar pannels were recently stollen.
Lokori/Kochodin Borehole | WIA | 2014/15 | N01⁰58.104' E036⁰06.105' | 2473905 | Lokori/Kochodin |  | Lokwii | Parakati Con Co Ltd |  |  |  | 2473905 | 0.8 | No | Drilling and testing done. Output 4.5 M³/Hr. Solar pump and solar pannels installed. Four pannels were recently stollen. There is need for fencing and securing the pannels with angle lines & raising them higher.
Lokori Borehole | WIA |  | N01⁰58.411' E036⁰05.209' |  | Lokori/Kochodin |  | Nadoto |  |  |  |  | - | 1 | No | Drilling and testing done. Output 2.2 M³/Hr.
Ngeu Borehole | WIA | 2013/14 |  | 2859150 | Katilia | [6 empty] | 2859150
Site No. 1 | WIA | 2013/14 |  | 2359000.35 | Katilia | [6 empty] | 2359000.35
Kamuge Borehole Fy 2013/14 | WIA |  |  | 2549000.4 | Lomelo/Napeitom | [6 empty] | 2549000.4 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Kakitei Borehole | WIA | 2013/14 |  | 2481700 | Lomelo/Napeitom | [6 empty] | 2481700 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Lomelo/Napeitom Water Pan | WIA | 2014/15 |  | 9622084 | Lomelo/Napeitom |  |  | Bellaack General Con & Suppliers Ltd |  |  |  | 9622084 | 0.5 | No | The team could not visit the site for security reasons. Information from water department states that the pan stalled at 50% intended volume of work due to breaking down of the doozer. The committee rocommended the team to visit the projects.
Equiping Of AIC Mission Compound Borehole | WIA | 2015/16 |  | 7-8 Million (Estimates) | Lokori/Kochodin |  | Lokori Aic Mission | In Tender | N/A | N/A | N/A | N/A | 0 | No | Tender advertised and opened. Evaluation and awarding to be done before 2015 Christmas break (Information from the Department of Water).
Flushing And Testing Of Lomelo And Napeitom Boreholes | WIA | 2015/16 |  | 2500000 | Lomelo/Napeitom |  | Lomelo And Kapedo | Bon Drillers | [5 empty] | No | Samples taken to laboratory. Survey/consultancy work on-going to inform the construction of desalination plants in both Lomelo and Kapedo. Intended beneficiaries are 4,000 (Information from the Department of Water).
Supply Of Water Tanks At Lomelo | WIA | 2015/16 |  | 624000 | Lomelo/Napeitom |  | Lomelo | Koibos General Contractors | [5 empty] | No | 2No. 10M³ plastic tanks supplied and installed. 500No. 20-Ltrs Jeericans and 500 Kg Chlorine were to be supplied.(Information from the Department of Water).
Drilling Of Boreholes | WIA | 2015/16 |  | 16-17 Million (Estimates) | Lokori/Kochodin, Lomelo/Napeitom And Katilia |  |  | In Tender | N/A | N/A | N/A | N/A | 0 | No | Tender advertised and opened. Evaluation and awarding to be done before 2015 Christmas break (Information from the Department of Water).
Drilling And Equiping Of Napeitom Borehole. | WIA |  |  | 2465000 | Lomelo/Napeitom |  | Ngatieket | Echami Turkana Company | [6 empty] | Equiping is subject to water quality report which has not been supplied by the contractor. (Information from the Department of Water).
Equiping Of Morulem Secondary Borehole With Solar Pump. | WIA |  |  | 1928000 | Lokori/Kochodin |  | Morulem | Fountain VENT | [6 empty] | Solar pump installed. Piping and construction of the water was to be done and LSO had already been issued. (Information from the Department of Water).
Drilling And Equiping Of Kamuge Borehole | WIA |  |  | 2549000 | Lomelo/Napeitom |  | Kamuge | Silale Investment Co Ltd | N/A | N/A | N/A | N/A | 0 | No | Not yet drilled. Rig failed to reach site because of steep hill. Contractor requested to source capable driller. (Information from the Department of Water).
Drilling And Equiping Of Nadoto Borehole | WIA |  |  | 2473905 | Lokori/Kochodin |  | Nadoto | Parakati Con Co Ltd | [6 empty] | Borehole drilled but dry. Contractor requested to look for an alternative site. (Information from the Department of Water).
| WIA | [13 empty] | (Information from the Department of Water).
Kaeris Borehole | WIA |  | N 03° 58.798' E 035° 28.855 /677M | 2550500 | Kaeris Ward |  | Kaeris | Loitangole Ent Ltd |  |  |  |  | 0.6 | Not yet | Yet to be equipped/installed
Kaikor Borehole | WIA |  | N 04° 30.559' E 035° 25.931 | 2515690 | Kaaleng/Kaikor |  | Kaikor Secondary | Kabarait Ltd |  |  |  |  | 0.6 | No | Already there but not installed water equipment
Lokumai II Borehole | WIA |  | N 04° 26.520' E 035° 35.585' /541 M | 2972130 | Kaaleng/Kaikor |  | Lokumai Ii | [5 empty] | 1 | Yes | Good sate/complete
Liwan Waperpan | WIA |  | N 04° 55.865' E 035° 41.740' /383 M |  | Lapur |  | Liwan | [5 empty] | 0.4 | No | Construction on-going
Nabulkok Borehole | WIA |  | N 04° 31.191' E 035° 41.756' /468 M | 2670150 | Lapur |  | Nabulkok | Nameturan Inve Ltd |  |  |  |  | 1 | Yes | Operational
Lokalale Akwaan Borehole | WIA |  | N 04° 20.812' E 035° 36.648' /586 M | 2450000 | Lapur |  | Kachoda | Nabek Constr Suppl Ltd |  |  |  |  | 1 | Yes | Operational,high yield,good work
Kaloyara Borehole | WIA |  | N 04° 01.645' E 035° 47.064' /454 M | 2203188 | Lakezone |  | Kaloyara/Narengewoi | Narina Inv Co Ltd |  |  |  |  | 1 | Yes | Operational
Kataboi Water Storage Tank | WIA |  | N 03° 44.970' E 035° 47.314' /490 M |  | Lakezone |  | Kataboi | [5 empty] | 1 | Yes | Good condition and fully operational
Naduat Borehole | WIA |  | N 03° 30.677' E 035° 11.207 /669M | 2450500 | Nakalale |  | Naduat | Ekanyarit Constr |  |  |  |  | 0.85 | No | Not completed fully
Nariokotome Borehole | WIA |  | N 04° 08.086' E 035° 54.261 /381M |  | Lakezone |  | Nariokotome | [5 empty] | 1 | No | Not operational,requires repairing
Todonyang Waterpan | WIA |  | N 04° 26.830' E 035° 54.863 / 408M |  | Lakezone |  | Todonyang | [5 empty] | 0.1 | No | Preliminary work only,duplication of the project next to the diocese of lodwar pan
Construction Of Losajait Water Pan | WIA |  |  | 10070482 | Nakalale |  | Losajait | Ekanyarit Atoo Entr. | [6 empty] | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
Construction Of Kanakurudio Water Pan | WIA |  |  | 8406930 | Kaeris |  | Kanakurudio | Miembo Con Suppliers Ltd. | [6 empty] | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
Kalochanapus Water Pan | WIA |  |  | 9504360 | Kaaleng/Kaikor |  | Kalochanapus | Ledo Con & Suppliers | [6 empty] | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
Equiping Of Naduat Borehole With A Handpump | WIA |  | N 03° 30.677' E 035° 11.207 /669M | 336000 | Nakalale |  | Naduat | The Installation Was Done By The Ministry | [5 empty] | No | Equiped awaiting commissioning
Flushing Of 2 No.Boreholes And Test Pumping Kariobok Borehole | WIA |  |  | 450000 | Nakalale | [8 empty] | No | Under procurement process
Equiping Of Locherengan Borehole With Submersible | WIA |  |  | 280000 | Lapur | [8 empty] | No | Under procurement process
Iprovement Of Kataboi Water Supply | WIA |  |  | 2000000 | Lakezone |  | Kataboi | To Be Sourced Through Raising Quotations | [5 empty] | No | Under procurement process
Improvement Of Lokitaung Water Supply | WIA |  |  | 7000000 (Estimate) | Lapur |  | Lokitaung | [6 empty] | No | Under procurement process
Improvement Of Kibish Water Supply | WIA |  |  | 7000000 (Estimate) | Kibish Ward |  | Kibish | [6 empty] | No | Under procurement process
Improvement Of Nachukui Water Supply | WIA |  |  | 5000000 (Estimate) | Nachukui | [8 empty] | No | Under procurement process
Improvement Of Loarengak Water Supply | WIA |  |  | 5000000 (Estimate) | Loarengak |  | Loarengak | [6 empty] | No | Under procurement process
Kaaleng Waterpan | WIA |  |  |  | Kaaleng/Kaikor |  | Natudao | [6 empty] | No | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
WIA
Nanam Dispensary | Health | 2014/15 | N04⁰12.623' E034⁰33.779' ELV 550m | 7396473 | Nanam |  | Nanam Centre | Brinkley Logistics |  |  |  | 7396473 | 0.99 | No | Yet to install window panes
Nanam Matternity Ward | Health | 2013/2014 | N04⁰12.611' E034⁰33.800' ELV 556m | 9800000 | Nanam |  | Nanam Centre |  |  |  |  | 9800000 | 1 | Yes | The project is complete and in use
AIC Lopiding Subcounty Hospital Renovation | Health | 2013/2014 | N04⁰12.109' E034⁰23.028' ELV 632m | 9901504 | Nanam |  | Lopiding | Wamwa Trading Co LTD |  |  |  | 9901504 | 1 | Yes | Painting, door replacements tiling the flours, ceilings repairs, piping and roof repairs, this repair were done on OPD theatre, one ward and office
Loteteleit Dispensary | Health | 2014/2015 | N04⁰12.321' E034⁰20.852' ELV 651m | 7500000 | Lokichogio |  | Lokichogio AIC Compound | Ekanyarit Atoo enterprise |  |  | 3000000 | 4500000 | 0.7 | No | The project is incomplete, not painted, the flour is cracking, no window panes and has been built on private property, the relevant department to come up with a clear managenent and operation plan
Teremkus Dispensary | Health | 2014/2015 | N04⁰06.272' E034⁰28.044' ELV 613m | 7130033 | Songot |  | Teremkus | Turkana Quarry services LTD |  |  | 4991023.14 | 2139009.86 | 0.9 | No | No toilet, yet to put ceiling board, painting. The project is stalled, no contractor on site
Aposta Dispensary | Health | 2014/2015 | N04⁰09.369' E034⁰25.408' ELV 620m | 7452999 | Songot |  | Aposta Village | Super Mogilla inv co LTD |  |  | 7452999 | - | 0.95 | No | Contracter on site, yet to do wiring and then install window panes, there is another similar facility built by a development partner within the vicinity.
Nakururum OPD block | Health | 2013/2014 | N03⁰59.711' E034⁰32.708' ELV 641m | 9800000 | Songot |  | Nakururum |  |  |  | 9800000 | - | 1 | Yes | The project is complete and in use. Commissioned in sep 2015. No signange
Nalapatui Dispensary | Health | 2014/2015 | N03⁰48.738' E034⁰35.848' ELV 784m | 7459515 | Kalobeyei |  | Nalapatui | Epolot ere construction co LTD |  |  | 7459515 | - | 1 | No | The contractor to repaint, there is need for provision of plumbing and solar power. The project is ready for commissioning. No signange
Lonyuduk Dispensary | Health | 2014/2015 | N03⁰42.548' E034⁰36.324' ELV 676m | 7456515 | Kalobeiyei |  | Lonyuduk | Turkana west Technical |  |  | 5215360.5 | 2241154.5 | 1 | No | Yet to do wiring, and repainting. Ready for commissioning. No signage
Komudei Dispensary | Health | 2014/2015 | N03⁰43.565' E034⁰52.913' ELV 609m | 7575200 | Kakuma |  | Komudei Village | Pelekech LTD |  |  | 6060160 | 1515040 | 1 | No | The project is complete, no signage. Yet to be commissioned.
Nasinyono Dispensary | Health | 2014/2015 | N04⁰17.793' E034⁰57.450' ELV 495m | 7950000 | Songot |  | Nasinyono | EMV Holdings LTD |  |  | 5565000 | 2385000 | 0.5 | No | The project is stalled, the contractor is not on site, the community is complaining that the workers who were working on site havent been paid, project manager to issue a default notice
Lokangae Dispensary | Health | 2013/2014 | N04⁰06.682' E034⁰53.363' ELV 519m | 2900000 | Songot |  | Lokangae | Katamanak gen constr co ltd |  |  |  | 2900000 | 0.8 | No | The contractor has done more work than originally agreed in the BQ, willing to complete and claim the actual cost. The project manager to guide on way forward.
Atiir OPD block | Health | 2013/2014 | N04⁰03.682' E034⁰52.769' ELV 530m | 6900000 | Songot |  | Lokangae |  |  |  |  | 6900000 | 1 | No | The ministry to replace collapsing ceiling, repaint and commission.
Namon Dispensary | Health | 2013/2014 | N04⁰00.253' E034⁰52.769' ELV 530m | 4900000 | Lopur |  | Namon |  |  |  |  | 4900000 | 0.99 | No | No waiting bench for the patients, the client ministry to organize for commissioning.
Lopusike Dispensary | Health | 2013/2014 | N03⁰51.496' E034⁰49.272' ELV 567m | 4900000 | Lopur |  | Lopur Village | Naita construction company |  |  |  | 4900000 | 1 | No | Notable cracks on the floor, walls and collapsing ceiling.The project manager to instruct the contractor to rectify
Kangitesroi Dispensary | Health | 2014/2015 | N03⁰52.639' E034⁰56.859' ELV 573m | 7439201 | Lopur |  | Kangitesroi | Urum construction and engineering co ltd |  |  | 5207440.7 | 2231760.3 | 0.5 | NO | Site abandoned, all material to completion are on site, the project manager to ensure the contractor finishes to project.
Nakoyo Dispensary | Health | 2014/2015 | N03⁰42.687' E034⁰47.411' ELV 614m | 7871999 | Lopur |  | Nakoyo | Napek construction and supp ltd |  |  | 5510399.3 | 2361599.7 | 0.8 | No | Contractor on site, project at the finishes level.
Pokotom Heath Centre | Health | 2013/2014 | N03⁰36.786' E034⁰49.315' ELV 627m | 9800000 | Kakuma |  | Pokotom Village | Rasabana Enterprise LTD |  |  | 9800000 | - | 1 | No | Project complete, to be taken over by client, contractor in default in another contract with TCG and therefore his retention be withheld untill he makes good the default.
Loreng Dispensary | Health | 2014/2015 |  | 7322532 | Letea |  | Loreng | Nakwama gen contractors |  |  | 5125722 | 2196810 | 0.8 |  | Team unable to reach site due to security concerns. Dispensary complete, staff house at roofing level, the contractor on site as informed by the ward admin
Kaameyan Dispensary | Health | 2014/2015 |  | 7500000 | Letea |  | Kaameyan | Ng'ilopechek Invest LTD |  |  | 7500000 | - | 0.8 | No | The contractor is onsite, doing plumbing and ceiling. Project ready for commissioning.
Letea OPD Block | Health | 2013/2014 | N03⁰31.068' E034⁰49.010' ELV 660m | 9800000 | Letea |  | Letea Village | Ekisil construction company limited |  |  | 9800000 | - | 1 | Yes | The project is in use
Lopeduru Dispensary | Health | 2013/2014 | N01⁰57.106' E036⁰01.530' | 6900000 | Katilia |  | Lopeduru | Achuma Contractors Ltd | 42535 | 42505 | 6900000 | 0 | 1 | Yes | Construction complete and serves an average of 25 patients per day. The medical staff include 2 nurses and 1 volunteer. There is need for equiping the facility with requisite equipments, running water and a fence. Notable defects; veranndar steel pillars are not holding the roof, poor ventilation in the maternity. Client to correct the defects.
Construction of staff quarters at Elelea Sub County Hospital | Health | 2014/2015 | N02⁰06.887' E036⁰09.171' | 10575000 | Katilia |  | Elelea | Ibus Turkan |  |  | 7402500 | 3172500 | 0.9 | No | 4 units staff houses complete with 2 units of latrines. Piping for water connection on going. There is need for fencing the facility. There is also a pressing need for more staff houses to accommodate the 12 staff members serving the facility.
Lotubae Dispensary | Health | 2014/2015 | N02⁰01.514' E036⁰07.541' | 7396473 | Lokori/Kochodin |  | Lotubae | Logistics Team Int Ltd |  |  | 5177531.1 | 2218941.9 | 0.8 | No | Part roofing for the dispensary done. Roofing for staff house complete. Steel windows and doors fitted. Escavation of the latrine done. The contractor was not on site. Project manager to follow up
Lokwii Dispensary | Health | 2013/2014 | N01⁰58.637' E036⁰06.327' | 9800000 | Lokori/Kochodin |  | Lokwii | Kodekode Contractors | 42535 | 42505 | 9800000 | 0 | 1 | Yes | The project is complete and commissioned. Maternity, Antenatal and Postnatal wings are in use. The facility is powered with solar energy and serves an average of 5-50 patients per day. The staff members comprise of 1 In Charge, 1 Clinical Officer, 2 Nurses and 1 CHEW.
Elelea Sub County Hospital | Health | 2013/2014 | N02⁰06.903' E036⁰09.111' | 2900000 | Katilia |  | Elelea |  | 42535 | 42505 | 2900000 | 0 | 1 | Yes | Completion works to the ESP modle Health centre. The hospital attends to an average of 30 patients per day. Staff members comprises of 3 Nurses, 2 Clinical Officers, 1 Medical Officers, 1 CHEW, 1 Volunteer and 2 Personal Assistants. By the time of the visit, the outreach programme had stopped for a month and the effect had already been felt.
Lomelo Dispensary | Health | 2013/2014 |  | 9800000 | Lomelo/Napeitom |  |  |  | 42535 | 42505 |  | 9800000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the project.
Napeitom Dispensary | Health | 2014/2015 |  | 7400902 | Lomelo/Napeitom | [6 empty] | 7400902 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the project.
Nakatongwa Dispensary | Health |  |  | 7650600 |  |  |  | Joeli Contractors |  |  |  | 7650600 |  |  | The team could not trace exact location of the dispensary.
Kikeunae Dispensary | Health |  |  | 7411320 |  |  |  | Ngapenderee |  |  |  | 7411320
Lomunyan Akwaan Dispensary | Health | [10 empty] | -
Naduat dispensary | Health | 2014/2015 | N 03° 30.855' E 035° 11.065' | 6900000 | Nakalale |  | Naduat | Kuchilchil contractors | 42535 | 42505 | 6900000 | - | 1 | no | The project is complete ready for commissioning
Losajait dispensary | Health | 2013/2014 | N 03° 37.153' E 035° 18.850' /637M | 2900000 | Nakalale |  | Losajait | Mugasi building & contractors |  |  | 2900000 | - | 1 | no | The project is complete ready for commissioning,there is need for pit latrine and staff house
Kaeris dispensary | Health | 2014/2015 | N 03° 58.798' E 035° 28.855 /677M | 7131600 | Kaeris |  | Kaeris | Almaso ent & const ltd | 42535 | 42505 | 7131600 | - | 1 | no | The project is complete,contractor to make good defects
Ekicheles dispensary | Health | 2014/2015 | N 04° 28.664' E 035° 26.960' /634M | 7575200 | Kaaleng/Kaikor |  | Ekichelees | lakika ntwork contrution & general suppliers | 42535 | 42505 | 6060160 | - | 0.8 | no | Construction on-going,workers on site,most of the materials on site
Kaaleng dispensary | Health | 2013/2014 | N 04° 22.478' E 035° 32.963' /607M | 9800000 | Kaaleng/Kaikor |  | Kaaleng | Kabarait builders & contractors |  |  | 9800000 | - | 1 | yes | The project was commissioned and use
Nakapelewoi dispensary | Health |  | N 04° 19.062' E 035° 26.001' /623M | 7459816 | Kaaleng/Kaikor |  | Nakapelewoi | Erex contractors | 42535 |  | 7459816 | - | 1 | no | Project is complete ready for commissioning
Karebur dispensary | Health | 2014/2015 | N 04° 26.133' E 035° 43.361' /536M | 7067290 | Lapur |  | Karebur | Jonice co ltd | 42535 | 42505 | 6360561 | - | 0.9 | no | The contractor to enhance ventillation and lighting on corridors,project manager to follow
Kokuro dispensary | Health | 2013/2014 |  | 9800000 | Lapur |  | Kokuro | moru koki & sons contractors |  |  | 7241268 | - | 1 | yes | The project is complete and in use
Napeikar dispensary | Health | 2014/2015 | N 04° 44.946' E 035° 39.781' /461M | 7591211 | Lapur |  | Meyan | morutena contractors | 42535 | 42505 | 5313847.7 | - | 0.7 | no | Noted some low quality blocks,project manger to act,contractor experiencing hostility from local community
Lokitaung sub county hospital pharmacy store and kitchen | Health |  | N 04° 15.746' E 035° 45.261' /745M | 11957674 | Lapur |  | Lokitaung | tilak hardware and tools | 42535 | 42505 | 8370371.8 | - | 1 | no | The project is complete waiting for commissioning
Riokomor dispensary | Health | 2014/2015 | N 04° 06.967' E 035° 43.228' /559 M | 7500049.6 | Lapur |  | Riokomor | rikomor inv ltd | 42535 | 42505 | 6750044.1 | - | 0.9 | no | No windows panes,toilet yet to be completed
Narengewoi health center | Health | 2013/2014 | N 04° 00.475' E 035° 51.067' /388 M | 9800000 | Lakezone |  | Narengewoi | nacet & sons contractors |  |  | 9800000 | - | 1 | yes | The project is in use though not fully equiped,client to work on remeding the defects
Lolupe dispensary | Health | 2014/2015 | N 03° 32.228' E 035° 14.392' /715 M | 7276271 | Nakalale |  | Lolupe | be-lochakai | 42535 | 42505 | 5093389.7 | - | 0.8 | no | The contractor on site,work progressing well
Nakitoe-kakumon dispensary | Health | 2014/2015 | N 04° 12.228' E 035° 21.614' | 7485526 | Kaeris |  | Nakitoe-Kakumon | Turkana hardware & constrution co. | 42535 | 42505 | 7485526 | - |  |  | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
Lopur Dispensary | Health | 2014/2015 |  | 7506256 | Lakezone |  | Lapur | Lakezone investment limited | 42535 | 42505 | 7506256 | - | 1 | no | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
Turkana West Market Renovation | TTI |  | N03⁰42.456' E034⁰51.734' | 1823878 | Kakuma |  | Kakuma Town | Rasabana Entr Ltd |  |  | 1823878 | 0 | 1 | yes | Project complete. Renovation works included painting, floor and roof repairs. Recommended for major renovations.
Lokori Market Stalls | TTI |  | N01⁰57.051' E035⁰01.830' | 10453259 | Lokori/Kochodin |  | Lokori Town | Lelar Inv Ltd |  |  | 10453259 | 0 | 1 | No | Project complete. Recommended for water connection, fencing, gate, toilet and a rubbish pit. Need for a revenue collection and revenue enforcement offices.
Loarengak Market Stalls | TTI | 2014/2015 | N 04° 16.795' E 035° 53.531' /380 M | 9889063.8 | Lakezone |  | Loarengak | Lapur Trading & Inv Co Ltd |  |  | 9889063.8 | 0 | 1 | no | Main structure complete.recommended for fencing,gate and a rubbish pit.need for revenue collection officers and revenue enforcement officers.water connection.guard rail
Kataboi Eco Lodge | TTI |  | N 03° 40.635' E 035° 49.941' /383 M | 66389746 | Lakezone |  | Lokitoeangaber | Kacheilap Gen.Contractors | 41957 | 42231 | 59750771.4 | 6638974.6 | 0.85 | no | Accomodation blocks near completion.dinning/ conference at roofing.fencing complete.contractor claim for variation for extra work
Nanam ECD | Education | 2014/2015 | N04⁰12.661'E034⁰33.644' EL 539m | 6000000 | Nanam Ward |  | Nanam Village | Jelaan Building And Construction & Supp | 42505 | 42416 | 5100000 | 900000 | 0.85 | No | Finishing works ongoing, no signage.
St Cosmas Napopongoit ECD | Education | 2013/2014 | N04⁰11.690'E034⁰23.931' EL 624m | 5412633.9 | Nanam Ward |  | Napopongoit Village | Lopiding Gen Construction Ltd |  |  |  | 5412633.9 | 0.5 | No | Project not complete, site abandoned. The project manager was not involved in this project. Client to liaise with office of the project manager for direction.
AIC Lopiding ECD | Education | 2014/2015 | N04⁰12.180'E034⁰23.515' EL 634m | 6000000 | Nanam Ward |  | Lopiding Village | Ato Gen Contractors | 42505 | 42416 | 6000000 | - | 1 | No | The project is complete. Ready to be commissioned
St Mathews Nadome ECD | Education | 2014/2015 | N04⁰11.814'E034⁰23.351' EL 628m | 3500000 | Nanam Ward |  | Lopiding Village | Logistics Team International | 42505 | 42416 |  | 3500000 | 0.8 | No | Costructions works ongoing
AIC Lokichoggio ECD | Education | 2013/2014 | N04⁰12.435'E034⁰20.713' EL 645m | 7500000 | Lokichogio Ward |  | Lokichoggio Centre | Mt Pelekech Contractors |  |  |  | 7500000 | 1 | Yes | Origal contract 100% complete, additional works was at 95% complete.
Teremkus ECD | Education | 2014/2015 | N04⁰06.344'E034⁰27.885' EL 627m | 5850000 | Songot |  | Teremkus | Nawik Contractors | 42505 | 42416 | 3510000 | 2340000 | 1 | No | Project is complete. Ready for commisioning.
Naremeto ECD | Education | 2013/20914 | N04⁰05.545'E034⁰32.932' EL 564m | 4320140.8 | Songot Ward |  | Naremeto | Aropa Investment Ltd |  |  | 4320140.8 | - | 1 | Yes | Project complete, ready for commissioning. Additional works recommended.
Lokudule ECD | Education | 2014/2015 | N04⁰00.839' E034⁰33.179' ELV 609m | 5948132 | Songot Ward |  | Lokudule | Lizton Ltd | 42505 | 42416 | 5948132 | - | 1 | Yes | Project complete, ready for commissioning.
Nakururum ECD | Education | 2014/2015 | N03⁰59.684' E034⁰32.631' ELV 644m | 5484100 | Songot Ward |  | Nakururum | Tode Contractors Ltd | 42505 | 42416 |  | 5484100 | 1 | No | Project complete except for the fence, ready to be commissioned.
Natiira ECD | Education | 2014/2015 | N03⁰53.200' E034⁰33.078' ELV 678m | 6000000 | Kalobeyei Ward |  | Natiira | Lomidat Construction Co Ltd | 42505 | 42416 | 3600000 | 2400000 | 0.7 | No | Contractor on site, works progressing well.
Oropoi ECD | Education | 2014/2015 | N03⁰48.817' E034⁰21.737' ELV 864m | 6000000 | Kalobeyei Ward |  | Oropoi | Eitanit Water Drilling And Construction Co Ltd | 42505 | 42416 | 3600000 | 2400000 | 0.5 | No | Site abandoned, project manager to follow up.
Nawotom ECD | Education | 2013/2014 | N03⁰48.734' E034⁰35.850' ELV 675m | 3500000 | Kalobeyei Ward |  | Nawotom | Lotikipi Investment Ltd |  |  |  | 3500000 | 1 | Yes | Project complete ready for commissioning, additional works recommended.
Kalobeyei ECD | Education | 2013/2014 | N03⁰46.383' E034⁰37.554' ELV 653m | 4320000 | Kalobeyei Ward |  | Kalobeyei | Aropa Investment Ltd |  |  |  | 4320000 | 1 | Yes | Project complete ready for commissioning, additional works recommended.
Komudei ECD | Education | 2014/2015 | N03⁰43.082' E034⁰52.344' ELV 608m | 6000000 | Kakuma Ward |  | Kakuma- Komudei Village | Laika Construction | 42505 | 42416 | 5400000 | 600000 | 0.98 | No | Project is complete excepy for fence, window panes.
Nabune ECD | Education | 2013/2014 |  |  | Kakuma Ward |  | Nabune |  |  |  |  | - | 1 | Yes | The project is complete and in use
NAMON ECD | Education | 2014/2015 | N04⁰00.166' E034⁰52.507' ELV 540m | 6000000 | Songot Ward |  | Namon | Natamakarwo Eng Ltd | 42505 | 42416 | 3600000 | 2400000 | 0.9 | No | Finishing works ongoing
LOPUR ECD | Education | 2014/2015 | N04⁰51.568' E034⁰49.101' ELV 570m | 6000000 | Lopur Ward |  | Lopur Centre | Behive Logistics Co Ltd | 42505 | 42416 | 5400000 | 600000 | 1 | No | Project complete except for the pit latrine finishes and classroom verandah. External paving to be redone,
KANGITESROI ECD | Education | 2013/2014 | N03⁰53.055' E034⁰56.918' ELV 571m | 3500000 | Lopur Ward |  | Kangitesroi |  |  |  | 3500000 | - | 1 | Yes | The project is complete and ready for commissioning additional works recommended.
LOMUNYANAKIRIONOK/ NGIJAWOI ECD | Education | 2013/2014 | N03⁰48.577' E034⁰53.451' ELV 592m | 3500000 | Lopur Ward |  | Ngijawoi | Kaisaki Building Contractors |  |  | 3500000 | - | 1 | Yes | The project is complete and ready for commissioning additional works recommended.
LOTAKA ECD | Education | 2014/2015 | N03⁰48.577' E034⁰53.451' ELV 592m | 6000000 | Kakuma Ward |  | Lotaka Village | Bluepower Construction Co Ltd | 42505 | 42416 | 4200000 | 1800000 | 0.9 | No | Finishes to the latrine outstanding, to put window panes and fence, the project manager to follow up.
LORENG ECD | Education | 2013/2014 |  |  | Letea |  | Loreng Village |  |  |  |  | - |  | No | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
LOKIPOTO ECD | Education | 2014/2015 |  | 5951612 | Letea |  | Lokipoto | Choroi Inv Ltd | 42505 | 42416 | 1785483.6 | 4166128.4 | 0 | No | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
TULABALANY ECD | Education | 2013/2014 |  | 3500000 | Letea |  | Tulabalany | Kakuma Building Entreprises |  |  |  | 3500000 | 1 | Yes | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
Akoros Loritit ECD | Education | 2013/2014 |  |  | Letea |  | Akoros | Kakuma Building Entreprises |  |  |  | - | 1 | Yes | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
Musug ECD | Education | 2014/2015 |  | 6000000 | Letea Ward |  |  | Kakuma Building Entreprises | 42505 | 42416 | 3600000 | 2400000
| Education |  | N02⁰05.814' E035⁰35.518' | 3500000 | Lokori/Kochodin |  | Lokicheda | Etich Bon Co Ltd | 42383 | 42474 | 3500000 | 0 | 0.9 | Yes | Classroom, Dining Hall and Kitchen complete. Need for supply of furniture. Floor needs rescreeding. Latrines 40% complete (Walling on going). Need for water connection to the ECD (Water tank within the school compound). Client to follow up with the project manager.
Construction of Lokwamosing ECD | Education | 2014/2015 | N01⁰59.544' E035⁰56.215' | 6000000 | Lokori/Kochodin |  | Lokwamosing | Ummatul Rahma Const | 42505 | 42416 | 6000000 | 0 | 1 | Yes | Construction of main structures complete. One more coat of paint needed. Fencing done. Project not yet handed over. The ECD is within a school compound and there is need for a urinal & more latrines for girls.
Construction of Lopeduru ECD | Education | 2014/2015 | N02⁰14.520' E036⁰07.586' | 6000000 | Katilia |  | Lopeduru | Lochar Emayan Contractors | 42505 | 42416 | 3600000 | 2400000 | 1 | Yes | Classroom, Dining Hall, Kitchen and Toilets done. The facility also has a gated fence. There need of clearing the site after construction to minimise injuries on pupils. The sinks for hand washing at the latrines well done. There is need for applying red oxide and ramping the strucutres to allow accessibility for all. It is located close to Lopeduru primary school. The contractor should clear the project site.
Construction of Lokorkor ECD | Education | 2014/2015 | N02⁰14.519' E036⁰07.582' | 6000000 | Katilia |  | Lokorkor | Kachilap Co Ltd | 42505 | 42416 | 6000000 | 0 | 1 | Yes | Classroom, Dining Hall, Kitchen and Toilets done. Need for running water in the facility. The classroom windows do not meet the safety standards. Need for ventilation louvres.
Construction of Katilia ECD | Education | 2013/2014 | N02⁰11.246' E036⁰07.324' | 3500000 | Katilia |  | Katilia |  | 42383 | 42474 | 3500000 | 0 | 1 | Yes | Classroom, Dining Hall, Kitchen and Toilets done. There is evidence of poor workmanship (paint falling off and floor scrapped). The Dinning Hall is not child friendly. There is need for repairs. Class in use but the Dinning is not functional (used as a dormitory for Katilia primary school). The facility is recomended for additional works.
Construction of Elelea ECD | Education | 2013/2014 | N02⁰06.427' E036⁰09.795' | 3500000 | Katilia |  | Elelea | Katilu Builders & Construction | 42383 | 42474 |  | 3500000 | 1 | Yes | Classroom, Dining Hall, Kitchen and Toilets done. The Dinning Hall floor is pealling off. There is need for equiping the facility with furniture. The classroom needs ceilling. The facility is also not fenced and there is no running water within. The client to forward the project to project manager for follow up.
Construction of Morulem ECD | Education | 2014/2015 | N02⁰01.143' E036⁰04.994' | 6000000 | Lokori/Kochodin |  | Nakwasinyen | Etau Build & Const Ltd | 42505 | 42416 | 6000000 | 0 | 1 | Yes | Project is complete and ready for commisioning. Poor accessibilty to the facility.
Construction of Nayanae Katon ECD | Education | 2013/2014 | N02⁰03.013' E036⁰07.829' | 3500000 | Katilia |  | Nayanae Katwan | Etich Bon Co Ltd | 42383 | 42474 |  | 3500000 | 1 | Yes | Project is complete and ready for commisioning.
Construction of Napeitom ECD | Education | 2013/2014 |  | 3500000 | Kapedo/Napeitom |  |  |  | 42383 | 42474 |  | 3500000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Construction of Kapedo ECD | Education | 2013/2014 |  | 3500000 | Kapedo/Napeitom |  | Kapedo | Silale Investment Ltd | 42383 | 42474 |  | 3500000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Construction of Lokidongoi ECD | Education | 2014/2015 |  | 6000000 | Kapedo/Napeitom |  |  |  | 42505 | 42416 |  | 6000000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Construction of Silale ECD | Education | 2014/2015 |  | 6000000 | Kapedo/Napeitom |  |  |  | 42505 | 42416 |  | 6000000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Construction of new ECD at Naduat | Education | 2014/2015 | N 03° 30.751' E 035° 11.954' | 6000000 | Nakalale |  | Naduat | Kuchulkuchil Build Const Co Ltd | 42505 | 42416 | 6000000 | - | 1 | No | Project complete awaiting commssioning,client ensure signage
Lokore ecd | Education | 2013/2014 | N 03° 30.905' E 035° 13.350' | 3500000 | Nakalale |  | Lokore | Kuchikuchil Contgractors |  |  | 3500000 | - | 1 | Yes | Project is complete,minor defects to be addresed by the client
Construction of new ECD at Losajait | Education | 2014/2015 | N 03° 37.278' E 035° 18.645' /637 M | 6000000 | Nakalale |  | Losajait | Napalakipor Inv Ltd | 42505 | 42416 | 6000000 | - | 1 | No | Project complete,inadequate fence chain link
Construction of new ECD at Ngaurenderia | Education | 2014/2015 | N 03° 56.764' E 035° 15.307' /569 M | 6000000 | Kaeris |  | Nadunga | Musuk Company | 42505 | 42416 | 6000000 | - | 1 | Yes | Project complete ready for commissioning
Construction of ECD at Kangakipur | Education |  | N 04° 01.951' E 035° 29.254' /696 M | 3500000 | Kaeris |  | Kanagkipur | Loitangole Investment |  |  | 3500000 | - | 1 | Yes | Project is complete,minor defects to be addresed by the client
Mlima tatu ecd | Education | 2013/2014 | N 04° 08.584' E 035° 28.136' /678 M | 3500000 | Kaeris |  | Mlima Tatu |  |  |  | 3500000 | - | 1 | Yes | Project complete and recomended for additional work
Nakapelewoi | Education | 2013/2014 | N 04° 19.062' E 035° 26.075' /632 M | 3500000 | Kaaleng/Kaikor |  | Nakapelewoi | Loitangole Investment |  |  | 3500000 | - | 1 | No | Client to address the defects on the windows and doors
Kaarubangorok ecd | Education |  | N 04° 26.868' E 035° 21.514' /572 M | 6000000 | Kaaleng/Kaikor |  | Loruth | Abdifatah & Siblings Company | 42505 | 42416 | 5400000 | 600000 | 0.85 |  | The classroom is not done to the standard design,pit latrine not complete,roofing for the dining hall is not complete,contractor has made a claim of variation on the basis of location,the project manager to address all this issue and report to commitee
Longelemwar ecd | Education |  | N 04° 31.750' E 035° 28.456' /625 M | 3500000 | Kaaleng/Kaikor |  | Longelemwar | Abdifatah & Siblings Company |  |  | 3500000 | - |  | Yes | Project is complete,client ministry to take care of the defects
Lokidongo ecd | Education | 2014/2015 | N 04° 25.956' E 035° 32.013' /592 M | 6000000 | Kaaleng/Kaikor |  | Lokidongo | Ledo Contractors & Suppliers Ltd | 42505 | 42416 | 4200000 | 1800000 | 0.7 | No | Projects on-going,most of the materrials on site
Lochwarengan ecd | Education | 2014/2015 | N 04° 23.406' E 035° 43.618' /609 M | 5330550 | Lapur |  | Loarengak | Nawonyei Gen.Constr And Supp Co Ltd | 42505 | 42416 | 3731385 | 1599165 | 0.6 | No | Project is on-going,most materials on site
Liwan ecd | Education | 2014/2015 | N 04° 53.971' E 035° 40.277' /407 M | 6000000 | Lapur |  | Liwan | Kopure Ent.Ltd | 42505 | 42416 | 5400000 | 600000 | 0.9 | Yes | Project complete except fencing and gate
Nabulkok ecd | Education |  | N 04° 31.007' E 035° 41.942' /476 M | 3500000 | Lapur |  | Nabulkok | Nameturan Investment Ltd |  |  | 3500000 | - | 1 | Yes | Project complete,additional work recomended,commissioning not done
Lochoredome ecd | Education | 2013/2014 | N 04° 15.893' E 035° 40.648' /588 M | 3500000 | Lapur |  | Kachoda | Lapur Construction Co.Ltd |  |  | 3500000 | - | 1 | Yes | Project complete,additional work recomended,commissioning not done
namorotot ecd | Education | 2013/2014 | N 04° 11.025' E 035° 54.098' /306M | 3500000 | Lakezone |  | Nadoupuwa | Hakika Foundation |  |  |  | 3500000 | 0.6 | No | Project is abandoned. Notable poor workmanship with collapsing walls.client to follow up with the project manager urgently (was not involved in the initial management of the project)
Nabeletakoit ecd | Education | 2014/2015 | N 04° 18.203' E 035° 53.518' /387 M | 6000000 | Lakezone |  | Loarengak | Napeget Co Ltd | 42505 | 42416 | 6000000 | - | 0.9 | Yes | Work complete save for fencing.project ready for commissioning
Kalosep ecd | Education | 2014/2015 | N 03° 49.093' E 035° 48.170' /419 M | 6000000 | Lakezone |  | Kalosep | Nasechabuin Co Ltd | 42505 | 42416 | 5400000 | 600000 | 0.9 | No | Pit latrine,gate,painting and dinning windows outstanding
Lokitoe angabeur ecd | Education | 2013/2014 | N 03° 46.587' E 035° 49.550' /388 M | 3500000 | Lakezone |  | Lokitoe Angaber | Kerman Company |  |  | 3500000 | - | 0.8 | No | Project abandoned at finishes stage.client to liase with project manager
kaaleng polytechnic | Education | 2014/2015 | N 04° 22.036' E 035° 32.562' /613 M | 9885844.8 | Kaaleng/Kaikor |  | Kaaleng | Kafia Company Limited |  |  | 8897260.3 | 988584.5 | 0.9 | No | Project complete safe for fencing and solar installation
kataboi youth polytechnic | Education | 2014/2015 | N 03° 45.117' E 035° 48.541' /409 M | 9771782 | Lakezone |  | Kataboi | Katiko Investments |  |  | 5863069.2 | 3908712.8 | 0.8 | No | Project is on-going.workers on site.project manager to check on pit latrine and mortar jointings
Nanam ward admin office | PSDDM |  | N04⁰12.988' E034⁰33.691' EL 576m | 9564620 | Nanam Ward |  | Nanam Centre |  |  |  | 9564620 | - | 1 | Yes | Client to ensure signage and maintain the facility, the project is complete and commissioned.
Lokichogio ward admin office | PSDDM |  | N04⁰11.333' E034⁰21.936' EL 640m | 13352191 | Lokichogio Ward |  | Lokichogio | Lojaam Luqa Energy |  |  | 12016971.9 | 1335219.1 | 0.8 | No | Project still ongoing, contractor on site, good work going, all materials were on site
Songot Ward Admin Office | PSDDM |  | N04⁰03.088' E034⁰31.665' EL 613m | 12544947 | Songot Ward |  | Aposta | Tiwae Inv LTD |  |  | 8781463.32 | 3763483.68 | 0.7 | No | Electrical works not done, the contractor is on site
Kalobeyei Ward Admin Office | PSDDM |  | N03⁰45.657' E034⁰37.945' EL 663m | 12488900 | Kalobeyei Ward |  | Kalobeyei Centre | Akanpich Building Co Ltd |  |  | 8742229.8 | 3746670.2 | 0.7 | No | The project is stalled. Finishes,openings and external works remaining. The directors of the contracted co are in a court dispute. The project manager to follow up, including issuance of default notice.
Kakuma Ward Admin Office | PSDDM |  | N03⁰42.610' E034⁰52.032' EL 607m | 11585001 | Kakuma Ward |  | Kakuma Town | Rasabana Ent Ltd |  |  | 8109792 | 3475209 | 0.6 | No | The project is stalled. Finishes,openings and external works remaining. The project manager to follow up, including issuance of default notice.
Lopur Ward admin | PSDDM |  | N03⁰51.453' E034⁰49.639' EL 566m | 11425340 | Lopur Ward |  | Lopur | Ekisil Co Ltd |  |  | 11425340 | - | 1 | No | Project complete, awaitng commisioning.
Letea Ward Admin Office | PSDDM |  | N03⁰31.304' E034⁰48.526' EL 650m | 9691164 | Letea Ward |  | Letea |  |  |  | 9691164 | - | 1 | Yes | Project complete
Lokori Ward Administrator's Office | PSDDM |  | N01⁰57.106' E036⁰01.530' |  | Lokori/Kochodin |  | Lokori Town | [5 empty] | 0.75 | No | Main works with undercoat paint done. Fencing and drainage also done. Placing of floor tiles on going.
Katilia Ward Administrator's Office | PSDDM |  | N02⁰07.428' E036⁰07.459' |  | Katilia |  | Katilia Town | Touchlife Co Ltd |  |  |  |  | 1 | No | Construction complete. Furniture supplied. The office is ready for use. There is need for clearing of site.
Nakalale ward admin office | PSDDM | 2014/2015 | N 03° 30.898' E 035° 13.529' | 12228947 | Nakalale |  | Makutano Gold Junction | Fithergur Gen Mer Ltd | 42505 | 42416 | 8560262.92 |  | 0.75 | No | Not complete,workers on site,complains on access road,no gate,fenced
Kaeris ward admin office | PSDDM | 2013/2014 | N 03° 59.530' E 035° 28.742' | 9501930 | Kaeris |  | Kaeris |  |  |  | 9501930 | 0 | 1 | Yes | Operational ,toilet doors falling off,outside paint worn out,no staff in the offices,ward admin to take care of maintenance
Kaaleng/Kaikor ward admin office | PSDDM |  | N 04° 31.662' E 035° 25.800' /600 M |  | Kaaleng/Kaikor |  | Kaikor | [5 empty] | 1 | No | Operational
Lapur ward admin office | PSDDM | 2014/2015 | N 04° 16.724' E 035° 52.639' /387 M | 12900075.8 | Lapur |  | Lokitaung | Salnel Const Ltd | 42505 | 42416 | 9030053 |  | 0.7 | No | Work progress is okay,but rum too steep
Lakezone ward admin office | PSDDM | 2014/2015 | N 04° 16.006' E 035° 45.420' /743 M | 13671516 | Lakezone |  | Nachukui | Lapur Trading & Inv Co Ltd | 42505 | 42416 |  |  | 0.8 | No | Wiring done,window works on going,no fence and gate,
Nanam- Nakaleso road | Roads |  | N04⁰12.743' E034⁰33.683' ELV 560m | 5276840 | Nanam Ward |  | Nanam Village | Rabbi Building And Const Co Ltd | 1st july2015 | 31st july 2015 |  |  | 1 | Yes | Project complete
Loki junc- Lopiding_Trackmack Road | Roads |  |  | 5405600 | Lokichoggio Ward |  | Lokichogio | Dafobotaz Transport And Construction Ltd | 1st july2015 | 31st july 2015 |  |  | 1 | Yes | Project complete.
A1 Junc- DRA-HO Zion Hosp_AP Line Kiwanja Ndege water kiosk road | Roads |  |  | 13960896 | Lokichogio Ward |  | Lokichogio Centre | Chavez Tech Ea Ltd |  |  |  |  | 0 | Yes | The road is at its old stage no garging nor gravelling has been done on the said road
Lokichogio - Lochor Ekope Road | Roads |  | N04⁰12.388' E034⁰20.461' ELV 648m | 7973950 | Lokichogio Ward |  | Lokichogio Centre | Lorado Co Ltd | 20/06/15 | 42163 |  |  | 1 | Yes | Project complete.
Lomidat -Ekaburu Road | Roads |  | N04⁰08.145' E034⁰26.818' | 4469480 | Songot Ward |  | Lomidat | Kaliou Const Co LTD |  |  |  |  | 1 | Yes | Project complete.
Lopiding-Naritae Road | Roads |  |  | 1900000 | Nanam Ward |  | Naritae | Lelep Inv Ltd |  |  |  |  | 0 | No | The team could not find because the community was not aware.
Aposta-Naremeto-Teremkus Road | Roads |  | N04⁰02.828' E034⁰31.869' ELV 619m | 4000260 | Songot Ward |  | Naremeto | Lokichar Enterprise Ltd |  |  |  |  | 1 | Yes | Project complete
Aposta- lokangae road | Roads |  | N04⁰01.046' E034⁰32.908' ELV 606m | 5948132 | Songot Ward |  | Lokudule | Lizton LTD |  |  |  |  | 1 | Yes | Project complete.
Natiira-Nameitak- Namaanik road | Roads |  | N03⁰53.291' E034⁰33.691' ELV 677m | 4410670 | Kalobeyei Ward |  | Natiira | Napakin Const Co LTD |  |  |  |  | 1 | Yes | Done
A1 junc- Oropoi- NB uganda Road | Roads |  | N03⁰50.900' E034⁰34.822' ELV 685m | 11980480 | Kalobeyei Ward |  | Oropoi- Natiira | Akajere Const Co Ltd |  |  |  |  | 1 | Yes | Done but the rains have destroyed some parts
Nakoyo - ayanae elelea road | Roads |  | N03⁰44.383' E034⁰44.476' ELV 632m | 4175676 | Lopur Ward |  | Nakoyo | Kachodae Building |  |  |  |  | 1 | Yes | Bad work
Kangitesuroi- Kanakuring Road | Roads |  | N03⁰52.258' E034⁰56.104' | 5212344 | Lopur Ward |  | Kangitesroi | [5 empty] | 1 | Yes | Done
Nakitongo Lokipoto- Nawotom | Roads |  |  | 4591860 | Letea Ward |  | Lokipoto | Loyoro Investment | 1st july 15 | 31st july 2015 |  |  | 1 | Yes | Was done and is complete
Lorengesinyen drift | Roads |  | N03⁰02.716' E034⁰48.229' ELV 648m | 18441259.5 | Letea Ward |  | Lorengesinyen | Nanam Const Co Ltd | 27/07/15 | 28/10/15 |  |  | 1 | Yes | Project complete but drift submerged. Project manager to follow up.
Lopwarin Drift | Roads |  |  | 18282765 | Nanam Ward |  | Lopwarin | Turkana Engineering Co Ltd |  |  |  |  | 0 | No | The drift has not been done as confirmed by the community. The team could not access site due to prosopis
A1 nadal village- moruangibuin road | Roads |  |  | 4616800 | Kakuma Ward |  | Moruangibuin | Lochorekope
Construction of Elelea - Katilia Road | Roads | 2014/2015 | N02⁰07.831' E036⁰07.040' | 9628000 | Katilia |  | Katilia - Elelea | Natoot Co Ltd |  |  | 6739600 | 2888400 | 1 | Yes | Project complete and the road is motorable.
Construction of Elelea Drift | Roads | 2014/2015 | N02⁰06.073' E036⁰09.149' | 6239988 | Katilia |  | Elelea | Natorobee Co Ltd |  |  | 4367991.6 | 1871996.4 | 1 | Yes | Project complete. There is need for embarkment down stream.
Routine maintenance of Lokwamosing/Kakongu Road | Roads |  | N02⁰00.628' E035⁰55.296' | 5868440 | Lokori/Kochodin |  | Lokwamosing - Kakongu | Turkana General Co Ltd |  |  | 4107908 | 1760532 | 1 | Yes | Project complete and the road is motorable.
Routine maintenance of Lopii - Kaaruko - Lokori Road | Roads | 2014/2015 | N02⁰03.820' E035⁰52.421' | 4200000 | Lokori/Kochodin |  | Lopii-Kaaruko-Lokori | Lowatat Contractors & Supplies Ltd |  |  | 2940000 | 1260000 | 1 | Yes | Project complete and the road is motorable.
Lotudae-Kaesamalit Road | Roads |  |  | 3125040 | Katilia |  | Lotudae-Kaesamalit | Jekanas Contractors & Supplies Company Ltd. |  |  | 2187528 | 937512 | 1 | Yes | The team could not locate the road but the information from the Department states that the project is complete.
Kamuge Drift | Roads |  |  | 7004399 | Lomelo/Napeitom |  | Kamuge | Suguta Building Contractors & Transporters Co Ltd |  |  | 2101319.7 | 4903079.3 |  |  | The team could not visit the site for security reasons. However, information from the department states that the project is on-going.
Kamuge - Baragoi | Roads | 2013/2014 |  | 12876400 | Lomelo/Napeitom |  | Kamuge - Baragoi |  |  |  |  | 12876400 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Lokori - Paragati | Roads | 2013/2014 |  | 7934400 | Lokori/Kochodin |  | Lokori - Paragati |  |  |  |  | 7934400 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Lomelo - Kamuge | Roads | 2013/2014 |  | 11564040 | Lomelo/Napeitom |  | Lomelo - Kamuge |  |  |  |  | 11564040 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Kamuge - Baragoi | Roads | 2014/2015 |  | 4902160 | Lomelo/Napeitom |  | Kamuge - Baragoi | Nakuru Machinery |  |  | 1960864 | 2941296 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
lokichar-loruth road | Roads |  | N 03° 30.905' E 035° 13.350' | 3380000 | Nakalale |  | Loruth | Kalemchuch Contractors | 42044 | 42216 |  | 0 | 1 | Yes | Operational,signage done
Spot improvement Makutano-Lokitaung road A | Roads |  | N 03° 32.581' E 035° 14.874' | 24985820 | Nakalale |  | Makutano Lokitaung Road |  | 42044 | 42164 |  |  | 1 | Yes | Operational,signage done
losajait-naurugori road | Roads |  | N 03° 30.751' E 035° 11.099' | 1641740 | Nakalale |  | Losajait | Natedelim Construction Ltd. | 42044 | 42259 |  |  | 1 | Yes | Opeational,signage done
nakapelekuruk-nadunga road | Roads | 2014/2015 | N 03° 43.391' E 035° 20.371' | 2847800 | Kaeris |  | Nakapelkuruk | Moru Edou Investment | 42044 | 42216 |  |  | 1 | Yes | Poorly done,entry ok,a few kilometres shoddy
Spot improvement Makutano-Lokitaung road A | Roads | 2014/2015 | N 04° 12.781' E 035° 28.136' | 25641800 | Nakalale |  | Makutano Lokitaung Road | Kalemchuch Contractors | 42044 | 42216 |  |  | 1 | Yes | Operational
kaaleng-kamothia-kibish road | Roads | 2013/2014 | N 04° 20.929' E 035° 33.280' /641 M | 23658707 | Kaaleng/Kaikor |  | Kaaleng | Kataboi Investmentd Limited |  |  |  |  | 1 | Yes | Operational
kaaleng-nakapelewoi road | Roads | 2014/2015 | N 04° 22.687' E 035° 30.636' /636 M | 1097360 | Kaaleng/Kaikor |  | Kaaleng/Nakapelewoi | Baross Investment | 42044 | 42269 |  |  | 0.8 | Yes | No levelling
routine maintenance of C47-Kaaleng road | Roads | 2014/2015 | N 04° 20.461' E 035° 36.632' /591 M | 1082472 | Kaaleng/Kaikor |  | Kaaleng Road | Napalakipor Investment Ltd | 42044 | 42216 |  |  | 0.9 | Yes | Operational
routine kachoda-riokomor road | Roads | 2014/2015 | N 04° 19.290' E 035° 40.458' /569 M | 2272788 | Lapur |  | Kachoda Rokomor Road | Jerman Contractors | 42044 | 42249 |  |  | 0.95 | Yes | Operational
routine maintenance of sasame-kabulokok-karioreng | Roads | 2014/2015 | N 04° 30.860' E 035° 44.838' /541 M | 1936620 | Lapur |  | Sasame | Jonice Investment Limited | 42044 | 42254 |  |  |  | Yes | Operational
kaikor-kangikala-lobur road | Roads |  | N 04° 30.397' E 035° 25.229' /599 M | 3557996.8 | Lapur |  |  |  | 42044 | 41991 |  |  | 1 | Yes | Operational
riokomor-narengewoi road | Roads | 2014/2015 | N 04° 06.385' E 035° 43.217' /552 M | 2265480 | Lapur |  | Riokomor | Nangorikitoe Investment | 42044 | 42216 |  |  | 1 | Yes | Operational
nachukui-narikiotome-lokapetamoe road | Roads | 2014/2015 | N 04° 04.194' E 035° 53.067' /382 M | 1911888 | Lakezone |  | Nachukui | Lokwairia Enterprises Ltd. | 42208 | 42300 |  |  | 1 | Yes | Operational
nadunga-lochor atesiro road | Roads | 2014/2015 | N 03° 57.907' E 035° 15.452' /565 M |  | Kaeris |  | Nadunga | Kalemchuch Contractors | 41878 | 41970 |  |  | 0.95 | Yes | Operational
kaeris- kalopeta road | Roads | 2014/2015 | N 04° 22.687' E 035° 30.636' /614 M | 2744400 | Nakalale |  | Kapotea |  | 42044 | 42216 |  |  | 0.9 | Yes | Poorly done,operational
kokuro-lobur road | Roads |  | N 04° 44.255' E 035° 40.361' /424 M |  | Lapur |  | Kokuro |  | 42044 | 42216 |  |  | 1 | Yes | Operational
Lokamarinyang - Soya road | Roads | 2014/2015 |  | 6722102 | Kibish |  |  | Inyang General Suppliers Ltd.
nakalale-nabuskaal-kairima road | Roads | 2014/2015 |  | 3580920
Koyasa-Natelo-Natapar | Roads | 2013/2014 |  | 9404700
Kataboi-Lopur | Roads | 2013/2014 |  | 5215800
Kaimothia-kibish | Roads | 2013/2014 |  | 23658707 | Kibish
Kaikor-Lokiyoto-Loruth Road | Roads |  |  | 3641889.8 | Kibish |  |  | Synchtolyte Gen.Contractors Ltd.
Kaaleng Animal Feed Reserve Store | PEF |  |  | 9599986 | Kaaleng/Kaikor |  | Kaaleng | Nyai Const Co Ltd |  |  | 9599986 | 0 | 1 | No | Project complete and ready for commissioning
St. Cosmas Primary School Solar Installation Project | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N04⁰11.708' E034⁰23.868' |  | Nanam Ward |  | Napopongoit | Olam Building And Construction | box 33-30501 kakuma | 42384 | 42566 |  |  | 1 | Yes | Project complete
St. Mathews Primary School Solar Project | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N04⁰11.798' E034⁰23.297' |  | Nanam Ward |  | Lopiding | Olam Building And Construction | box 33-30501 kakuma | 42384 | 42566 |  |  | 1 | Yes | Project complete
St. Patricks Primary School Solar Installation | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N04⁰09.400' E034⁰25.915' |  | Lokichogio Ward |  | Lomidat | Olam Building And Construction | box 33-30501 kakuma | 42384 | 42566 |  |  | 1 | Yes | Project complete
Lokwanya Primary School Solar Project | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N04⁰56.439' E034⁰33.732' |  | Songot Ward |  | Lokwanya | Olam Building And Construction | box 33-30501 kakuma | 42384 | 42566 |  |  | 1 | Yes | Project complete
Natiira Primary School Solar Project | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N03⁰53.146' E034⁰33.663' |  | Kalobeyei Ward |  | Natiira | Olam Building And Construction | box 33-30501 kakuma | 42384 | 42566 |  |  | 1 | Yes | Project complete
Pokotom Primary School Solar Project | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N03⁰43.949' E034⁰51.174' |  | Kakuma |  | Pokotom Primary | Olam Building And Construction | box 33-30501 kakuma | 42384 | 42566 |  |  | 1 | Yes | Project complete
Letea Primary School Solar Installation Project | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  |  |  | Letea Ward |  | Letea Primary School | Olam Building And Construction | box 33-30501 kakuma | 42384 | 42566 |  |  | 1 | Yes | Project complete
Teremkus Tree Nursery | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  |  |  | Songot Ward |  | Teremkus | Kotome Building And Enterprises | [5 empty] | 0.5 | No | There is no functional nursery yet. Works not done to specification. Suppliers paid fully but the materials have not been supplied fully. The client ministry to make follow up.
Kalobeyei Tree Nursery | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N03⁰46.374' E034⁰36.969' |  | Kalobeyei |  | Kalobeyei | Kotome Building And Enterprises | [5 empty] | 0.5 | No | There is no functional nursery yet. Works not done to specification. Suppliers paid fully but the materials have not been supplied fully. The client ministry to make follow up.
Kakuma Tree Nursery | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N03⁰43.198' E034⁰51.576' |  | Kakuma |  | Kakuma | Kotome Building And Enterprises | [5 empty] | 0.5 | No | There is no functional nursery yet. Works not done to specification. Suppliers paid fully but the materials have not been supplied fully. The client ministry to make follow up.
Lopur Tree Nursery | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N03⁰51.377' E034⁰49.000' |  | Lopur |  | Lopur | Kotome Building And Enterprises | [5 empty] | 0.5 | No | There is no functional nursery yet. Works not done to specification. Suppliers paid fully but the materials have not been supplied fully. The client ministry to make follow up.
Letea Tree Nursery | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  |  |  | Letea Ward |  | Letea | Kotome Building And Enterprises | [5 empty] | 0.5 | No | There is no functional nursery yet. Works not done to specification. Suppliers paid fully but the materials have not been supplied fully. The client ministry to make follow up.
Nanam Ward Tree Nursery | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  |  |  | Nanam Ward |  |  | Kotome Building And Enterprises | [5 empty] | 0 | No | The team could not find the tree nursery
Lokichogio Ward Tree Nursery | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  |  |  | Lokichogio Ward |  |  | Kotome Building And Enterprises | [5 empty] | 0 | No | The team could not find the tree nursery
Solar Installation-Naduat Primary School | ENERGY, ENVIRONMENT AND NATURAL RESOURCES | 2014/20015 | N 03° 30.709' E 035° 12.118' |  | Nakalale |  | Naduat | Lokitaung Contractors |  | 42384 | 42566 |  |  | 1 | Yes | Operational
Solar Installation -Losajait Primary School | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N 03° 37.405' E 035° 18.543' |  | Nakalale |  | Losajait | Lokitaung Contractors |  | 42384 | 42566 |  |  | 1 | Yes | Operational
Solar Installation -Nadunga Primary School | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N 03° 57.132' E 035° 18.349' |  | Kaeris |  | Nadunga | Lokitaung Contractors |  | 42384 | 42566 |  |  | 1 | Yes | Operational
Solar Installation -Kaeris Girls Secondary School | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N 03° 59.063' E 035° 28.565' |  | Kaeris |  | Kaeris | Lokitaung Contractors |  | 42384 | 42566 |  |  | 1 | Yes | Operational
Solar Installation -Loruth Mixed Primary | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N 04° 26.706' E 035° 21.517' |  | Kaaleng/Kaikor |  | Loruth | Lokitaung Contractors |  | 42384 | 42566 |  |  | 1 | Yes | Operational
Solar Installation-Kokuro Dispensary | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N 04° 38.088' E 035° 41.824' |  | Lapur |  | Kokuro | Lokitaung Contractors |  | 42384 | 42566 |  |  | 1 | Yes | Operational
Solar Installation -Makutano Health Center | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N 03° 31.078' E 035° 13.516' |  | Nakalale |  | Makutano Gold Junction | Lokitaung Contractors | [5 empty] | 1 | Yes | Operational
Solar Installation-Kokuro Primary | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N 04° 39.851' E 035° 42.506' |  | Lapur |  | Kokuro | Lokitaung Contractors |  | 42384 | 42566 |  |  | 1 | Yes | Operational
Solar Installation - Riokomor Primary | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N 04° 06.714' E 035° 43.159' |  | Lapur |  | Riokomor | Lokitaung Contractors |  | 42384 | 42566 |  |  | 1 | Yes | Operational
Solar Installation-Lomekwi Primary | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N 04° 54.850' E 035° 50.250' |  | Lakezone |  | Lomekwi | Lokitaung Contractors |  | 42384 | 42566 |  |  | 1 | Yes | Operational
Losajait Tree Nursery | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N 03° 37.424' E 035° 18.549' |  | Nakalale |  | Losajait | [6 empty] | 0.3 | No | There is no functional nursery yet, works not done to specification suppliers paid fully. The entire contract was ambiguous. Client ministry to follow up
Kaeris Tree Nursery | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N 03° 59.192' E 035° 27.969' |  | Kaeris |  | Kaeris | [6 empty] | 0.3 | No | There is no functional nursery yet. Works not done to specification. Suppliers paid fully. The entire contract was ambiguous. Client ministry to follow up
Kaaleng/Kaikor Tree Nursery | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N 04° 30.397' E 035° 25.229' |  | Kaikor/Kaleng |  | Kaikor | [6 empty] | 0.3 | No | Fence erected, no sign of nursery trees, no water tank,0.35 acres
Lokitaung Tree Nursery | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N 04° 16.396' E 035° 44.779' |  | Lapur |  | Lokitaung | [6 empty] | 0.3 | Not in use | Fence erected, no sign of nursery trees, no water tank, beneath wire open
lakezone tree nursery | ENERGY, ENVIRONMENT AND NATURAL RESOURCES |  | N 04° 16.849' E 035° 53.584' |  | Lakezone |  | Loarengak | [6 empty] | 0.3 | Not in use | Fence erected, no sign of nursery trees, no water tank,0.4044 acres
County Treasury Building | F$P | 2014/2015 | N 03° 06.680´ E 035° 37.063' | 44545369 | KANAMKEMER | CENTRAL | Nawoitorong | LOMIA ENERGY |  |  |  |  | 26726426 | 17818943 | 1 | Yes | Project complete amd in use. Entrance pavement need to be redone.
Citizen Resource Centre-Kerio | F$P | 2014/2015 | N 03° 00.060´ E 036° 02.386' | 34613328 | KERIO | CENTRAL | Kerio Town | EDOU AKIDE CONST |  |  |  |  | 24229329 | 10383999 | 0.9 | No | Structures complete and fencing done. Basketball and handball court done.
Construction of Cess collection office. | F$P | 2014/2015 | N 03° 31.794´ E 035° 51.223' |  | Kalokol | CENTRAL | Kalokol Town | [7 empty] | 1 | Yes | Office, latrine and a barrier costructed. Need for furniture. Revenue officer on site working.
Nawoitorong Slaughter House | F$P | 2014/2015 | N 03° 06.497´ E 035° 37.443' |  | KANAMKEMER | CENTRAL | Nawoitorong | [7 empty] | 1 | No | Facility operations stopped by NEMA.
Lorugum Citizen Resource Culture | F$P | 2014/2015 | N 02⁰ 52.399`E 035 16.063 |  | Turkwel |  | Lorugum | Loima Devt. Ltd |  | 42066 |  |  | 3273867 | 14030853 | 1 | yes | excellent job, awaiting commisioning
Lokiriama Revenue Generating Perimeter wall | F$P | 2014/2015 | N 02⁰ 45.021`E 035 52.206 |  | Lorengipi Lokiriama |  | Lokiriama | Ekori Agete Enterprise |  | April ,2015 |  |  | 32565456 | 25401416 | 1 | yes | awaiting more funding
Lokiriama Cess Station | F$P | 2014/2015 | N 02⁰ 45.403`E 035 52.638 |  | Lorengipi Lokiriama |  | Lokiriama | [7 empty] | 1 | Yes | Generating Revenue, good condition
Nakalale Borehole | WIA | 2014/15 | N 02° 52.946´ E 035° 56.199' |  | Kerio | Central | Nakalale | [7 empty] | 40 | No | The borehole is dry.
Lolupe Borehole | WIA | 2014/15 | N 03° 06.448´ E 035° 40.486' |  | Kanamkemer | Central | Lolupe | [7 empty] | 100 | Yes | Project complete.
Elelea Borehole | WIA | 2014/15 | N 03° 07.483´ E 035° 44.142' |  | Kanamkemer | Central | Elelea | [7 empty] | 100 | Yes | Water salty.
Supply and Installation of hand pumps | WIA | 2014/15 | N 03° 22.636´ E 035° 40.703' | 56399200 | Kalokol | Central | Kapokor | Silale Investment LTD | [6 empty] | 100 | Yes | Project complete.
Kangirisae/Kaatir Water Pan | WIA | 2014/15 | N 02° 38.915´ E 036° 11.341' |  | Kerio | Central | Kangirisae/Kaatir | Cinoc Const Company | [6 empty] | 100 | Yes | Project complete with feeder channels and good holding. There is no water in the pan.
Natome Borehole | WIA | 2014/15 | N 02° 42.446´ E 036° 12.839' | 2560000 | Kerio | Central | Nakoret | Magee Const & Gen Supplies | [6 empty] | 100 | Yes | Hand pump installed. Water flowing.
Nangitony Irrigation Scheme | WIA | 2014/15 | N 03° 05.372´ E 036° 06.560' |  | Kerio | Central | Nangitony | Namortunga Const Co |  | 42186 | 42491 |  |  |  | 80 | no | Construction of main canal (1375M) on going. Vandalism of wheels and wiremesh noted.
Equiping of Namadak water supply with solar system | WIA | 2014/15 | N 03° 37.764´ E 035° 47.888' |  | Kalokol | Central | Namadak | Turkana Salama | [6 empty] | 100 | Yes | Project complete.
Construction of Kalokol Water Pan | WIA | 2014/15 | N 03° 34.677´ E 035° 48.475' |  | Kalokol | Central | Kalimapus | Sacred Ventures | [6 empty] | 95 | No | Escavation, fencing and inlet complete.
Drilling of Kalokol Borehole | WIA | 2014/15 | N 03° 34.677´ E 035° 48.475' |  | Kalokol | Central | Napasinyen | Turkana Hardware | [6 empty] | 100 | No | Drilling and water testing done. The borehole not yet equipped.
Pump House and laying of new line. | WIA | 2014/15 | N 03° 31.499´ E 035° 50.206' |  | Kalokol | Central | Napasinyen | Turkana Hardware | [6 empty] | 70 | No | Fence and pump house done.
Supply and Installation of hand pumps | WIA | 2014/15 | N 03° 31.499´ E 035° 50.206' |  |  | Central |  | Silale Investment LTD | [6 empty] | 70 | No
Kangatotha Water Pan | WIA | 2014/15 | N03⁰12.248' E035⁰59.027' | 9194078 | Kangatotha | Central | Kangatotha | Urumi Lose Gen.Co | [8 empty] | In use and attention is really needed at the entrances
Protection&Dev't of Eliye Spring Water Supply | WIA | 2014/15 | N03⁰15.147' E036⁰01.237' | 13861804 | Kangatotha | Central | Eliye | Garite Ltd | [6 empty] | 60 | Yes
Lokaparaparae Borehole | WIA | 2014/15 | N03⁰09.147' E035⁰38.509' |  | Township | Central | Monti | [7 empty] | 50 | No | No handpump.Need to be piped to the IDPs.Project in progrss
Kakwanyang Irrigation Scheme | WIA | 2014/15 | N03⁰08.168' E035⁰40.999' |  | Township | Central | Kakwanyang | [7 empty] | 20 | No | Partial canal and bush cleaning..Broken down Tractor in sight.
Nakoringora Borehole | WIA | 2014/15 | N03⁰14.469' E035⁰46.236' |  | Township | Central | Borehole | [7 empty] | 100 | Yes | Saline condition.In use but not for Consumption.
Lodwar Township Water Pan | WIA | 2014/15 | N03⁰13.251' E035⁰43.440' | 9199680 | Township | Central | Lodwar | Kalimapus Co. | [6 empty] | 95 | Yes | Project Complete.Well fenced.Attention needed at the entrances.
Napuu Irrigation Scheme | WIA | 2014/15 | N03⁰06.472' E035⁰38.278' | 57859814.76 | Kanamkemer | Central | Napuu | Ortipirro Ltd. | [6 empty] | 100 | Yes | Project Complete.Water Channels underway.Need of fertilizers and Seed for plantation.
Naotin Borehole | WIA | 2014/15 | N03⁰02.278' E035⁰32.704' |  | Kanamkemer | Central | Naotin | [7 empty] | 90 | No | Need a ahndpump.Not in use.
Kanamkemer Water Pan | WIA | 2014/15 | N03⁰01.329' E035⁰33. | 9213474 | Kanamkemer | Central | Naotin | [7 empty] | 100 | Yes | Complete and In use.Well fenced and the entrances were well made.
Moruese canal | WIA | 2014/15 | N 02⁰ 56.416' E 035 25.622' |  | Turkwel |  | Moruese | [7 empty] | 0.5 | No | work ongoing contractor pulled out of site without paying workers
Kaekuto water pan | WIA | 2014/15 | N 02⁰ 34.545' E 035 17.247 |  | lobei/kotaruk |  | Kaekuto | [7 empty] | 0.6 | No | ongoing contractors on site machne/equipments broken
Lokipetot Borehole | WIA | 2014/15 | N 02⁰ 38.420' E 035 21.180 |  | lobei/kotaruk |  | lobei/kotaruk | [7 empty] | 1 | Yes | In use Excellent job
Lorugum sub-coubty Hospital Borehole | WIA | 2014/15 | N 02⁰ 52.467 E 035 15.384 |  | Turkwel |  | Lorugum | [7 empty] | 0.5 | No | capped, Not equipped
Nang'oleki water pan | WIA | 2014/15 | N 02⁰ 54.240' E 035 03.824' |  | Loima |  | Nang'oleki | [7 empty] | 1 | Yes | No inlet Depends on rain water
Urum Water Pan | WIA | 2014/15 | N 02⁰ 57.572`E 03440.997 |  | Lorenkipi/lokiriama |  | Urum | [7 empty] | 1 | Yes | In use, waiting for rains, well constructed
Nakurio Borehole | WIA | 2014/15 | N 02⁰ 42.010`E 035 03.824 |  | Lorenkipi/lokiriama |  | Nakurio | [7 empty] | 1 | Yes | in use, far from community, need for a solar powered system
Kangiregae Borehole | WIA | 2014/15 | N 02" 11.383 E 035" 32.450 |  | Katilu |  | Kangiregae | [7 empty] | 1 | YES | Complete & functional Chairperson need chain for maintenance purpose
Katilu Borehole | WIA | 2014/15 | N 02" 16.188 E 035" 26.750 |  | Katilu |  | Katilu | [7 empty] | 1 | YES | In use panel installed. Fenced off. Panels secured
Katilu market & toilets | WIA | 2014/15 | N 02" 16.393 E 035" 25.858 |  |  |  | Katilu | [7 empty] | 0.9 | No ops | Toilet roof flown off. Toilets to be re-done. No gabbage pit. Not fenced off.
Naakalei Borehole | WIA | 2014/15 | N 02" 31.046 E 036" 09.961' |  | Kalapata |  | Kangiranyir | [7 empty] | 1 | YES | Operational
Kangakipur Borehole | WIA | 2014/15 | N 02" 22.951 E 036" 02.710' |  | Kalapata |  | Kangakipor | [7 empty] | 1 | YES | Borehole equiped. Installed solar and storage tank. Operational.
Loyapat Borehole | WIA | 2014/15 | N 01" 50.414 E 035" 28..931' |  | Lobokat |  | Loyapat | [7 empty] | 1 | YES
Lokichar Water pan | WIA | 2014/15 | N 02" 18.842 E 035" 42..051' |  | Lokichar |  | Lowoida | Ape company | [8 empty] | Fence should be re-done(put chain link). In let stream to the waterpan should be re-done. The bed of the waterpan is higher than the inlet. No catchment. In lets drawing waterpan. The technical team to visit it.
Napussmoru Borehole | WIA | 2013/2014 | N 02" 39.555 E 035" 50.4928' |  | Lokichar |  | Napussmoru | [7 empty] | 0 | NO | Nothing on the site. The contractor was not able to proceed.
Kaadongole Borehole | WIA | 2014/15 | N 02" 25.623 E 035" 39.309' |  | Lokichar |  | Kaadongole | Arid Pillars | [6 empty] | 1 | YES | Operational. Need additional pipe to reach the water. Need repairs.
Borehole 3 | WIA | 2014/15 | N 02" 10.342 E 035" 24.615' |  | Kaptir |  | Juluk BH 3 | [9 empty] | Not equipped. To identify C11/2 in extension paper up (on the casing)
Kapelibok Borehole | WIA | 2014/15 | N 02" 06.095 E 035" 25.231' |  | Kaptir |  | Kapelibok | [9 empty] | Complete. In use. Need repair of the handle.
Juluk Borehole BH 1 | WIA | 2014/15 | N 02" 10.358 E 035" 24.611' |  |  |  | Juluk BH 1 | [7 empty] | 1 |  | Complete. Broken on 2/4/2016
Borehole 2 | WIA | 2014/15 | N 02" 10.343 E 035" 24.613' |  | Kaptir |  | Juluk BH 2 | [9 empty] | In complete. Casing not equipped( In the middle of the three boreholes)
Lokapel Borehole | WIA | 2014/15 | N 02" 24.618 E 035" 53.067' |  | Kalopate |  | Lokapel | [7 empty] | 0.5 | No | Drilled with casing. Awaits to be equipped
Lomelekwi Borehole | WIA | 2014/15 | N 02" 22.162 E 035" 58.413' |  | Kalapata |  | Lomelekwi | [7 empty] | 0.5 | NO | Drilled with casing and not equipped.
Kakongu waterpan | WIA | 2014/15 | N 02" 02.369 E 035" 31.321' |  | Lobokat |  | Kakongu | [7 empty] | 1 | YES | Well done drainage & waterpan
Kalemorongok waterpan | WIA | 2014/15 | N 02" 09.477 E 035" 32.137' |  | katilu |  | Kalemorongok | Lomral construction company | [6 empty] | 1 | YES | Inlet not done well. Not catching water anymore.
LODWAR YOUTH POLYTECHNIC Hair Dressing Workshop | Education | 2014/2015 | N 03° 07.444´ E 035° 36.335' | 9618200 | LODWAR TOWNSHIP | CENTRAL | Lodwar Town | Katilu Builders |  |  |  | 9618200 | 0 | 100 | Yes | Project complete.
Turkana cultural centre | Education | 2014/2015 | N 03° 06.496´ E 035° 47.443' | 36427190 | KANAMKEMER WARD | CENTRAL | Nawoitorong |  |  |  |  | 36427190 | 0 | 100 | YES | The project is complete and fenced with 3 No gates. 4 No main structures for shade and 2 No VIP shades. Several Latrines for men and women. The facility is connected to electricity.
CONSTRUCTION OF IMPRESSA ECD | Education | 2014/2015 | N 03° 33.315´ E 035° 53.129' | 6000000 | Kalokol | CENTRAL | Impressa |  |  |  |  | 6000000 | 0 | 100 | Yes | Need for a fence and connection to water supply. The classroom has no door.
CONSTRUCTION OF NAKEKICHOK ECD | Education | 2014/2015 | N 03° 07.824´ E 035° 51.388' | 6000000 | KERIO WARD | CENTRAL | Nakekichok | KERMAN CONST CO LTD |  |  |  | 6000000 | 0 | 95 | NO | Contractor not on site. Classroom dining latrines and fencing done. There is need for repaiting and construction of a ramp in the dining hall.
CONSTRUCTION OF NANGOLEBEI ECD | Education | 2014/2015 | N 02° 43.919´ E 036° 14.364' | 6000000 | KERIO WARD | CENTRAL | Nangolebei |  |  |  |  | 6000000 | 0 | 100 | YES | Complete structures. Secured with a fence and lockable gate. The project location was changed from Nakurio to Nalongebei. The facility is close to the community.
CONSTRUCTION OF NAMERESINYEN ECD | Education | 2014/2015 | N 03° 23.174´ E 035° 34.674' | 6000000 | KALOKOL | CENTRAL | Namerisinyen | KALIMAPUS CONST CO LTD | 42005 | 42217 |  | 6000000 | 0 | 100 | Yes | Project complete.
Construction of Elelea ECD | Education | 2013/2014 | N 03° 07.606´ E 035° 44.083' |  | KANAMKEMER WARD | CENTRAL | Elelea | [5 empty] | 0 | 100 | Yes | Toilet door need repairs.
Construction of Kaamekwi ECD | Education |  | N 02° 38.640´ E 036° 15.103' |  | KERIO WARD | CENTRAL | Kaamekwi | [5 empty] | 0 | 100 | Yes | Project complete.
Construction of Nakalale ECD | Education | 2013/2014 | N 02° 52.993´ E 036° 56.178' |  | KERIO WARD | CENTRAL | Nakalale | [5 empty] | 0 | 100 | Yes | Need for a fence and connection to water supply. The classroom has no door.
Construction of Nayana Ekalale ECD | Education | 2013/2014 | N 03° 27.326´ E 035° 51.779' |  | KALOKOL | CENTRAL | Nayana Ekalale | [5 empty] | 0 | 100 | Yes | Need for a fence and connection to water supply. There is also need for renovations.
Construction of Muruongor ECD | Education | 2013/2014 | N 03° 30.010´ E 035° 36.337' |  | KALOKOL | CENTRAL | Muruongor | [5 empty] | 0 | 100 | Yes | Project complete.
Construction of a dorm in Namaide Girls Primary School | Education |  | N 02° 59.387´ E 036° 04.200' |  | KERIO WARD | CENTRAL | Namaide |  | 42186 | 42461 |  |  | 0 | 100 | Yes | Finishing works on going.
Nakadukui ECD Centre | Education | 2014/2015 | N03⁰10.363' E035⁰45.672' | 6000000 | Kangatotha | Central | Nakadukui | Chapchap Fishing Industry |  |  |  | 6000000 | 0 | 100 | Yes | Complete.The project is in use.Has been installed with solar and toilets are available.
RedBanna IDP ECD | Education |  | N03⁰06.296' E035⁰33.874' | 6000000 | Township | Central | Nakwamekwi | [5 empty] | 6000000 | 100 | Yes | Complete.Well fenced.In us.
Legio of Mary ECD | Education |  | N03⁰07.345' E035⁰35.069' |  | Township | Central | Nakwamekwi | [5 empty] | 0 | 90 | Yes | No fencing.Open walls.No security but the project is in use.
St.Michael Kawalase ECD Centre | Education |  | N03⁰07.440' E035⁰36.860' | 6000000 | Township | Central | Napetet | Kuron Cnst. Ltd |  |  |  |  | 6000000 | 80 | Yes | N fencing but the project is in use.Complete.
Natambusio ECD | Education |  | N03⁰08.204' E035⁰37.037' |  | Township | Central | Natambusio | Kabarait Builders and Contractors |  |  |  |  | 0 | 100 | Yes | Complete.Not fenced yet.Urgent need of security.
Juluk ECD | Education |  | N03⁰05.399' E035⁰35.853' | 5600000 | Kanamkemer | Central | Kanamkemer | [5 empty] | 5600000 | 100 | Yes | Well fenced.Was commissioned.Toilets available.Complete
Naotin ECD | Education |  | N03⁰03.182' E035⁰32.825' | 6000000 | Kanamkemer | Central | Kanamkemer | [5 empty] | 6000000 | 95 | No | Not fenced.Classrooms and dinning are well done.
Kakemera ECD Centre | Education |  | N02⁰59.070' E035⁰38.593' | 6000000 | Kanamkemer | Central | Napetao | Gatuzi Co Ltd |  |  |  |  | 6000000 | 100 | No | Ready for commissioning.Standard workmanship.Well built.
RENOVATION OF TURKANA COUNTY ECD COLLEGE | Education |  | N02⁰59.070' E035⁰38.593' | 18002596.8 | LODWAR TOWNSHIP | CENTRAL | Lodwar Town | KERIOUCON CONST CO LTD | 42125 | 42278 |  |  | 18002596.8 | 85 | YES | Works on going. Partly remaining works are Latrines, Drainage, Painting and Rennovation of floors. Contractor on site with adequate labour. Fencing done. Most of the works not captured in the BoQS.
Kalomegur ECD centre | Education |  | N 02⁰ 53.74' E 035 25.030' |  | Turkwel | Loima | Kalomegur | Moruese Gen Con ltd |  |  |  |  | 0 | 1 | yes | Quality job
Kalemnyang Ecd centre | Education |  | N 02⁰ 44.12' E 035 22.089 |  | lobei/kotaruk | Loima | Kalemunyang |  | 41661 | 41743 |  | 1050000 | -1050000 | 1 | yes | Satisfacory
Lorugum Youth polytechnic | Education |  | N 02⁰ 52.007' E 035 15.842 |  | Turkwel | Loima | Lorugum |  | April, 2015 |  |  | 2848432.2 | -2848432.2 | 1 | Yes | job done well Waiting for commissioning
Lomukusei Ecd | Education |  | N 02⁰ 50.973 E 035 07. 831' |  | Loima | Loima | Lomukusei | Locher Emeyan const. |  |  |  |  | 0 | 1 | yes | Satisfacory
Lopedur Ecd centre | Education |  | N 02⁰ 51.505' E 035 05.836' |  | Loima | Loima | Lopedur |  | 41661 | 41804 |  | 1050000 | -1050000 | 1 | Yes | No fence Cracked floors Teacher not in school construction fauly done
Lochor Edome ECDE | Education |  | N 02⁰ 45.414`E 035 01.658 |  | Loima | Loima | Lochor Edome | Naamwa const & supp |  |  |  |  | 0 | 1 | No | fenced, awaiting commisioning, good work
Lobole ECDE Centre | Education |  | N 02⁰ 48 .783 `E 035 00. 610 |  | Loima | Loima | Lobole |  | 41661 | 41743 |  | 1050000 | -1050000 | 1 | Yes | No fence, in use
Nakwapua ECDE Centre | Education |  | N 02⁰ 57.202`E 035 44.777 |  | Lorengipi/Lokiriama | Loima | Nakwapua |  | 41661 | 41804 |  | 1050000 | -1050000 | 1 | Yes | No fence , in use, bush near the cntre isnt cleared
Urum ECDE Centre | Education |  | N 02⁰ 57.553`E 035 41.771 |  | Lorengipi/Lokiriama | Loima | Urum |  | 41661 | 41804 |  | 2450000 | -2450000 | 1 | yes | no fence, pit atrine not in good condition, flor is in bad condition
Lokirima ECDE Centre | Education |  | N 02⁰ 45.383`E 035 52.368 |  | Lorengipi/Lokiriama | Loima | Lokiriama |  | June,2015 | September, 2015 |  | 1800000 | -1800000 | 1 | No | fenced, DH in good state, awaiting commisioning
Sasak-Echoke ECD | Education |  | N 02⁰ 46.216' E 035 12.m994 |  | Lobei/Kotaruk | Loima | Sasak-Echoke |  |  |  |  | 1800000 | -1800000 | 1 | No | finished well, Awaiting commissioning, well fenced
Nakurio ECD | Education |  | N 02⁰ 41.744' E 035 04.058' |  | lorengipi lokiriama | Loima | Nakurio | Nyati Gen const. |  |  |  | 1800000 | -1800000 | 1 | yes | Not fenced, floor has not been covered well, inside walls have not been painted
Lomilo ECD centre | Education |  | N 02⁰ 46.920' E 035 08.728 |  | Lobei/Kotaruk | Loima | Lomilo |  | 41661 | 41743 |  | 2800000 | -2800000 | 1 | yes | Floor has cracked, in use
Lolemgete ECD centre | Education |  | N 03⁰ 00.549' E 035 15.775 |  | Turkwel | Loima | Lolemgete |  | 41661 | 41804 |  | 3150000 | -3150000 | 1 | yes | Fenced, well finished, no water.
Kalokutonyang ECD centre | Education |  | N 03 ⁰20.480' E 035 28.192' |  | Turkwel | Loima | Kalokutonyang | [5 empty] | 0 | 1 | yes | Fenced well, in use
Amani ECD | Education |  | N 02" 14.729' E 035" 26.029' |  | Katilu | Loima | Korinyang | [5 empty] | 0 | 1 | YES | Completed & operational. Solar installed. Toilets completed (double toilets separate)
Kaakalel ECD | Education |  | N 02" 27.772' E 036" 05.198' |  | Kalapata | T. South | Kaakalel | [5 empty] | 0 | 0.95 | NO | No gate. No chimney. Complete structures. Fenced
Nakwamoru ECD | Education |  | N 02" 03.356' E 036" 25.893' |  | Kaputir | T. South | Nakwamoru | [5 empty] | 0 | 0.8 | NO | Contractor has abandoned the site. Pit latrine not complete(50%). Painting not done. Cracks on the wall. Kitchen not complete(no winds & doors). Kitchen slabs not done.
Construction of new ECD at kimabur( St. Teresa) | Education |  | N 02" 48.381' E 035" 37.317' |  | Lokichar | T. South | Kimabur | Lomido |  |  |  |  | 0 | 0.3 | NO | Not finished. Seems abandoned. No contractor on site. Pit latrine not started.
Lokichar IDP ECD | Education |  | N 02" 21.543' E 035" 37.834' |  | Lokichar | T. South | Lokichar(IDP) | [5 empty] | 0 | 0.9 | NO | Fenced. Not painted inside. No gate. No chimney. Installation on roofing. Structures complete.
Lokichar youth polytechnic | Education |  | N 02" 21.470' E 035" 38.488' |  | Lokichar | T. South | Lokichar(IDP) | [5 empty] | 0 | 1 | YES | Complete structures. Pit latrine door is falling.
Napussmoru ECD | Education |  | N 02" 37.736' E 035" 50.824' |  | Lokichar | T. South | Napussmoru | [5 empty] | 0 | 1 | YES | Structures, Fence & gate complete. Awaits opening. Has chimney. One door not easy to close.
Naakalei ECD | Education |  | N 02" 32.203' E 036" 13.328' |  | Kalapata | T. South | Kalapata | [5 empty] | 0 | 1 | YES | Complete. No chimney. Ground floors and dining hall need renovations.
Kainuk Mixed ECD | Education |  | N 01" 46.491' E 035" 30.403' |  | Lobokat | T. South | Kainuk | [5 empty] | 0 | 1 | NO | Should have open grills. Not fenced. No signpost. No branding
Kaputiro ECD | Education |  | N 01" 46.748' E 035" 30.053' |  | Lobokat | T. South | Kaputiro Primary | [5 empty] | 0 |  |  | No fence. Avoid grills. No sign post.
Kapelbok ECD | Education |  | N 02" 05.965' E 035" 25.061' |  | Kaputir | T. South | Kapelbok | [5 empty] | 0 | 0.7 |  | Class room complete. Toilets incomplete. Dining hall incomplete. No windows.
Juluk ECD | Education | 2013/2014 | N 02" 09.957' E 035" 24.560' |  |  | T. South | Juluk | [5 empty] | 0 |  |  | No toilet pit dug. No fence. In complete
Lokoropus ECD | Education | 2014/2015 | N 02" 08.196' E 035" 26.887' |  |  | T. South | Lokoropus | [5 empty] | 0 |  |  | Need ramps
Nakuse ECD | Education | 2014/2015 | N 02" 04.683' E 035" 27.670' |  |  | T. South | Nakuse | [5 empty] | 0 | 1 |  | Chimney missing. Use ramps at the entrance
Lokapel ECD | Education | 2014/2015 | N 02" 22.683' E 035" 25.908' |  | Katilu | T. South | Lokapel ECD | [5 empty] | 0 | 1 | YES | Well fenced. In use. Space small
Kagiturikon ECD | Education | 2014/2015 | N 02" 25.944' E 035" 25.412' |  | Kaputir | T. South | Kagiturikon ECD | [5 empty] | 0 |  |  | Fence nil. Chimney nil. Dh walls raised. In use
Loperot ECD | Education |  | N 02" 20.043' E 035" 50.101' |  | Kalapata | T. South | Loperot | [5 empty] | 0 | 0.9 | YES | Complete structures. No chimney. Floors need repairs(Dining)
Lokaburu ECD | Education | 2014/2015 | N 02" 23.781' E 035" 33.365' |  |  | T. South | Lokaburu | [5 empty] | 0
Kangakipor ECD | Education |  | N 02" 22.606' E 036" 01.831' |  | Kalapata | T. South | Kangakipor | [5 empty] | 0 | 1 | YES | Solar & Batteries Installed. Operational
Kakongu ECD | Education |  | N 02" 01.713' E 035" 31.431' |  | Lobokat | T. South | Kakongu | [5 empty] | 0 | 1 | YES | Complete & Operational. Installed with solar panels.
COSNTRUCTION OF LOUWAE DISPENSARY | Health | 2014/2015 | N 02° 49.765´ E 036° 12.108' | 7253476.12 | Louwae | CENTRAL | Kerio | LOKONE EMPORIOM | [5 empty] | 2901390.45 | 4352085.67 | 100 | Yes | In use by a community health worker. There is need for fencing and nurse.
NAKIRIA DISPENSARY | Health |  | N 03° 33.606´ E 035° 49.994' | 7400902 | Nakiria | CENTRAL | KALOKOL | MT.LOIMA GENERAL CONSTRUCTION |  |  | 42217 | 42248 |  | 2960360 | 4440542 | 100 | No | Need for fencing and fittings.
Lodoket Engol Dispensary | Health |  | N 02° 36.932´ E 036° 15.280' | 7500000 | Edoket Engol | CENTRAL | Kerio | Mankos Agencies Ltd | [5 empty] | 3000000 | 4500000 | 95 | No | Finishing not done. Contractor not on site.
Lolupe Dispensary | Health |  | N 03° 06.160´ E 035° 41.082' |  | Lolupe | CENTRAL | Kanamkemer | Lochakai Const Co Ltd | Haji Bilal Lochakai | 727070769 | 42125 | 42217 | 1 Month |  |  | 85 | No | Floor, Window panes and septic tank not done.
Mortuary Block in Turkana County Hospital | Health |  | N 03° 07.450´ E 035° 36.059' | 37950633.8 | Lodwar Town | CENTRAL | LODWAR TOWNSHIP | Naita Const Co Ltd | [7 empty] | 100 | No | Project complete awaiting hand over to clients. Parking lot, Chapel and fencing done..
Nakurio Dispensary | Health | 2013/2014 | N 02° 52.156´ E 036° 09.868' | 5600000 | Nakurio | CENTRAL | Kerio
Ekwar Dispensary | Health |  | N 03° 03.958´ E 036° 07.366' |  | Ekwar | CENTRAL | Kerio | [8 empty] | 100 | No | Need for a fence and a connection to water supply.
Longech Dispensary | Health | 2013/2014 | N 03° 32.722´ E 035° 55.406' | 9800000 | Longech | CENTRAL | KALOKOL |  |  |  | 41791 | 41974 |  |  |  | 100 | No | Project complete but the building is infested with bats. There is need for a fence and a staff house. The client ministry to visit the facility.
Kalokol Dispensary | Health | 2013/2014 | N 03° 31.200´ E 035° 50.941' | 9800000 | Kalokol Town | CENTRAL | KALOKOL | [8 empty] | 100 | No | Project complete but the building is infested with bats. There is need for a fence and a staff house. The client ministry to visit the facility.
Kapokor Dispensary | Health | 2014/2015 | N 03° 21.163´ E 035° 41.456' |  | Kapokor | CENTRAL | KALOKOL | Lochn Gen Supplies | [7 empty] | 100 | No | Project complete and ready for commissioning.
Akatuma Dispensary | Health |  | N03⁰06.867' E036⁰06.991' | 6817133 | Eliye | Central | Kangatotha | Logolei Co Ltd | 42505 | [6 empty] | 90 | No | Complete and awaits coomissioning.Drainage system.No toilet.Need fencing.
Kangagetei Dispensary | Health |  | N03⁰09.972' E035⁰52.087' | 6817133 | Kangagetei | Central | Kangatotha | Jenalo Ent. Ltd | [7 empty] | 100 | No | Complete and not in use.Toilets to be dug.
Nayanae Angikalalio Dispensary | Health |  | N03⁰09.928' E035⁰32.869' | 9800000 | Nayanae Angikalalio | Central | Township | [8 empty] | 90 | Yes | No lights.Water and water tanks needed.No doctor's house.In use
Monti Dispensary | Health |  | N03⁰08.168' E035⁰38.509' | 7429985.6 | Monti | Central | Township | Lobeyi Const. Co. Ltd | [7 empty] | 100 | No | Complete and awaits commissioning.Need of water tanks and Solar installation.
ChokChok Dispensary | Health |  | N03⁰09.988' E035⁰43.737' | 6793756.6 | ChokChok | Central | Township | Egong Trading Co. Ltd | [7 empty] | 100 | No | Complete.Ready for Commissioning.
Naotin Dispensary | Health |  | N03⁰03.058' E035⁰32.883' | 7375090 | Naotin | Central | Kanamkemer | Lotiruk Building Const. Co.Ltd | [7 empty] | 90 | No | Need solar installation and water tanks.Drainage system in progress.
Natutun Dispensary and staff house | Health |  | N 02⁰ 55.100' E 035 26.573' |  | Natutun | Loima | Turkwel | [8 empty] | 1 | No | work dome well
OPD block, staff house and pit latrine | Health |  | N 02⁰ 54.839' E 035 24.239' |  | Turkwel | Loima | Turkwel | Lymas cleaning services ltd | [7 empty] | 1 | No | Satisfactory
Kabulokor Health centre | Health |  | N 02⁰ 48.819' E 035 26.573' |  | kabulokor | Loima | lobei | [8 empty] | 1 | Yes | project complete and in use
Lokipetot Areng'an Dispensary and staff house | Health |  | N 02⁰ 36.545' E 035 20.912 |  | Lokipetot Areng'an | Loima | lobei/kotaruk | Lorugum Medical Services Ltd |  |  |  |  | 7459865 |  |  | 1 | No | construction comlete
Naipa Dispensary | Health |  | N 02⁰ 31.138' E 035 22.541 |  | Nang'oleki | Loima | lobei/kotaruk | [8 empty] | 1 | Yes | No inlet Depends on rain water
Lorugum sub-county Hospital | Health |  | N 02⁰ 52.544`E 035 15.396 |  | Lorugum | Loima | Turkwel | Puch Building and construction ltd | 728527555 | 42200 | 42353 |  |  |  |  | 1 | Yes | commisioned, under use with staff
locher Ekuyen Dispensary staff house | Health |  | N 02 ⁰52.004`E 035 11.05 |  | locher Ekuyen | Loima | Loima | [8 empty] | 1 | Yes | construction are standard, awaiting commisioning
nakorimunyen dispensary staff house & pit latrne | Health |  | N 02 ⁰51.20`E 035 05.330 |  | Nakorimunyen | Loima | loima | Aminit Suppliers & const LTd | 728527555 | May, 2015 |  |  | 2940364 | 4410546 |  | 1 | Yes | works ongoing, contractor ad abandoned site due to lack of funds, no fence in the plan
lochor emeyen dispensary | Health |  | N 02⁰ 48.658`E 035 04.824 |  | Lochee Emeyen | Loima | loima | [8 empty] | 1 | Yes | well completed, no fence, commisioned and its in use, no staff house
lochor Edome dispensary staff house & pit latrine | Health |  | N02⁰ 45.329`E 035 01.552 |  | Lochor Edome | Loima | Lochor Edome | [8 empty] | 1 | Yes | no fence, awaiting commmision
lochor alomala dispensary, staff huouse, pit latrine | Health |  | N 02 ⁰48.636`E 035 52.848 |  | lochor Alomala | Loima | Lorenkipi/lokiriama | Perro Inv Ltd | [7 empty] | 1 | No | awaiting commmisioning, no fence, well constructed
Urum dispensary | Health |  | N 02⁰ 57.404`E 035 41.630 |  | Urum | Loima | Lorenkipi/lokiriama | [8 empty] | 1 | Yes | commisioned, under use, no fence, without water
sasak dispensary, staff house, pit latrine | Health |  | N 02⁰ 46.028`E 035 13.051 |  | Sasak | Loima | lobei/kotaruk | [8 empty] | 1 | No | not fenced, ready for commisioning
lorengkipi dispensary | Health |  | N 02 ⁰ 34.428`E 034 59.450 |  | Lorenkipi | Loima | Lorenkipi/lokiriama | Namuyan Ent. | 42131 | 42200 |  |  | 7494060 |  |  | 1 | No | not fenced, ready for commisioning
loroo dispensary | Health |  | N 03 ⁰ 18.852`E 035 17.915 |  | Loroo | Loima | Turkwel | Rio constr ltd | [7 empty] | 0.75 | No | contructor on site, finishing is in processs
Kaakalel Dispensary | Health |  | N 02° 27.060´ E 036° 04.198' |  | Kaakalel | T. South | Kalapata | [8 empty] | 0.5 | NO | Not complete. Materials on site. No workers. Staff house not roufed. Dispensary not well finished. Pit latrine not done.
Kakongu maternity ward | Health |  | N 02" 01.321' E 035" 31.579' |  | Kakongu | T. South | Lobokat | [8 empty] | 0.9 | NO | Project complete without equipment. Ceiling is not in some part of the roof
Loyapat Dispensary | Health |  | N 02" 50.391' E 035" 28.892' | 7988967.8 | Loyapat primary school | T. South | Lobokat | Adukon trans supplies ltd | [7 empty] | 1 | YES | Project complete. Repair floor. Should be fenced off. Pilling of floors. Need repairing.
Loyapat Dispensary | Health |  | N 01" 50.198' E 035" 28.740' |  | Loyapat | T. South | Lobokat | [8 empty] | 1 | NO | Ready for commissioning. Structures complete.
Lochwaa Dispensary | Health |  | N 02" 36.103' E 035" 39.380' | 7998967 | Lochwaa | T. South | Lokichar | Square africa yok ltd | [7 empty] | 0.6 | NO | Roofing not finished. Latrines doors not installed. No ceiling. Incomplete project
Lokichar Drug store | Health |  | N 02" 22.166' E 035" 38.961' |  | Akaalis | T. South | Lokichar | [8 empty] | 1 | NO | No fence. Complete structures. Pit latrine doors not easy to be closed. Need set ups
Nakaalei Health Centre | Health |  | N 02" 32.236' E 036" 12.905' |  | Nakaalei | T. South | Kalapata | [9 empty] | YES | Structure complete. No staff. Some small cracks. Need electricity. Opened. Staff house needed.
Kaputir Dispensary | Health | 2014/2015 | N 02" 04.438' E 035" 29.983' |  |  | T. South | [11 empty] | Amref & Danida labels yet for County Government
Kagiturikori Dispensary | Health | 2014/2015 | N 02" 26.027' E 035" 25.664' |  | Kagiturikori Dispensary | T. South | Katilu | [10 empty] | Staff house broken windows. Not equipped. No personnel.
Lomeleku Dispensary | Health |  | N 02" 21.795' E 036" 58.126' |  | Lomeleku | T. South | Kalapata | [8 empty] | 0.5 | NO | Not complete. Window glasses not installed
Kakongu Dispensary | Health |  | N 02" 01.329' E 035" 31.579' |  | Kakongu | T. South | Lobokat | [9 empty] | NO | Done upto the linton. No materials on site. Pit latrine not started. Staff quarters not started.
Namakat Dispensary | Health |  | N 02" 09.736' E 035" 27.032' |  | Namakat | T. South | Katilu | [8 empty] | 0.9 | NO | Structures complete. Double toilet complete. Staff quarters ceiling not done well.
Lorogon Dispensary | Health |  | N 01" 55.998' E 035" 21.688' |  | Lorogon | T. South | Lobokat | [8 empty] | 0.7 | NO | Project still on going. Materials on site. Signage in place. Constructor not on site.
Sopel Dispensary | Health |  | N 02" 47.346' E 035" 31.290' |  | Sopel | T. South | Lokichar | [8 empty] | 1 | YES | No lighting system. Water far from the facility. No staff house.
Refurbishment of office building | TTI |  | N 03° 07.035´ E 035° 36.162' | 4542583 | LODWAR TOWNSHIP | CENTRAL |  | kakurio contractor |  |  |  |  | 4542582.9 |  | 100 | YES | 04 NO of AC installed. A waiting bay and 2 parking lots constructed. Repainting of the office block done. The office with office furniture. Windows, doors and ceiling replaced. Thfacility was fenced and a gate erected.
Construction of market stall and toilet project | TTI |  | N 02° 52.257´ E 036° 09.903' | 9806672 | kerio ward | CENTRAL | Nakurio | parakati constraction |  |  |  |  | 6147140.9 | 3659531.1 | 90 | NO | Market stall done but no Latrines. The floor is rough (finishing not done). Contractor not on site.
Construction of market stalls and toilets | TTI |  | N 03° 32.070´ E 035° 52.708' | 10337827.2 | Kalokol | CENTRAL | Kalokol Town | seansapps co.ltd | [5 empty] | 10337827.2 | 80 | NO | Maket stalls and Latrines done (though in need of breathers). The fence is not yet done. There is need for a ramp to the stall. The lockable doors are falling off hence a need for repair.
Turkwel market stalls | TTI |  | N 02⁰ 55.157`E 035 23.905 Elevation 547 |  | Turkwel | Loima | Turkwel | Marekai Building & nonst. | [6 empty] | 1 | NO | Done well Awaiting comng
renovation of lokiriama market stalls | TTI |  | N 02⁰ 45.505`E 034 52.220 Elevation 896 |  | Lokiriama | Loima | Lokiriama | Nyati Gen Const. |  |  |  |  | 2400000 | 1600000 | 1 | NO | Not commisioned Gatein bad condition
Katilu market & toilets | TTI |  | N 02" 16.393 E 035" 25.858 |  | Katilu | T. South | Katilu | [7 empty] | 0.9 | No ops | Toilet roof flown off. Toilets to be re-done. No gabbage pit. Not fenced off.
Eco lodge hotel | TTI |  | N 01" 50.224 E 035" 33.021 |  | Lobokat | T. South | Kainuk | [7 empty] | 0.75 | NO | Project on going. Contractor on site. Materials on site. Ceiling being installed. Finishing being done.
Lokichar slaughter house | TTI |  | N 02" 22.987 E 035" 39.250' |  | Lokichar | T. South | Town chim | [7 empty] | 1 | YES | Fenced with gate. Structures still in good state. Need additional sewage system
Kalemungorok stall market | TTI | 2014/2015 | N 02" 08.540 E 035" 29.801' |  | Katilu | T. South | Kalemungorok | [9 empty] | Customer ramp. Good work. Need 5 rumps. Customers rump is not disability.
Katilu stall market | TTI | 2014/2015 | N 02" 16.404 E 035" 25.887' |  | Katilu | T. South | Katilu market | [9 empty] | Stalls not in use. Entrance not good. Toilet floor incomplete
Revival of Turkana Fisheries Cooperative Society(TFCS) | FEP |  | N 03° 32.253´ E 035° 51.849' | 7000000 | KALOKOL | CENTRAL | Kalokol Town | Kalokol Engineering |  |  |  |  | 4200000 | 2800000 | 65 | No | Fencing done with a gate. Store under construction.
Construction of Fresh Fish Market | FEP |  | N 03° 32.238´ E 035° 51.440' | 9456640 | KALOKOL | CENTRAL | Impressa | Nakiria Co. Ltd | [5 empty] | 9456640 | 100 | No | Need for a septic tank and latrines.
Purchase of two patrol boats | FEP |  | N 03° 33.378´ E 035° 53.625' | 21754947 | KALOKOL | CENTRAL |  | Captain Andys Fishing Ltd | [6 empty] | 100 | YES | Two Engine Boats in place.
Nakoret Sale Yard | FEP |  | N 02° 41.410´ E 036° 15.016' |  | KERIO | CENTRAL | Nakoret | [7 empty] | 100 | YES | Complete fence done.
Construction of Multiplication and breeding centre | FEP |  | N 03° 01.312´ E 036° 01.035' | 29002257 | KERIO | CENTRAL | Nanyakipi | Lotulia Kor Contractors |  | 26/08/2015 | 42339 |  | 20301579.9 | 8700677.1 | 40 | No | Structures at roofing stage. Contractor not on site.
Kangatotha Animal SaleYard | FEP |  | 056 N03⁰07.930' E035⁰57.7373' | 2449076 | Kangatotha | Central | Kangatotha | Lobei Construction Ltd | [6 empty] | 100 | Yes | Project Complete.Well fenced.The gates were well made as per the community argue.
nakorokoroite poultry | FEP |  | N 02⁰ 48.867`E 035 22.549 Elevation 584 |  | Lobei kotaruk |  | kabulokos | [7 empty] | 1 | No | complete chichen distributors
kalemyang sale yard | FEP |  | N 02⁰ 43.685`E 035 22.099 Elevation 602 |  |  |  | kalemyang | Locher Emeyen Contractors | [6 empty] | 1 | No | completeawaiting commisioning
lorugum slaughter house | FEP |  | N 02⁰ 52.922`E 035. 14.934 Elevation 625 |  | Turkwel |  | lorugum | [7 empty] | 1 | No | awaiting commiioning
Nadapal tannery (industry) | FEP |  | N 03⁰ 05.853`E 035 31.893 Elevation 518 |  | Turkwel |  | nadapal | [7 empty] | 1 | No | complete awaiting more allocation for specil analyzation
Napeililim holding ground | FEP |  | N 03⁰ 25.94`E 22.223 Elevation 652 |  | Turkwel |  | napeililim | Puch Building construction |  |  |  |  | 34142164 | 14632356 | 1 | No | contractor site works undergoing fencing ongoing
Kalokol Ward Admimistrator's office | PSDDM | 2014/2015 | N 03° 31.741´ E 035° 51.511' | 11528958 | Kalokol | Central | Kalokol Town | Amana Suppliers Ltd |  |  |  |  | 3458687.4 | 8070270.6 | 100 | NO | Project complete.
Kerio Ward Admimistrator's office | PSDDM | 2014/2015 | N 03° 00.035´ E 036° 03.533' | 9379270 | Kerio | Central | Kerio Town | Akajalo Const Gen Supplies | [6 empty] | 100 | Yes | Project complete.
Ward Administration Office | PSDDM | 2014/2015 | 053 N03⁰13.872' E036⁰01.162' | 9377750 | Kangatotha | Central | Eliye | [7 empty] | 100 | Yes | Project complete.
Administration Office Lodwar | PSDDM | 2014/2015 | 064 N03⁰06.970' E035⁰35.450' | 10800000 | Township | Central | Nakwamekwi | Ekori Kapana Inv Ltd | [8 empty] | Project complete. Need for landscaping, installation of a gate and supply of furniture.
Kanamkemer Ward Admin Office | PSDDM | 2014/2015 | 077 N03⁰06.480' E035⁰37.069' | 9843272 | Kanamkemer | Central | Kanamkemer | Natoot Const. Co Ltd | [6 empty] | 50 | No | Incomplete.Neglected site.Poor drainage system.No doors fixed yet.
Turkwel ward administration ofice | PSDDM | 2014/2015 | N 03 07.190 E 035 35.796 Elevation 568m |  | Turkwel |  | Turkwel | Narina investment company |  |  |  |  | 3600000.18 | 8400000.42 | 1 | No | job done satisfactory
Lobei/kotaruk ward administration office | PSDDM | 2014/2015 | N 02⁰ 44.007' E 035 21.625 Elevation 587m |  | lobei/koaruk |  | kalemnyang | Sasak contr ltd | April, 2015 |  |  |  | 3008672.4 | 7020235.6 | 0.9 | No | Satisfactory
Loima ward Administration office | PSDDM | 2014/2015 | N 02⁰ 50.717' E 035 03.393' Elevation 719m | [11 empty] | 0.8 | No | contractor not on site
Lokiriama/lorenkipi ward admin office | PSDDM | 2014/2015 | N 02 ⁰45.433 E 035 03.393 Elevation 891m | [11 empty] | 1 | Yes | Satisfactory
Lokichar ward administrator office | PSDDM | 2014/2015 | N 02" 21.776' E 035" 38.244' |  | Lokichar |  | Lokichar (IDP) | [7 empty] | 0.9 | NO | Fenced & with gate. Structures complete. Needs land scaping.
Kaputir ward admin office | PSDDM | 2014/2015 | N 01" 50.224 E 035" 33.026 |  | Kaputir |  | Nakwamoru | [7 empty] | 0.9 | NO | Project complete. Gate pillars need repairs. Fenced with gates. Awaits opening.
Lobokat ward admin office | PSDDM | 2014/2015 | N 01" 47.024 E 035" 30.880 |  | Lobokat |  | Kainuk | [7 empty] | 0.7 |  | Toilets need doors. Finishes for painting and windows required.
Katilu ward admin office | PSDDM | 2014/2015 | N 02" 15.698 E 035" 25.841 |  | Katilu |  | Katilu | [7 empty] | 0.6 |  | Toilet dug but destroyed by rains
Kalapata ward admin office | PSDDM | 2014/2015 | N 02" 22.731 E 036" 01.993 |  | Kalapata |  | Kangakipor | [7 empty] | 1 | YES | Structures complete. Fenced with gate. In use. No staff in office.
Turkana Central Solar Project - Kapua Primary | Energy | 2014/2015 | N 03° 25.628´ E 035° 39.179´ | 18879540 | Kalokol | CENTRAL | Kapua Primary | Turkana Salama |  | 42125 | 42125 |  | 7561611.99 | 11317928.01 | 100 | Yes | One pannel need to be repaired.
Turkana Central Solar Project - Kangirisae Primary | Energy | 2014/2015 | N 02° 36.933´ E 036° 15.280´ | 18879540 | Kerio | CENTRAL | Kangirisae Primary | Turkana Salama |  |  |  |  | 7561611.99 | 11317928.01 | 100 | Yes | Project complete.
Kalokol Tree Nursery - Fencing and Supply of Tanks. | Energy | 2014/2015 | N 03° 31.520´ E 035° 50.117´ | 5597900 | Kalokol | CENTRAL | Napasinyen | Ng'ikajik Group Co. Ltd |  | 42309 | [5 empty] | No | Fencing done with a gate and the shade. The stand for the tank in palce.
Turkana Central Solar Project - Lochuga Primary | Energy | 2014/2015 | N 03° 29.975´ E 035° 50.318' | 18879540 | Kalokol | CENTRAL | Lochuga Primary | Turkana Salama |  | 42309 |  |  |  |  | 100 | Yes | Power is not lighting in two classes.
Nakurio Tree Nursery | Energy | 2014/2015 | N 02° 52.323´ E 035° 10.375' | 5597900 | Kerio | CENTRAL | Nakurio | Ng'ikajik Group Co. Ltd | [6 empty] | 100 | No | Fencing done and a shade constructed. Termites are invading the wooden poles used in the fence and the shade.
Turkana Central Solar Project - Nadoto Primary | Energy | 2014/2015 | N 03° 04.991´ E 036° 05.408' | 18879540 | Kerio | CENTRAL | Nadoto | Turkana Salama |  | 42309 |  |  |  |  | 100 | Yes | Project complete.
Kangatotha Tree Nursery | Energy | 2014/2015 | 051 N03⁰07.844' EO35⁰57.973' | 5597900 | Kangatotha | Central | Kangatotha | Ngikajik Group Co Ltd | [6 empty] | 70 | No | Not complete.Well fenced and awaits for the seedlings.
Nakadukui Solar Installation | Energy | 2014/2015 | 061 N03⁰10.363' E035⁰45.687' |  | Kangatotha | Central | Nakadukui | Turkana Salama Enterprise Ltd | [6 empty] | 100 | Yes | Well installed and in complete.
St.Michael Kawalase Sollar Installation | Energy | 2014/2015 | 067 N03⁰07.487' E035⁰36.903' |  | Township | Central | Napetet | [7 empty] | 30 | Yes | Poor standard workmanship.
Napeikar school solar pv system | Energy | 2014/2015 | N 03⁰ 00.365' Elevation 535 |  | Turkwel |  | Napeikar | Magee construction company limited | [6 empty] | 1 | Yes | Satisfactory
Napeikar Dispensary solar pv systems | Energy | 2014/2015 | N 03⁰ 00.204' E 035 30.425 Elevation 535 |  | Turkwel |  | Napeikar | Magee construction company limited | [6 empty] | 1 | Yes | Satisfactory
Kabulouor primary school solar panel system | Energy | 2014/2015 | N 02 ⁰48.926' E 035 22.344' Elevation 606 |  | Lobei/kotaruk |  | Kabulour | Magee construction company limited | [6 empty] | 1 | Yes | Satisfactory
Kotela primary school solar panel system | Energy | 2014/2015 | N 02⁰ 45.717 E 035 22.054 Elevation 589m |  | Lobei/kotaruk |  | Kotela | Magee construction company limited |  |  |  |  | 5416937.59 | 9277180.34 | 1 | Yes | Satisfactory
Kalemnyang primary school solar panel system | Energy | 2014/2015 | N 02⁰ 44.110' E 035 22.063 Elevation 603m |  | Lobei/kotaruk |  | Kalemnyang | Magee construction company limited | [6 empty] | 1 | Yes | Satisfactory
naipa pri. School solar project system | Energy | 2014/2015 | N 02⁰ 31.197`E 035 22.392 Elevation 638 |  | lobei/kotaruk |  | Naipa | Magee construction company limited | [6 empty] | 1 | YES | in use project
lokwatuba dispensary | Energy | 2014/2015 | N 02⁰ 53.606`E 035 59.633 Elevation 804 |  | Loima |  | Lokwatuba | [7 empty] | 1 | YES | in use project
Urum pri. School power system | Energy | 2014/2015 | N 02⁰ 57.529`E 035 41.792 Elevation 1003 |  | Lorenkipi/Lokiriama |  | Urum | Magee construction company limited |  |  |  |  | 5416937.59 | 9277180.34 | 1 | YES | in use project
Lokiriama ward free nursery | Energy | 2014/2015 | N 02⁰ 45.084`E 035 52402 Elevation 848 |  | Lorenkipi/Lokiriama |  | Lokiriama | Davine Ltd | [6 empty] | 1 | YES | was abandoned, trees are nott in space
Lomilo ECD/pri power solar system | Energy | 2014/2015 | N 02⁰ 46.916`E 035 08.727 Elevation 715 |  | lobei/kotaruk |  | lomilo | Magee construction company limited | [6 empty] | 1 | YES | in use project
Lolemgete primary school solar panel system | Energy | 2014/2015 | N 03⁰ 00.500' E 035 15.816' Elevation 627m |  | Turkwel |  | Lolemgete | Magee construction company limited | [6 empty] | 1 | Yes | in use
Kalokutanyang ECD solar oanel system | Energy | 2014/2015 | N 03⁰ 20. 480' E 035 28.192' Elevation 563m |  | Turkwel |  | kalokutanyang | Magee construction company limited | [6 empty] | 1 | Yes | inverter is malfunctioning
Loroo primary school solar panel system | Energy | 2014/2015 | N 03⁰ 18.979' E 035 17.905' Elevation 576m |  | Turkwel |  | Loroo | Magee construction company limited | [6 empty] | 1 | Yes | In good condition
Katilu Tree Nursery | Energy | 2014/2015 | N 02" 11.385 E 035" 32.451 | [11 empty] | 0.9 | YES | Water tank installed
Nakwamoru Health Centre Solar Istallation | Energy | 2014/2015 | N 02" 03.201 E 035" 25.872' |  | Kaputir | [10 empty] | YES | No. of solar panels less & batteries
St. Teresa primary Solar panels | Energy | 2014/2015 | N 02" 48.323 E 035" 37.323' |  | Lokichar |  | Kinador | Pisonar | [6 empty] | 1 | YES | Operational. Complete.
Solar panels lochwangikamek primary school | Energy | 2014/2015 | N 02" 36.467 E 035" 37.301' |  | Lokichar |  | Lochwaa | [7 empty] | 1 | YES | Installed to one stream. Solar panels are less. Performance improved due to it.
Solar panels lnstallation lochwangikamata health centre | Energy | 2014/2015 | N 02" 36.422 E 035" 39.254' |  | Lokichar |  | Lochwaa | [7 empty] | 1 | YES | Installed to staff houses only
Solar panel Napussmoru Dispensary | Energy | 2014/2015 | N 02" 36.929 E 035" 50.809' |  | Lokichar |  | Napussmoru | [7 empty] | 1 | YES | Solar installed. Operational. Complete. Sign plot is there
Lokichar Solar street Lights | Energy | 2014/2015 | N 02" 36.929 E 035" 50.809' |  | Lokichar |  | Town | [7 empty] | 1 |  | Working
Kalapata Tree Nursery | Energy | 2014/2015 | N 02" 32.303 E 036" 13.441' |  | Kalapata |  | Nakaalei | [8 empty] | NO | Incomplete shade. Incomplete water tank stand. Use of wood as fence post.
Kainuk Tree Nursery | Energy | 2014/2015 | N 01" 46.390 E 036" 29.928' |  | Lobokat |  | Kainuk | [9 empty] | Water tank installed. Fenced. Shade constructed. No seedling.
Kaputir Tree Nursery | Energy | 2014/2015 | N 02" 04.972 E 035" 27.731'
Kaputir Solar Installation | Energy | 2014/2015 | N 02" 04.571 E 036" 27.342'
Kangakipor primary school Solar Installation | Energy | 2014/2015 | N 02" 22.469 E 036" 01.864' |  | Kalapata |  | Kangakipor | [7 empty] | 1 | YES | Solar batteries Installed. Operational
Kakongu primary school Solar Installation | Energy | 2014/2015 | N 02" 01.709 E 035" 31.429' |  | Lobokat |  | Kakongu | [7 empty] | !00% | YES | Solar panel installed
Nakabusen primary school Solar Installation | Energy | 2014/2015 | N 02" 15.655 E 035" 33.817' |  | Katilu |  | Nakabusen primary school | [7 empty] | 1 | YES | Solar panel installed. Batteries in place. Operational. Signage done.
Lokichar Tree Nursery | Energy | 2014/2015 | N 02" 22.849 E 035" 38.657' |  | Lokichar |  | Nachukule | [8 empty] | YES | Need to replace fence posts with angle lines. Shade structures not sustainable
Monti – Namerisinyen - Lokatukon | Roads |  | N 03° 11.685´ E 035° 38.860´ | 3090281.76 | LODWAR TOWNSHIP | CENTRAL | Monti – Namerisinyen - Lokatukon | Ashmmartna Constructor Co. Ltd |  |  |  | 3090281.76 | 0 | 100 | YES | Project complete.
Light grading of Kerio-Ekwar | Roads |  | N 03° 00.139´ E 036° 03.624´ | 7168800 | KERIO | CENTRAL | Kerio-Ekwar | Turkana South Com AG Ltd |  |  |  | 5018160 | 2150640 | 100 | YES | Project complete.
Heavy grading and bush clearing of Nabwel-Ekorot Road | Roads |  | N 03° 32.659´ E 035° 49.971´ | 2690980 | KALOKOL | CENTRAL | Nabwel-Ekorot | Muruongor Const and General Supplies Ltd |  |  |  |  | 2690980 | 100 | YES | Project complete.
Bush clearing and light grading of Nakalale-Nabuskal-Kairiama Road | Roads |  | N 03° 01.934´ E 035° 58.352´ | 3580290 | KALOKOL | CENTRAL | Nakalale-Nabuskal-Kairiama | Kablade Invest Ltd | [5 empty] | 100 | YES | Project complete. The road is motorable.
Heavy grading and bush clearing of Kalotum-Nachamai-Nanukumeri Road | Roads |  | N 03° 17.898´ E 035° 43.570´ |  | KALOKOL | CENTRAL | Kalotum-Nachamai-Nanukumeri | Mieebo Const & Supplies | [5 empty] | 100 | YES | The road is motorable.
Bush clearing and light grading of Akatorongot-Kangirisae Road | Roads |  | N 02° 57.045´ E 036° 05.178´ | 11910000 | KERIO | CENTRAL | Akatorongot-Kangirisae | Ngakomwam Contr Ltd | [5 empty] | 100 | YES | Project complete. The road is motorable.
Heavy grading and bush clearing of Kalokol-Airstrip Junction-Namukse-Loyoro Road | Roads |  | N 03° 29.289´ E 035° 50.509´ | 2,545,620,00 | KALOKOL | CENTRAL | Kalokol-Airstrip Junction-Namukse-Loyoro | Nados Construction Co.Ltd |  |  |  |  | 2,545,620,00 | 100 | YES | Project is complete. The road is motorable.
Spot improvement works at Lodwar-Kalokol-Eliye Springs Road | Roads |  | N 03° 29.039´ E 035° 37.730´ | 5689800 | KANGATOTHA | CENTRAL | Lodwar-Kalokol-Eliye Springs | Natamakarua Eng Ltd | [5 empty] | 100 | YES | Project is complete. The road is motorable.
Naipa-Moruongor junction | Roads |  | N 02⁰ 31.632`E 035 22.228 Elevation 636 |  | Lobei kotaruk | LOIMA | Naipa-Moruongor Junction | Apen Investment Company | [5 empty] | 1 | YES | destroyed by rain
Routine maintainance of Naipa - Moruongor | Roads |  | N 02⁰ 31.632`E 035 22.228 Elevation 636 |  | Lobei kotaruk | LOIMA | Naipa | [6 empty] | 1 | YES | destroyed by rain
New Turkwel Kalemnyang - Naipa road | Roads |  | N 02⁰ 54.616`E 035 22.648 Elevation 578 | 10422600 | Lobei kotaruk | LOIMA | Turkwel | Lilmark Construct | [5 empty] | 1 | YES | poor drainage, completed
Lochor Emeyen-Namorputh-Lokwatubwa road | Roads |  | N 02⁰ 50.513`E 035 0248 Elevation 740 | 2141824 | Loima | LOIMA | Lochor Emeyen-Namoruputh-Lokwatuba | [6 empty] | 1 | YES | underwork, drainage system ruined, rain destroyed roads
Nakorimunyen-Kakorikamar road | Roads |  | N 02⁰ 51.324`E 035 03.046 |  | Loima | LOIMA | Nakorimunyen | Urum Const Co. Ltd | [5 empty] | 1 | YES | in use, job done well
Lokwatuba-Kapetakinei road | Roads |  | N 02⁰ 50.957`E 035 01.809 Elevation 741 | 2702800 | Loima | LOIMA | Lokwatuba-Kapetakinei | Silale Moonlight Investment Limited | June, 2015 | July, 2015 |  |  |  | 1 | YES | drainage system is okay, in use
Urum-Namoruarengen | Roads |  | N 02⁰ 57.486`E 035 04.32 Elevation 1002 | 3800980 | Lorengipi/Lokiriama | LOIMA | Urum | Apuco Holdings Group Co. Ltd | 23rd June,2015 | 10th July, 2015 |  |  |  | 1 | YES | nin use, good drainage
Nakurio-Kaemanik | Roads |  | N 02 41.957`E 035 04.32 Elevation 785 | 3958848 | Lorengipi/Lokiriama | LOIMA | Nakurio | Rikinei Construction Company limited | [5 empty] | 1 | YES | rains have destroyed some parts of the road
Lobei-Kalapata | Roads |  | N 02⁰ 43.787`E 035 06.787 Elevation 732 | 3073590 | Lobei/Kotaruk | LOIMA | Lobei | Almond Air and Logistics | [5 empty] | 1 | YES | in use, raines ruined some segments of the road
Lorugum-NO Uganda Road | Roads |  | N 02⁰ 52.621`E 035 14.791 | 32642400 | Turkwel | LOIMA | Lorugum/Namoruputh/Lokiriama | [6 empty] | 1 | YES | in use
Lorugum-Nakwasinyen-Kopeto Road | Roads |  | N 02⁰ 55.634' E 035 16.074' Elevation 618m | 7123101 | Turkwel | LOIMA | Lorurum-Nakwaasinyen-Kopeto | [6 empty] | 1 | YES | Drainage flooded by rains
Nakwamekwi-Kaloboi-Kaikapel | Roads |  | N 03⁰ 07.288' E 035 35.149 Elevation 508m | 4016964 | Turkwel | LOIMA | Nakwamekwi-Kaloboi-Kaikapel | [6 empty] | 1 | YES | In good condition apart from some parts that have been ruined by the rains
Napeililim- Kasagol-Etom-Loparia | Roads |  | N 03⁰ 24.740' E 035 21.381 Elevation 661m | 3070000 | Turkwel | LOIMA | Napeililim | Kabarait Builders and Construction Co. Ltd | [5 empty] | 1 | YES | in use
Nakaalei- Kaatir Road | Roads |  | N 02° 32.164´ E 036° 11.947´ | 5171280 | Kalapata | T SOUTH | Naakalei- kaatir | Philona Ltd | [5 empty] | 1 | YES | Complete. In good condition
Lochwaa- Napusmoru Road | Roads |  |  |  | Lokichar | T SOUTH | Napusmoru | [6 empty] | 1 | YES | Complete. Operational. It's perfect
Astus-Namabu Road | Roads |  | N 01° 47.187´ E 035° 31.137´ |  |  | T SOUTH | [9 empty] | No branding. Rarely used.
Lokabusen- Lomonying- Lokapel Road | Roads | 2014/2015 | N 02° 03.819´ E 035° 52.421 |  | Katilu | T SOUTH | Nakabusen | [6 empty] | 1 | YES | Road complete. Grading done. Road drainage done. Signage done.
Naoyarega- Kapelbok Bridge | Roads |  | N 02° 06.076´ E 035° 26.178 | 98062884 |  |  |  | Naipa Building Co. Ltd |  |  |  | 29418865.2 | 68644018.8 | 0.15 |  | on-Going
Kanaodon- Lokaburu Road | Roads |  | N 02° 29.016´ E 035° 24.938 | 2635752 | Katilu Road |  | Kanaodon |  |  |  |  | 2635752 | 0 | 1 |  | complete but records indicate that the contractor was paid 30% . Justification of completion without 70%?
Karoge-Lotunluja-Lokaburu Road | Roads |  | N 02° 24.684´ E 035° 33.143 | 2820120 | Katilu |  | Lokabum | Westmint Construction Ltd. |  |  |  | 2820120 | 0 | 1 | YES | Complete
Kakongu- Lokwamosing Road | Roads |  | N 02° 01.744´ E 035° 31.516 | 5868440 | Lobokat |  | Kakongu | Turkana General Co. Ltd |  |  |  | 5868440 | 0 | 0.95 | YES | Drainage not well done
Kaekunyuk-Korinyang Road | Roads | 2014/015 | N 02° 14.230´ E 035° 33.332 | 2696652 | Katilu |  | Kaekunyuk-Korinyang | Epae company |  |  |  | 2696652 | 0 | 0.9 | YES | Poor drainage system done. Bush not cleared well.
Sopel- Lochwaa Road | Roads |  | N 02° 39.649´ E 035° 38.084 | 2107140 | Lokichar |  | Sopel- Lochwaa | Natotoo Enterprises Road |  |  |  | 2107140 | 0 | 1 | YES | Drainage done. No sign post.
Arboretum Lodwar | Lands |  | 076 N03⁰06.859' E035⁰36.004' | 2100000 | Township | Central | Lodwar | Jibu Langu Construction |  |  |  | 1542704 | 557296 | 40 | Yes | Negleted project.Poor labelling and Very bad workmanship.
Fencing of Ministry's Offices | Lands |  | 076 N 03⁰07.123' E 035⁰36.132' | 4930638 | Township | Central | Lodwar | Katilu Builders |  |  |  | 4930638 | 0 | 100 | Yes | Project complete.
Construction of recreation parks and abolution blocks in Lodwar | Lands |  |  | 19935371.4 | Township | Central | Lodwar | Turkana Salama |  |  |  | 0 | 19935371.4 | 0 | No | No works done. Land grabbed by a private developer. Case in court.
Construction of Bus park. | Lands |  |  | 14574095 | Township | Central | Lodwar | Mena Inv Ltd |  |  |  | 10201866.5 | 4372228.5
Supply and delivery of survey equipments | Lands |  |  | 8000000 | Township | Central | Lodwar | Measurement Systems Ltd |  |  |  | 8000000 | 0 | 100 | Yes | Equipments in use
Physical Planning of potential towns in the County | Lands |  |  | 334131300 | County Wide | County Wide | County Wide | Geomaps & Habitat Planners |  |  |  | 267305040 | 66826260 | 80 | Done | Project complete.
Kalokol Street Lights | Lands |  | N 03° 32.253´ E 035° 51.849' | 18000000 | Kalokol | Central | Kalokol | Muruong'or Co Ltd
Renovation of UN camp Lokichogio | F$P | 2013-2014 | N04⁰12.465' E034⁰21.908' ELV 626m |  | Lokichogio |  | Lokichogio UN Camp | [5 empty] | 1 | Yes | Project complete and operational
Renovation- 4 blocks of 2 units each | F$P | 2014/2015 | N04⁰12.465' E034⁰21.908' ELV 626m | 36263314.23 | Lokichogio |  | Lokichogio Un Camp | Rudolf construction co LTD | [5 empty] | NO | The team didn’t find renovation project. There was a new construction of 4 blocks 2 units each. The project manager was not involved. The client to provide committee with information on payment regarding the project.
construction of Lokichogio Slaughter House | F$P |  | N04⁰12.644' E034⁰21.225' ELV 660m |  | Lokichogio |  | Lokichogio | [5 empty] | 1 | yes
construction of Kakuma slaughter house | F$P | [11 empty] | 0 | NO | The team could not find the project in kakuma
installation and fabrication ofCess Barriers | F$P | 2013/2014 |  |  |  |  | Kakuma
Lokori Slaughter House | F$P |  | N01⁰57.108' E035⁰01.526' |  | Lokori/Kochodin |  | Lokori Town | [5 empty] | 1 | No | Main structure complete. Latrines done. Water tanks supplied but not installed. The facility needs labeling.
Nanam Borehole | WIA |  | N04⁰12.528' E034⁰33.603' EL 559m | 1694000 | Nanam Ward |  | Nanam Village | Sagal Petrol Station |  |  |  |  | 0.5 | No | The borehole has been drilled but havent been equipped
Nanam Waterpan | WIA |  |  |  | Nanam Ward |  | Nanam Village | [5 empty] | 0 | No | Nothing has been done up to now
Nanam Borehole | WIA |  | N04⁰12.631' E034⁰33.218' EL 566m |  | Nanam Ward |  | Nanam Village | [5 empty] | 1 | No | The borehole was drilled but thre is no water
Songot Waterpan | WIA |  | N04⁰12.631' E034⁰33.218' EL 566m | 9259310 | Songot Ward |  | Naremeto | Nawasin Co Ltd |  |  |  |  | 0.5 | No | The project is stalled
Songot Borehole | WIA |  | N04⁰01.028' E034⁰32.687' | 2608000 | Songot Ward |  | Lokudule | Turkana Quarry Services |  |  |  |  | 1 | Yes | The project is complete and there is water and a water trough
Lookulan Waterpan | WIA | [13 empty] | NOT DONE
Atiir Borehole | WIA | [13 empty] | NOT DONE
Namon (Kanakuring) Waterpan | WIA |  |  |  | Songot Ward |  | Kanakuring | [6 empty] | No | Incomplete
Letea Waterpan | WIA |  |  |  | Letea Ward |  | Lomosing Ekori | [6 empty] | No | Incomplete
Lomukur Waterpan | WIA |  |  |  | Letea Ward |  | Lomukor | [6 empty] | No | Yet to be done
Letea Borehole | WIA |  | N03⁰30.884' E034⁰48.463' EL 654m |  | Letea Ward |  | Letea Village | [5 empty] | 0.5 | No | Drilled and capped equipment not installed
Loita Sonyok Borehole | WIA |  |  |  | Letea Ward |  | Loita Sonyok Village | [5 empty] | 0.5 | No | Drilled and capped equipment not installed
Nakitongo Borehole | WIA |  |  |  | Letea Ward |  | Nakitongo | [7 empty] | Was drilled but water wasn’t found
Lokichogio W/S Kakuma W/S Oropoi, Lomidat, Lopiding,Kalobeyei | WIA |  |  |  | Songot, Lokichosio And Kalobeyei |  |  | Mwia | [5 empty] | No | Ongoing
Komunyaate Borehole | WIA |  |  |  | Lopur Ward |  | Kamunyaate | Ministry Satff And Lokichogio Water Providers | [5 empty] | No | Drilling complete yet to equip the borehole
Kakuma Water Supply | WIA |  |  | 13524010 | Kakuma Ward |  |  | To Be Sourced After Evaluation | [5 empty] | No | Tendering stage
Lokichogio Water Pan | WIA |  |  | 9238240 | Lokichogio Ward |  | Lokichogio | Yedida Investment Contractors | [5 empty] | No | Stalled
Nataparelim Waterpan | WIA |  |  | 9125600 | Kalobeyei Ward |  | Nataparelim | Morutena Investment Ltd | [5 empty] | No | Stalled at 59% complete, dozer not on site
Kakuma Water Pan | WIA |  |  | 9120105 | Kakuma Ward |  | Kakuma | Kaliou Enterprise Ltd | [5 empty] | No | Stalled at 31%, dozer not on site
Lopur Waterpan | WIA |  |  | 9224900 | Lopur Ward |  | Lopur | Kotome Building And Enterprise Ltd | [5 empty] | No | Contractor yet to request for assessment to be done
Lomosingekori Waterpan | WIA |  |  | 9408760 | Letea Ward |  | Letea Village | Kochodae Building Construction Ltd |  |  |  |  | 0.6 | No | The contractor is yet to make arrangement for assessment to be done.
Nataparelim Waterpan | WIA |  |  | 9125600 | Kalobeyei Ward |  | Nataparelim | Morutena Investment Ltd |  |  |  |  | 0.59 | No | Stalled, dozer not on site
Nariemeto Waterpan | WIA |  |  | 9259310 | Songot Ward |  | Naremeto | Nawasin Co Ltd |  |  |  |  | 0.38 | No | Stalled, dozer on site but believed to be spoilt and not in working condition.
Kapetadie Water Supply | WIA |  |  | 20000 | Nanam Ward |  | Nanam Village | Ministry Staff | [5 empty] | No | Not operational, insecurity
Arengoit Borehole | WIA |  |  | 2229990 | Lokichogio Ward |  |  | Bon Borehole Drillers | [6 empty] | Another site has been surveyed, the office to support the contractor to drill a replacement.
Naiperkar Borehole | WIA |  |  | 2700000 | Songot Ward |  | Naiperkar | Tiwae Investment Co Ltd | [5 empty] | No | The borehole equiped with handpump but will be equiped with agenset. Design works complete
Natir-Lokangae Borehole | WIA |  |  | 2620800 | Songot Ward |  | Lokangae | Ekanyarit Cons Supplies | [5 empty] | No | Another site has been surveyed, the office to support the contractor to drill a replacement.
Lokabuk Borehole | WIA |  |  | 2538900 | Kalobeyei Ward |  | Lokabuk | Eitanit Consultancy And Drilling | [5 empty] | No | Another site has been surveyed, the office to support the contractor to drill a replacement.
Lopuski Borehole | WIA |  |  | 2291100 | Lopur Ward |  | Lopur | Hussen Hand Pumps Repairs | [5 empty] | No | Bore hole collapsed. The office to support the contractor to drill a replacement borehole
Nakoyo Borehole | WIA |  |  | 2620800 | Lopur Ward |  | Nakoyo | Solar Tech Company | [5 empty] | No | Dry, the contractor supported to drill a replacement borehole where the office has surveyed
Nakiteng,O Borehole | WIA |  |  | 2635269 | Letea Ward |  | Nakiteng,O | Baraka Contractors | [5 empty] | No | The office has planned to equip the boreholes in the first and second week of december
Loitasonyok Borehole | WIA |  |  | 2620800 | Letea Ward |  | Loita Sonyok Village | Mt Pelekech Contractors | [5 empty] | No | The office has planned to equip the borhole in december 2015
Natiir Nadung,A Borehole | WIA |  |  | 2700000 | Kakuma Ward |  | Natiir | Lopiding Building And Construction Ltd | [5 empty] | No | Drilling complete yet to equip the borehole
Natiir Asekon Borehole | WIA |  |  | 2457630 | Kakuma Ward |  | Natiirasekon | Rasabana Enterprise Ltd | [5 empty] | No | Drilling complete. The office is planning to equip the borehole in december 2015
Kalobeyei Borehole | WIA |  |  | 2175000 | Kalobeyei Ward |  | Kalobeyei | Lorengesinyen Company Ltd | [5 empty] | No | Drilling complete. The office is planning to equip the borehole in december 2015
Letea Borehole | WIA |  |  | 2560000 | Letea Ward |  | Letea Village | Mayandakimonent | [5 empty] | No | Drilling complete. The office is planning to equip the borehole in december 2015
Kipeto Borehole | WIA |  |  | 2206000 | Songot Ward |  | Kipeto | Turkana Quarry Services | [5 empty] | No | Drilling on going
Mogilla Borehole | WIA |  |  | 2240000 | Nanam Ward |  | Nanam Village | Sagal Petrol Station | [5 empty] | No | Drilling complete. The office is planning to equip the borehole in december 2015
Lopur (Komunyaate) Borehole | WIA |  |  | 2250000 | Lopur Ward |  | Komunyaate | Nabek Const And Supplies Ltd | [5 empty] | No | Ongoing, the office has planned to equip the borehole in december
Naporoto Sand Dam | WIA |  |  | 9669516 | Kalobeyei Ward |  | Naporoto | Lomidat Constr Co Ltd | [5 empty] | No | Stalled, the office has served the contractor with a difault notice
Kochomin Rock Catchment | WIA |  |  | 6284300 | Lokichogio Ward |  | Kochomin | Ngilopechek Inv Co Ltd | [5 empty] | No | Stalled, the office has served the contractor with a difault notice
Lomidat Rock Catchment | WIA |  |  | 8114380 | Songot |  | Lomidat | Ekaburu Construction Co Ltd | [5 empty] | No | Stalled, the office has served the contractor with a difault notice
Improvement Of Kalobeyei Water Supply | WIA |  |  | 500000 | Kalobeyei Ward |  | Kalobeyei | To Be Sourced After Evaluation
Construction Of Napeikar Water Supply | WIA |  |  | 7000000 | Songot Ward |  | Napeikar | To Be Sourced After Evaluation
Lokori/Kochodin Water Pan | WIA | 2014/2015 | N02⁰09.194' E035⁰49.535' |  | Lokori/Kochodin |  | Katamanak | Akide |  |  |  | - | 0.7 | Yes | The pan has water 30% its volume. There is evidence of silting from earlier rains. The project is not fenced.
Lokori Aic Borehole | WIA | 2013/2014 | N01⁰56.620' E036⁰01.964' | 2715386 | Lokori/Kochodin |  | Lokori Aic | African B/H Company |  |  |  | 2715386 | 1 | No | Drilling and testing done. Output 12 M³/Hr. Transferred from Katamanak. The project is to benefit Kang'itit Girls Secondary, Polytechnic, Lokori Primary School, Health Centre and part of Town.
Rehabilitation Of Lokori Borehole | WIA |  | N01⁰57.067' E036⁰01.601' |  | Lokori/Kochodin |  | Lokori |  |  |  |  | - | 1 | No | Solar panels and pumps installed, The Bore Hole collapsed, The pannels were taken back for storage
Rehabilitation Of Lokri Main Borehole | WIA |  | N01⁰57.425' E036⁰02.721' |  | Lokori/Kochodin |  | Lokori |  |  |  |  | - | 1 | Yes | Pump and controller supplied. Solar pannels installed. Output is 12 M³/Hr. The borehole serves Lokori town.
Katilia Ward Water Pan | WIA |  | N02⁰18.072' E036⁰07.927' |  | Katilia |  | Lopeduru | Natorube Co Ltd |  |  |  | - | 1 | No | Presipitation low. Need for more inlet channels to feed the water pan. The facility is fenced with barbed wire.
Equiping Of Elelea Borehole | WIA |  | N02⁰06.659' E036⁰09.974' |  | Katilia |  | Elelea |  |  |  |  | - | 1 | Yes | Installation of solar pump and 34 solar pannels done. Output is 15 M³/Hr. Drilling and fencing had earlier been done by World Vision. There is need for another fence. 3 solar pannels were recently stollen.
Lokori/Kochodin Borehole | WIA | 2014/2015 | N01⁰58.104' E036⁰06.105' | 2473905 | Lokori/Kochodin |  | Lokwii | Parakati Con Co Ltd |  |  |  | 2473905 | 0.8 | No | Drilling and testing done. Output 4.5 M³/Hr. Solar pump and solar pannels installed. Four pannels were recently stollen. There is need for fencing and securing the pannels with angle lines & raising them higher.
Lokori Borehole | WIA |  | N01⁰58.411' E036⁰05.209' |  | Lokori/Kochodin |  | Nadoto |  |  |  |  | - | 1 | No | Drilling and testing done. Output 2.2 M³/Hr.
Ngeu Borehole | WIA | 2013/2014 |  | 2859150 | Katilia | [6 empty] | 2859150
Site No. 1 | WIA | 2013/2014 |  | 2359000.35 | Katilia | [6 empty] | 2359000.35
Kamuge Borehole | WIA | 2013/2014 |  | 2549000.4 | Lomelo/Napeitom | [6 empty] | 2549000.4 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Kakitei Borehole | WIA | 2013/2014 |  | 2481700 | Lomelo/Napeitom | [6 empty] | 2481700 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Lomelo/Napeitom Water Pan | WIA | 2014/2015 |  | 9622084 | Lomelo/Napeitom |  |  | Bellaack General Con & Suppliers Ltd |  |  |  | 9622084 | 0.5 | No | The team could not visit the site for security reasons. Information from water department states that the pan stalled at 50% intended volume of work due to breaking down of the doozer. The committee rocommended the team to visit the projects.
Equiping Of AIC Mission Compound Borehole | WIA | 2015/2016 |  | 7-8 Million (Estimates) | Lokori/Kochodin |  | Lokori Aic Mission | In Tender | N/A | N/A | N/A | N/A | 0 | No | Tender advertised and opened. Evaluation and awarding to be done before 2015 Christmas break (Information from the Department of Water).
Flushing And Testing Of Lomelo And Napeitom Boreholes | WIA | 2015/2016 |  | 2500000 | Lomelo/Napeitom |  | Lomelo And Kapedo | Bon Drillers | [5 empty] | No | Samples taken to laboratory. Survey/consultancy work on-going to inform the construction of desalination plants in both Lomelo and Kapedo. Intended beneficiaries are 4,000 (Information from the Department of Water).
Supply Of Water Tanks At Lomelo | WIA | 2015/2016 |  | 624000 | Lomelo/Napeitom |  | Lomelo | Koibos General Contractors | [5 empty] | No | 2No. 10M³ plastic tanks supplied and installed. 500No. 20-Ltrs Jeericans and 500 Kg Chlorine were to be supplied.(Information from the Department of Water).
Drilling Of Boreholes | WIA | 2015/2016 |  | 16-17 Million (Estimates) | Lokori/Kochodin, Lomelo/Napeitom And Katilia |  |  | In Tender | N/A | N/A | N/A | N/A | 0 | No | Tender advertised and opened. Evaluation and awarding to be done before 2015 Christmas break (Information from the Department of Water).
Drilling And Equiping Of Napeitom Borehole. | WIA |  |  | 2465000 | Lomelo/Napeitom |  | Ngatieket | Echami Turkana Company | [6 empty] | Equiping is subject to water quality report which has not been supplied by the contractor. (Information from the Department of Water).
Equiping Of Morulem Secondary Borehole With Solar Pump. | WIA |  |  | 1928000 | Lokori/Kochodin |  | Morulem | Fountain VENT | [6 empty] | Solar pump installed. Piping and construction of the water was to be done and LSO had already been issued. (Information from the Department of Water).
Drilling And Equiping Of Kamuge Borehole | WIA |  |  | 2549000 | Lomelo/Napeitom |  | Kamuge | Silale Investment Co Ltd | N/A | N/A | N/A | N/A | 0 | No | Not yet drilled. Rig failed to reach site because of steep hill. Contractor requested to source capable driller. (Information from the Department of Water).
Drilling And Equiping Of Nadoto Borehole | WIA |  |  | 2473905 | Lokori/Kochodin |  | Nadoto | Parakati Con Co Ltd | [6 empty] | Borehole drilled but dry. Contractor requested to look for an alternative site. (Information from the Department of Water).
| WIA | [13 empty] | (Information from the Department of Water).
Kaeris Borehole | WIA |  | N 03° 58.798' E 035° 28.855 /677M | 2550500 | Kaeris Ward |  | Kaeris | Loitangole Ent Ltd |  |  |  |  | 0.6 | Not yet | Yet to be equipped/installed
Kaikor Borehole | WIA |  | N 04° 30.559' E 035° 25.931 | 2515690 | Kaaleng/Kaikor |  | Kaikor Secondary | Kabarait Ltd |  |  |  |  | 0.6 | No | Already there but not installed water equipment
Lokumai II Borehole | WIA |  | N 04° 26.520' E 035° 35.585' /541 M | 2972130 | Kaaleng/Kaikor |  | Lokumai Ii | [5 empty] | 1 | Yes | Good sate/complete
Liwan Waperpan | WIA |  | N 04° 55.865' E 035° 41.740' /383 M |  | Lapur |  | Liwan | [5 empty] | 0.4 | No | Construction on-going
Nabulkok Borehole | WIA |  | N 04° 31.191' E 035° 41.756' /468 M | 2670150 | Lapur |  | Nabulkok | Nameturan Inve Ltd |  |  |  |  | 1 | Yes | Operational
Lokalale Akwaan Borehole | WIA |  | N 04° 20.812' E 035° 36.648' /586 M | 2450000 | Lapur |  | Kachoda | Nabek Constr Suppl Ltd |  |  |  |  | 1 | Yes | Operational,high yield,good work
Kaloyara Borehole | WIA |  | N 04° 01.645' E 035° 47.064' /454 M | 2203188 | Lakezone |  | Kaloyara/Narengewoi | Narina Inv Co Ltd |  |  |  |  | 1 | Yes | Operational
Kataboi Water Storage Tank | WIA |  | N 03° 44.970' E 035° 47.314' /490 M |  | Lakezone |  | Kataboi | [5 empty] | 1 | Yes | Good condition and fully operational
Naduat Borehole | WIA |  | N 03° 30.677' E 035° 11.207 /669M | 2450500 | Nakalale |  | Naduat | Ekanyarit Constr |  |  |  |  | 0.85 | No | Not completed fully
Nariokotome Borehole | WIA |  | N 04° 08.086' E 035° 54.261 /381M |  | Lakezone |  | Nariokotome | [5 empty] | 1 | No | Not operational,requires repairing
Todonyang Waterpan | WIA |  | N 04° 26.830' E 035° 54.863 / 408M |  | Lakezone |  | Todonyang | [5 empty] | 0.1 | No | Preliminary work only,duplication of the project next to the diocese of lodwar pan
Construction Of Losajait Water Pan | WIA |  |  | 10070482 | Nakalale |  | Losajait | Ekanyarit Atoo Entr. | [6 empty] | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
Construction Of Kanakurudio Water Pan | WIA |  |  | 8406930 | Kaeris Ward |  | Kanakurudio | Miembo Con Suppliers Ltd. | [6 empty] | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
Kalochanapus Water Pan | WIA |  |  | 9504360 | Kaaleng/Kaikor |  | Kalochanapus | Ledo Con & Suppliers | [6 empty] | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
Equiping Of Naduat Borehole With A Handpump | WIA |  | N 03° 30.677' E 035° 11.207 /669M | 336000 | Nakalale |  | Naduat | The Installation Was Done By The Ministry | [5 empty] | No | Equiped awaiting commissioning
Flushing Of 2 No.Boreholes And Test Pumping Kariobok Borehole | WIA |  |  | 450000 | Nakalale | [8 empty] | No | Under procurement process
Equiping Of Locherengan Borehole With Submersible | WIA |  |  | 280000 | Lapur | [8 empty] | No | Under procurement process
Iprovement Of Kataboi Water Supply | WIA |  |  | 2000000 | Lakezone |  | Kataboi | To Be Sourced Through Raising Quotations | [5 empty] | No | Under procurement process
Improvement Of Lokitaung Water Supply | WIA |  |  | 7000000 (Estimate) | Lapur |  | Lokitaung | [6 empty] | No | Under procurement process
Improvement Of Kibish Water Supply | WIA |  |  | 7000000 (Estimate) | Kibish Ward |  | Kibish | [6 empty] | No | Under procurement process
Improvement Of Nachukui Water Supply | WIA |  |  | 5000000 (Estimate) | Nachukui | [8 empty] | No | Under procurement process
Improvement Of Loarengak Water Supply | WIA |  |  | 5000000 (Estimate) | Loarengak |  | Loarengak | [6 empty] | No | Under procurement process
Kaaleng Waterpan | WIA |  |  |  | Kaaleng/Kaikor |  | Natudao | [6 empty] | No | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
nanam dispensary | Health and Sanitation | 2014/2015 | N04⁰12.623' E034⁰33.779' ELV 550m | 7396473 | Nanam Ward |  | Nanam Centre | Brinkley Logistics |  |  |  | 7396473 | 0.99 | No | Yet to install window panes
Nanam matternity ward | Health and Sanitation | 2013/2014 | N04⁰12.611' E034⁰33.800' ELV 556m | 9800000 | Nanam Ward |  | Nanam Centre |  |  |  |  | 9800000 | 1 | Yes | The project is complete and in use
AIC lopiding subcounty hospital renovation | Health and Sanitation | 2013/2014 | N04⁰12.109' E034⁰23.028' ELV 632m | 9901504 | Nanam Ward |  | Lopiding | Wamwa Trading Co LTD |  |  |  | 9901504 | 1 | Yes | Painting, door replacements tiling the flours, ceilings repairs, piping and roof repairs, this repair were done on OPD theatre, one ward and office
Loteteleit Dispensary | Health and Sanitation | 2014/2015 | N04⁰12.321' E034⁰20.852' ELV 651m | 7500000 | Lokichogio Ward |  | Lokichogio AIC Compound | Ekanyarit Atoo enterprise |  |  | 3000000 | 4500000 | 0.7 | No | The project is incomplete, not painted, the flour is cracking, no window panes and has been built on private property, the relevant department to come up with a clear managenent and operation plan
Teremkus Dispensary | Health and Sanitation | 2014/2015 | N04⁰06.272' E034⁰28.044' ELV 613m | 7130033 | Songot Ward |  | Teremkus | Turkana Quarry services LTD |  |  | 4991023.14 | 2139009.86 | 0.9 | No | No toilet, yet to put ceiling board, painting. The project is stalled, no contractor on site
Aposta Dispensary | Health and Sanitation | 2014/2015 | N04⁰09.369' E034⁰25.408' ELV 620m | 7452999 | Songot Ward |  | Aposta Village | Super Mogilla inv co LTD |  |  | 7452999 | - | 0.95 | No | Contracter on site, yet to do wiring and then install window panes, there is another similar facility built by a development partner within the vicinity.
Nakururum OPD block | Health and Sanitation | 2013/2014 | N03⁰59.711' E034⁰32.708' ELV 641m | 9800000 | Songot Ward |  | Nakururum |  |  |  | 9800000 | - | 1 | Yes | The project is complete and in use. Commissioned in sep 2015. No signange
Nalapatui Dispensary | Health and Sanitation | 2014/2015 | N03⁰48.738' E034⁰35.848' ELV 784m | 7459515 | Kalobeyei Ward |  | Nalapatui | Epolot ere construction co LTD |  |  | 7459515 | - | 1 | No | The contractor to repaint, there is need for provision of plumbing and solar power. The project is ready for commissioning. No signange
Lonyuduk Dispensary | Health and Sanitation | 2014/2015 | N03⁰42.548' E034⁰36.324' ELV 676m | 7456515 | Kalobeiyei |  | Lonyuduk | Turkana west Technical |  |  | 5215360.5 | 2241154.5 | 1 | No | Yet to do wiring, and repainting. Ready for commissioning. No signage
Komudei dispensary | Health and Sanitation | 2014/2015 | N03⁰43.565' E034⁰52.913' ELV 609m | 7575200 | Kakuma Ward |  | Komudei Village | Pelekech LTD |  |  | 6060160 | 1515040 | 1 | No | The project is complete, no signage. Yet to be commissioned.
Nasinyono Dispensary | Health and Sanitation | 2014/2015 | N04⁰17.793' E034⁰57.450' ELV 495m | 7950000 | Songot Ward |  | Nasinyono | EMV Holdings LTD |  |  | 5565000 | 2385000 | 0.5 | No | The project is stalled, the contractor is not on site, the community is complaining that the workers who were working on site havent been paid, project manager to issue a default notice
Lokangae Dispensary | Health and Sanitation | 2013/2014 | N04⁰06.682' E034⁰53.363' ELV 519m | 2900000 | Songot Ward |  | Lokangae | Katamanak gen constr co ltd |  |  |  | 2900000 | 0.8 | No | The contractor has done more work than originally agreed in the BQ, willing to complete and claim the actual cost. The project manager to guide on way forward.
Atiir OPD block | Health and Sanitation | 2013/2014 | N04⁰03.682' E034⁰52.769' ELV 530m | 6900000 | Songot Ward |  | Lokangae |  |  |  |  | 6900000 | 1 | No | The ministry to replace collapsing ceiling, repaint and commission.
Namon Dispensary | Health and Sanitation | 2013/2014 | N04⁰00.253' E034⁰52.769' ELV 530m | 4900000 | Lopur Ward |  | Namon |  |  |  |  | 4900000 | 0.99 | No | No waiting bench for the patients, the client ministry to organize for commissioning.
Lopusike Dispensary | Health and Sanitation | 2013/2014 | N03⁰51.496' E034⁰49.272' ELV 567m | 4900000 | Lopur Ward |  | Lopur Village | Naita construction company |  |  |  | 4900000 | 1 | No | Notable cracks on the floor, walls and collapsing ceiling.The project manager to instruct the contractor to rectify
Kangitesroi Dispensary | Health and Sanitation | 2014/2015 | N03⁰52.639' E034⁰56.859' ELV 573m | 7439201 | Lopur Ward |  | Kangitesroi | Urum construction and engineering co ltd |  |  | 5207440.7 | 2231760.3 | 0.5 | NO | Site abandoned, all material to completion are on site, the project manager to ensure the contractor finishes to project.
Nakoyo Dispensary | Health and Sanitation | 2014/2015 | N03⁰42.687' E034⁰47.411' ELV 614m | 7871999 | Lopur Ward |  | Nakoyo | Napek construction and supp ltd |  |  | 5510399.3 | 2361599.7 | 0.8 | No | Contractor on site, project at the finishes level.
Pokotom Heath Centre | Health and Sanitation | 2013/2014 | N03⁰36.786' E034⁰49.315' ELV 627m | 9800000 | Kakuma Ward |  | Pokotom Village | Rasabana Enterprise LTD |  |  | 9800000 | - | 1 | No | Project complete, to be taken over by client, contractor in default in another contract with TCG and therefore his retention be withheld untill he makes good the default.
Loreng Dispensary | Health and Sanitation | 2014/2015 |  | 7322532 | Letea Ward |  | Loreng | Nakwama gen contractors |  |  | 5125722 | 2196810 | 0.8 |  | Team unable to reach site due to security concerns. Dispensary complete, staff house at roofing level, the contractor on site as informed by the ward admin
Kaameyan Dispensary | Health and Sanitation | 2014/2015 |  | 7500000 | Letea Ward |  | Kaameyan | Ng'ilopechek Invest LTD |  |  | 7500000 | - | 0.8 | No | The contractor is onsite, doing plumbing and ceiling. Project ready for commissioning.
Letea OPD Block | Health and Sanitation | 2013/2014 | N03⁰31.068' E034⁰49.010' ELV 660m | 9800000 | Letea Ward |  | Letea Village | Ekisil construction company limited |  |  | 9800000 | - | 1 | Yes | The project is in use
Construction of Lopeduru Dispensary | Health and Sanitation | 2013/2014 | N01⁰57.106' E036⁰01.530' | 6900000 | Katilia |  | Lopeduru | Achuma Contractors Ltd | 43996 | 43966 | 6900000 | 0 | 1 | Yes | Construction complete and serves an average of 25 patients per day. The medical staff include 2 nurses and 1 volunteer. There is need for equiping the facility with requisite equipments, running water and a fence. Notable defects; veranndar steel pillars are not holding the roof, poor ventilation in the maternity. Client to correct the defects.
Construction of staff quarters at Elelea Sub County Hospital | Health and Sanitation | 2014/2015 | N02⁰06.887' E036⁰09.171' | 10575000 | Katilia |  | Elelea | Ibus Turkan |  |  | 7402500 | 3172500 | 0.9 | No | 4 units staff houses complete with 2 units of latrines. Piping for water connection on going. There is need for fencing the facility. There is also a pressing need for more staff houses to accommodate the 12 staff members serving the facility.
Lotubae Dispensary | Health and Sanitation | 2014/2015 | N02⁰01.514' E036⁰07.541' | 7396473 | Lokori/Kochodin |  | Lotubae | Logistics Team Int Ltd |  |  | 5177531.1 | 2218941.9 | 0.8 | No | Part roofing for the dispensary done. Roofing for staff house complete. Steel windows and doors fitted. Escavation of the latrine done. The contractor was not on site. Project manager to follow up
Construction of Lokwii Dispensary | Health and Sanitation | 2013/2014 | N01⁰58.637' E036⁰06.327' | 9800000 | Lokori/Kochodin |  | Lokwii | Kodekode Contractors | 43996 | 43966 | 9800000 | 0 | 1 | Yes | The project is complete and commissioned. Maternity, Antenatal and Postnatal wings are in use. The facility is powered with solar energy and serves an average of 5-50 patients per day. The staff members comprise of 1 In Charge, 1 Clinical Officer, 2 Nurses and 1 CHEW.
Elelea Sub County Hospital | Health and Sanitation | 2013/2014 | N02⁰06.903' E036⁰09.111' | 2900000 | Katilia |  | Elelea |  | 43996 | 43966 | 2900000 | 0 | 1 | Yes | Completion works to the ESP modle Health centre. The hospital attends to an average of 30 patients per day. Staff members comprises of 3 Nurses, 2 Clinical Officers, 1 Medical Officers, 1 CHEW, 1 Volunteer and 2 Personal Assistants. By the time of the visit, the outreach programme had stopped for a month and the effect had already been felt.
Lomelo Dispensary | Health and Sanitation | 2013/2014 |  | 9800000 | Lomelo/Napeitom |  |  |  | 43996 | 43966 |  | 9800000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the project.
Napeitom Dispensary | Health and Sanitation | 2014/2015 |  | 7400902 | Lomelo/Napeitom | [6 empty] | 7400902 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the project.
Nakatongwa Dispensary | Health and Sanitation |  |  | 7650600 |  |  |  | Joeli Contractors |  |  |  | 7650600 |  |  | The team could not trace exact location of the dispensary.
Kikeunae Dispensary | Health and Sanitation |  |  | 7411320 |  |  |  | Ngapenderee |  |  |  | 7411320
Lomunyan Akwaan Dispensary | Health and Sanitation | [10 empty] | -
Naduat dispensary | Health and Sanitation | 2014/2015 | N 03° 30.855' E 035° 11.065' | 6900000 | Nakalale |  | Naduat | Kuchilchil contractors | 43996 | 43966 | 6900000 | - | 1 | no | The project is complete ready for commissioning
Losajait dispensary | Health and Sanitation | 2013/2014 | N 03° 37.153' E 035° 18.850' /637M | 2900000 | Nakalale |  | Losajait | Mugasi building & contractors |  |  | 2900000 | - | 1 | no | The project is complete ready for commissioning,there is need for pit latrine and staff house
Kaeris dispensary | Health and Sanitation | 2014/2015 | N 03° 58.798' E 035° 28.855 /677M | 7131600 | Kaeris |  | Kaeris | Almaso ent & const ltd | 43996 | 43966 | 7131600 | - | 1 | no | The project is complete,contractor to make good defects
Ekicheles dispensary | Health and Sanitation | 2014/2015 | N 04° 28.664' E 035° 26.960' /634M | 7575200 | Kaaleng/Kaikor |  | Ekichelees | lakika ntwork contrution & general suppliers | 43996 | 43966 | 6060160 | - | 0.8 | no | Construction on-going,workers on site,most of the materials on site
Kaaleng dispensary | Health and Sanitation | 2013/2014 | N 04° 22.478' E 035° 32.963' /607M | 9800000 | Kaaleng/Kaikor |  | Kaaleng | Kabarait builders & contractors |  |  | 9800000 | - | 1 | yes | The project was commissioned and use
Nakapelewoi dispensary | Health and Sanitation |  | N 04° 19.062' E 035° 26.001' /623M | 7459816 | Kaaleng/Kaikor |  | Nakapelewoi | Erex contractors | 43996 |  | 7459816 | - | 1 | no | Project is complete ready for commissioning
Karebur dispensary | Health and Sanitation | 2014/2015 | N 04° 26.133' E 035° 43.361' /536M | 7067290 | Lapur |  | Karebur | Jonice co ltd | 43996 | 43966 | 6360561 | - | 0.9 | no | The contractor to enhance ventillation and lighting on corridors,project manager to follow
Kokuro dispensary | Health and Sanitation | 2013/2014 |  | 9800000 | Lapur |  | Kokuro | moru koki & sons contractors |  |  | 7241268 | - | 1 | yes | The project is complete and in use
Napeikar dispensary | Health and Sanitation | 2014/2015 | N 04° 44.946' E 035° 39.781' /461M | 7591211 | Lapur |  | Meyan | morutena contractors | 43996 | 43966 | 5313847.7 | - | 0.7 | no | Noted some low quality blocks,project manger to act,contractor experiencing hostility from local community
Lokitaung sub county hospital pharmacy store and kitchen | Health and Sanitation |  | N 04° 15.746' E 035° 45.261' /745M | 11957674 | Lapur |  | Lokitaung | tilak hardware and tools | 43996 | 43966 | 8370371.8 | - | 1 | no | The project is complete waiting for commissioning
Riokomor dispensary | Health and Sanitation | 2014/2015 | N 04° 06.967' E 035° 43.228' /559 M | 7500049.6 | Lapur |  | Riokomor | rikomor inv ltd | 43996 | 43966 | 6750044.1 | - | 0.9 | no | No windows panes,toilet yet to be completed
Narengewoi health center | Health and Sanitation | 2013/2014 | N 04° 00.475' E 035° 51.067' /388 M | 9800000 | Lakezone |  | Narengewoi | nacet & sons contractors |  |  | 9800000 | - | 1 | yes | The project is in use though not fully equiped,client to work on remeding the defects
Lolupe dispensary | Health and Sanitation | 2014/2015 | N 03° 32.228' E 035° 14.392' /715 M | 7276271 | Nakalale |  | Lolupe | be-lochakai | 43996 | 43966 | 5093389.7 | - | 0.8 | no | The contractor on site,work progressing well
Nakitoe-kakumon dispensary | Health and Sanitation | 2014/2015 | N 04° 12.228' E 035° 21.614' | 7485526 | Kaeris |  | Nakitoe-Kakumon | Turkana hardware & constrution co. | 43996 | 43966 | 7485526 | - |  |  | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
Lopur Dispensary | Health and Sanitation | 2014/2015 |  | 7506256 | Lakezone |  | Lapur | Lakezone investment limited | 43996 | 43966 | 7506256 | - | 1 | no | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
turkana west market renovation | Tourism,Trade and Industrialization |  | N03⁰42.456' E034⁰51.734' | 1823878 |  | Kakuma |  | Kakuma Town | Rasabana Entr Ltd |  |  | 1823878 | 0 | 1 | yes | Project complete. Renovation works included painting, floor and roof repairs. Recommended for major renovations.
Lokori Market Stalls | Tourism,Trade and Industrialization |  | N01⁰57.051' E035⁰01.830' | 10453259 |  | Lokori/Kochodin |  | Lokori Town | Lelar Inv Ltd |  |  | 10453259 | 0 | 1 | No | Project complete. Recommended for water connection, fencing, gate, toilet and a rubbish pit. Need for a revenue collection and revenue enforcement offices.
loarengak market stalls | Tourism,Trade and Industrialization | 2014/2015 | N 04° 16.795' E 035° 53.531' /380 M | 9889063.8 |  | Lakezone |  | Loarengak | Lapur Trading & Inv Co Ltd |  |  | 9889063.8 | 0 | 1 | no | Main structure complete.recommended for fencing,gate and a rubbish pit.need for revenue collection officers and revenue enforcement officers.water connection.guard rail
kataboi co Lodge | Tourism,Trade and Industrialization |  | N 03° 40.635' E 035° 49.941' /383 M | 66389746 |  | Lakezone |  | Lokitoeangaber | Kacheilap Gen.Contractors | 41957 | 42231 | 59750771.4 | 6638974.6 | 0.85 | no | Accomodation blocks near completion.dinning/ conference at roofing.fencing complete.contractor claim for variation for extra work
Nanam ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N04⁰12.661'E034⁰33.644' EL 539m | 6000000 | Nanam Ward |  | Nanam Village | Jelaan Building And Construction & Supp | 43966 | 43877 | 5100000 | 900000 | 0.85 | No | Finishing works ongoing, no signage.
St Cosmas Napopongoit ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N04⁰11.690'E034⁰23.931' EL 624m | 5412633.9 | Nanam Ward |  | Napopongoit Village | Lopiding Gen Construction Ltd |  |  |  | 5412633.9 | 0.5 | No | Project not complete, site abandoned. The project manager was not involved in this project. Client to liaise with office of the project manager for direction.
AIC Lopiding ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N04⁰12.180'E034⁰23.515' EL 634m | 6000000 | Nanam Ward |  | Lopiding Village | Ato Gen Contractors | 43966 | 43877 | 6000000 | - | 1 | No | The project is complete. Ready to be commissioned
St Mathews Nadome ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N04⁰11.814'E034⁰23.351' EL 628m | 3500000 | Nanam Ward |  | Lopiding Village | Logistics Team International | 43966 | 43877 |  | 3500000 | 0.8 | No | Costructions works ongoing
AIC Lokichoggio ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N04⁰12.435'E034⁰20.713' EL 645m | 7500000 | Lokichogio Ward |  | Lokichoggio Centre | Mt Pelekech Contractors |  |  |  | 7500000 | 1 | Yes | Origal contract 100% complete, additional works was at 95% complete.
Teremkus ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N04⁰06.344'E034⁰27.885' EL 627m | 5850000 | Songot |  | Teremkus | Nawik Contractors | 43966 | 43877 | 3510000 | 2340000 | 1 | No | Project is complete. Ready for commisioning.
Naremeto ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N04⁰05.545'E034⁰32.932' EL 564m | 4320140.8 | Songot Ward |  | Naremeto | Aropa Investment Ltd |  |  | 4320140.8 | - | 1 | Yes | Project complete, ready for commissioning. Additional works recommended.
Lokudule ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N04⁰00.839' E034⁰33.179' ELV 609m | 5948132 | Songot Ward |  | Lokudule | Lizton Ltd | 43966 | 43877 | 5948132 | - | 1 | Yes | Project complete, ready for commissioning.
Nakururum ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N03⁰59.684' E034⁰32.631' ELV 644m | 5484100 | Songot Ward |  | Nakururum | Tode Contractors Ltd | 43966 | 43877 |  | 5484100 | 1 | No | Project complete except for the fence, ready to be commissioned.
Natiira ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N03⁰53.200' E034⁰33.078' ELV 678m | 6000000 | Kalobeyei Ward |  | Natiira | Lomidat Construction Co Ltd | 43966 | 43877 | 3600000 | 2400000 | 0.7 | No | Contractor on site, works progressing well.
Oropoi ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N03⁰48.817' E034⁰21.737' ELV 864m | 6000000 | Kalobeyei Ward |  | Oropoi | Eitanit Water Drilling And Construction Co Ltd | 43966 | 43877 | 3600000 | 2400000 | 0.5 | No | Site abandoned, project manager to follow up.
Nawotom ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N03⁰48.734' E034⁰35.850' ELV 675m | 3500000 | Kalobeyei Ward |  | Nawotom | Lotikipi Investment Ltd |  |  |  | 3500000 | 1 | Yes | Project complete ready for commissioning, additional works recommended.
Kalobeyei ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N03⁰46.383' E034⁰37.554' ELV 653m | 4320000 | Kalobeyei Ward |  | Kalobeyei | Aropa Investment Ltd |  |  |  | 4320000 | 1 | Yes | Project complete ready for commissioning, additional works recommended.
Komudei ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N03⁰43.082' E034⁰52.344' ELV 608m | 6000000 | Kakuma Ward |  | Kakuma- Komudei Village | Laika Construction | 43966 | 43877 | 5400000 | 600000 | 0.98 | No | Project is complete excepy for fence, window panes.
Nabune ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 |  |  | Kakuma Ward |  | Nabune |  |  |  |  | - | 1 | Yes | The project is complete and in use
NAMON ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N04⁰00.166' E034⁰52.507' ELV 540m | 6000000 | Songot Ward |  | Namon | Natamakarwo Eng Ltd | 43966 | 43877 | 3600000 | 2400000 | 0.9 | No | Finishing works ongoing
LOPUR ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N04⁰51.568' E034⁰49.101' ELV 570m | 6000000 | Lopur Ward |  | Lopur Centre | Behive Logistics Co Ltd | 43966 | 43877 | 5400000 | 600000 | 1 | No | Project complete except for the pit latrine finishes and classroom verandah. External paving to be redone,
KANGITESROI ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N03⁰53.055' E034⁰56.918' ELV 571m | 3500000 | Lopur Ward |  | Kangitesroi |  |  |  | 3500000 | - | 1 | Yes | The project is complete and ready for commissioning additional works recommended.
LOMUNYANAKIRIONOK/ NGIJAWOI ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N03⁰48.577' E034⁰53.451' ELV 592m | 3500000 | Lopur Ward |  | Ngijawoi | Kaisaki Building Contractors |  |  | 3500000 | - | 1 | Yes | The project is complete and ready for commissioning additional works recommended.
LOTAKA ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N03⁰48.577' E034⁰53.451' ELV 592m | 6000000 | Kakuma Ward |  | Lotaka Village | Bluepower Construction Co Ltd | 43966 | 43877 | 4200000 | 1800000 | 0.9 | No | Finishes to the latrine outstanding, to put window panes and fence, the project manager to follow up.
LORENG ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 |  |  | Letea |  | Loreng Village |  |  |  |  | - |  | No | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
LOKIPOTO ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 |  | 5951612 | Letea |  | Lokipoto | Choroi Inv Ltd | 43966 | 43877 | 1785483.6 | 4166128.4 | 0 | No | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
TULABALANY ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 |  | 3500000 | Letea |  | Tulabalany | Kakuma Building Entreprises |  |  |  | 3500000 | 1 | Yes | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
Akoros Loritit ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 |  |  | Letea |  | Akoros | Kakuma Building Entreprises |  |  |  | - | 1 | Yes | The team could not visit the site because of the rains and time constraint, the team to revisit the site.
Musug ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 |  | 6000000 | Letea Ward |  |  | Kakuma Building Entreprises | 43966 | 43877 | 3600000 | 2400000
| EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE |  | N02⁰05.814' E035⁰35.518' | 3500000 | Lokori/Kochodin |  | Lokicheda | Etich Bon Co Ltd | 43844 | 43935 | 3500000 | 0 | 0.9 | Yes | Classroom, Dining Hall and Kitchen complete. Need for supply of furniture. Floor needs rescreeding. Latrines 40% complete (Walling on going). Need for water connection to the ECD (Water tank within the school compound). Client to follow up with the project manager.
Construction of Lokwamosing ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N01⁰59.544' E035⁰56.215' | 6000000 | Lokori/Kochodin |  | Lokwamosing | Ummatul Rahma Const | 43966 | 43877 | 6000000 | 0 | 1 | Yes | Construction of main structures complete. One more coat of paint needed. Fencing done. Project not yet handed over. The ECD is within a school compound and there is need for a urinal & more latrines for girls.
Construction of Lopeduru ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N02⁰14.520' E036⁰07.586' | 6000000 | Katilia |  | Lopeduru | Lochar Emayan Contractors | 43966 | 43877 | 3600000 | 2400000 | 1 | Yes | Classroom, Dining Hall, Kitchen and Toilets done. The facility also has a gated fence. There need of clearing the site after construction to minimise injuries on pupils. The sinks for hand washing at the latrines well done. There is need for applying red oxide and ramping the strucutres to allow accessibility for all. It is located close to Lopeduru primary school. The contractor should clear the project site.
Construction of Lokorkor ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N02⁰14.519' E036⁰07.582' | 6000000 | Katilia |  | Lokorkor | Kachilap Co Ltd | 43966 | 43877 | 6000000 | 0 | 1 | Yes | Classroom, Dining Hall, Kitchen and Toilets done. Need for running water in the facility. The classroom windows do not meet the safety standards. Need for ventilation louvres.
Construction of Katilia ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N02⁰11.246' E036⁰07.324' | 3500000 | Katilia |  | Katilia |  | 43844 | 43935 | 3500000 | 0 | 1 | Yes | Classroom, Dining Hall, Kitchen and Toilets done. There is evidence of poor workmanship (paint falling off and floor scrapped). The Dinning Hall is not child friendly. There is need for repairs. Class in use but the Dinning is not functional (used as a dormitory for Katilia primary school). The facility is recomended for additional works.
Construction of Elelea ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N02⁰06.427' E036⁰09.795' | 3500000 | Katilia |  | Elelea | Katilu Builders & Construction | 43844 | 43935 |  | 3500000 | 1 | Yes | Classroom, Dining Hall, Kitchen and Toilets done. The Dinning Hall floor is pealling off. There is need for equiping the facility with furniture. The classroom needs ceilling. The facility is also not fenced and there is no running water within. The client to forward the project to project manager for follow up.
Construction of Morulem ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N02⁰01.143' E036⁰04.994' | 6000000 | Lokori/Kochodin |  | Nakwasinyen | Etau Build & Const Ltd | 43966 | 43877 | 6000000 | 0 | 1 | Yes | Project is complete and ready for commisioning. Poor accessibilty to the facility.
Construction of Nayanae Katon ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N02⁰03.013' E036⁰07.829' | 3500000 | Katilia |  | Nayanae Katwan | Etich Bon Co Ltd | 43844 | 43935 |  | 3500000 | 1 | Yes | Project is complete and ready for commisioning.
Construction of Napeitom ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 |  | 3500000 | Kapedo/Napeitom |  |  |  | 43844 | 43935 |  | 3500000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Construction of Kapedo ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 |  | 3500000 | Kapedo/Napeitom |  | Kapedo | Silale Investment Ltd | 43844 | 43935 |  | 3500000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Construction of Lokidongoi ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 |  | 6000000 | Kapedo/Napeitom |  |  |  | 43966 | 43877 |  | 6000000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Construction of Silale ECD | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 |  | 6000000 | Kapedo/Napeitom |  |  |  | 43966 | 43877 |  | 6000000 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Construction of new ECD at Naduat | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N 03° 30.751' E 035° 11.954' | 6000000 | Nakalale |  | Naduat | Kuchulkuchil Build Const Co Ltd | 43966 | 43877 | 6000000 | - | 1 | No | Project complete awaiting commssioning,client ensure signage
Lokore ecd | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N 03° 30.905' E 035° 13.350' | 3500000 | Nakalale |  | Lokore | Kuchikuchil Contgractors |  |  | 3500000 | - | 1 | Yes | Project is complete,minor defects to be addresed by the client
Construction of new ECD at Losajait | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N 03° 37.278' E 035° 18.645' /637 M | 6000000 | Nakalale |  | Losajait | Napalakipor Inv Ltd | 43966 | 43877 | 6000000 | - | 1 | No | Project complete,inadequate fence chain link
Construction of new ECD at Ngaurenderia | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N 03° 56.764' E 035° 15.307' /569 M | 6000000 | Kaeris |  | Nadunga | Musuk Company | 43966 | 43877 | 6000000 | - | 1 | Yes | Project complete ready for commissioning
Construction of ECD at Kangakipur | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE |  | N 04° 01.951' E 035° 29.254' /696 M | 3500000 | Kaeris |  | Kanagkipur | Loitangole Investment |  |  | 3500000 | - | 1 | Yes | Project is complete,minor defects to be addresed by the client
Mlima tatu ecd | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N 04° 08.584' E 035° 28.136' /678 M | 3500000 | Kaeris |  | Mlima Tatu |  |  |  | 3500000 | - | 1 | Yes | Project complete and recomended for additional work
Nakapelewoi | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N 04° 19.062' E 035° 26.075' /632 M | 3500000 | Kaaleng/Kaikor |  | Nakapelewoi | Loitangole Investment |  |  | 3500000 | - | 1 | No | Client to address the defects on the windows and doors
Kaarubangorok ecd | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE |  | N 04° 26.868' E 035° 21.514' /572 M | 6000000 | Kaaleng/Kaikor |  | Loruth | Abdifatah & Siblings Company | 43966 | 43877 | 5400000 | 600000 | 0.85 |  | The classroom is not done to the standard design,pit latrine not complete,roofing for the dining hall is not complete,contractor has made a claim of variation on the basis of location,the project manager to address all this issue and report to commitee
Longelemwar ecd | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE |  | N 04° 31.750' E 035° 28.456' /625 M | 3500000 | Kaaleng/Kaikor |  | Longelemwar | Abdifatah & Siblings Company |  |  | 3500000 | - |  | Yes | Project is complete,client ministry to take care of the defects
Lokidongo ecd | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N 04° 25.956' E 035° 32.013' /592 M | 6000000 | Kaaleng/Kaikor |  | Lokidongo | Ledo Contractors & Suppliers Ltd | 43966 | 43877 | 4200000 | 1800000 | 0.7 | No | Projects on-going,most of the materrials on site
Lochwarengan ecd | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N 04° 23.406' E 035° 43.618' /609 M | 5330550 | Lapur |  | Loarengak | Nawonyei Gen.Constr And Supp Co Ltd | 43966 | 43877 | 3731385 | 1599165 | 0.6 | No | Project is on-going,most materials on site
Liwan ecd | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/15 | N 04° 53.971' E 035° 40.277' /407 M | 6000000 | Lapur |  | Liwan | Kopure Ent.Ltd | 43966 | 43877 | 5400000 | 600000 | 0.9 | Yes | Project complete except fencing and gate
Nabulkok ecd | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE |  | N 04° 31.007' E 035° 41.942' /476 M | 3500000 | Lapur |  | Nabulkok | Nameturan Investment Ltd |  |  | 3500000 | - | 1 | Yes | Project complete,additional work recomended,commissioning not done
Lochoredome ecd | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N 04° 15.893' E 035° 40.648' /588 M | 3500000 | Lapur |  | Kachoda | Lapur Construction Co.Ltd |  |  | 3500000 | - | 1 | Yes | Project complete,additional work recomended,commissioning not done
namorotot ecd | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N 04° 11.025' E 035° 54.098' /306M | 3500000 | Lakezone |  | Nadoupuwa | Hakika Foundation |  |  |  | 3500000 | 0.6 | No | Project is abandoned. Notable poor workmanship with collapsing walls.client to follow up with the project manager urgently (was not involved in the initial management of the project)
Nabeletakoit ecd | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N 04° 18.203' E 035° 53.518' /387 M | 6000000 | Lakezone |  | Loarengak | Napeget Co Ltd | 43966 | 43877 | 6000000 | - | 0.9 | Yes | Work complete save for fencing.project ready for commissioning
Kalosep ecd | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N 03° 49.093' E 035° 48.170' /419 M | 6000000 | Lakezone |  | Kalosep | Nasechabuin Co Ltd | 43966 | 43877 | 5400000 | 600000 | 0.9 | No | Pit latrine,gate,painting and dinning windows outstanding
Lokitoe angabeur ecd | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2013/2014 | N 03° 46.587' E 035° 49.550' /388 M | 3500000 | Lakezone |  | Lokitoe Angaber | Kerman Company |  |  | 3500000 | - | 0.8 | No | Project abandoned at finishes stage.client to liase with project manager
kaaleng polytechnic | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N 04° 22.036' E 035° 32.562' /613 M | 9885844.8 | Kaaleng/Kaikor |  | Kaaleng | Kafia Company Limited |  |  | 8897260.3 | 988584.5 | 0.9 | No | Project complete safe for fencing and solar installation
kataboi youth polytechnic | EDUCATION, SOCIAL SERVICES, SPORTS AND CULTURE | 2014/2015 | N 03° 45.117' E 035° 48.541' /409 M | 9771782 | Lakezone |  | Kataboi | Katiko Investments |  |  | 5863069.2 | 3908712.8 | 0.8 | No | Project is on-going.workers on site.project manager to check on pit latrine and mortar jointings
Nanam ward admin office | PUBLIC SERVICE, DECENTRALISED ADMINISTRATION AND DISASTER MANAGEMENT | 2013/2014 | N04⁰12.988' E034⁰33.691' EL 576m | 9564620 | Nanam Ward |  | Nanam Centre |  |  |  | 9564620 | - | 1 | Yes | Client to ensure signage and maintain the facility, the project is complete and commissioned.
Lokichogio ward admin office | PUBLIC SERVICE, DECENTRALISED ADMINISTRATION AND DISASTER MANAGEMENT | 2014/2015 | N04⁰11.333' E034⁰21.936' EL 640m | 13352191 | Lokichogio Ward |  | Lokichogio | Lojaam Luqa Energy |  |  | 12016971.9 | 1335219.1 | 0.8 | No | Project still ongoing, contractor on site, good work going, all materials were on site
Songot Ward Admin Office | PUBLIC SERVICE, DECENTRALISED ADMINISTRATION AND DISASTER MANAGEMENT | 2014/2015 | N04⁰03.088' E034⁰31.665' EL 613m | 12544947 | Songot Ward |  | Aposta | Tiwae Inv LTD |  |  | 8781463.32 | 3763483.68 | 0.7 | No | Electrical works not done, the contractor is on site
Kalobeyei Ward Admin Office | PUBLIC SERVICE, DECENTRALISED ADMINISTRATION AND DISASTER MANAGEMENT | 2013/2014 | N03⁰45.657' E034⁰37.945' EL 663m | 12488900 | Kalobeyei Ward |  | Kalobeyei Centre | Akanpich Building Co Ltd |  |  | 8742229.8 | 3746670.2 | 0.7 | No | The project is stalled. Finishes,openings and external works remaining. The directors of the contracted co are in a court dispute. The project manager to follow up, including issuance of default notice.
Kakuma Ward Admin Office | PUBLIC SERVICE, DECENTRALISED ADMINISTRATION AND DISASTER MANAGEMENT | 2013/2014 | N03⁰42.610' E034⁰52.032' EL 607m | 11585001 | Kakuma Ward |  | Kakuma Town | Rasabana Ent Ltd |  |  | 8109792 | 3475209 | 0.6 | No | The project is stalled. Finishes,openings and external works remaining. The project manager to follow up, including issuance of default notice.
Lopur Ward admin | PUBLIC SERVICE, DECENTRALISED ADMINISTRATION AND DISASTER MANAGEMENT | 2013/2014 | N03⁰51.453' E034⁰49.639' EL 566m | 11425340 | Lopur Ward |  | Lopur | Ekisil Co Ltd |  |  | 11425340 | - | 1 | No | Project complete, awaitng commisioning.
Letea Ward Admin Office | PUBLIC SERVICE, DECENTRALISED ADMINISTRATION AND DISASTER MANAGEMENT | 2013/2014 | N03⁰31.304' E034⁰48.526' EL 650m | 9691164 | Letea Ward |  | Letea |  |  |  | 9691164 | - | 1 | Yes | Project complete
Lokori Ward Administrator's Office | PUBLIC SERVICE, DECENTRALISED ADMINISTRATION AND DISASTER MANAGEMENT | 2014/2015 | N01⁰57.106' E036⁰01.530' |  | Lokori/Kochodin |  | Lokori Town | [5 empty] | 0.75 | No | Main works with undercoat paint done. Fencing and drainage also done. Placing of floor tiles on going.
Katilia Ward Administrator's Office | PUBLIC SERVICE, DECENTRALISED ADMINISTRATION AND DISASTER MANAGEMENT |  | N02⁰07.428' E036⁰07.459' |  | Katilia |  | Katilia Town | Touchlife Co Ltd |  |  |  |  | 1 | No | Construction complete. Furniture supplied. The office is ready for use. There is need for clearing of site.
Nakalale ward admin office 2014/2015 | PUBLIC SERVICE, DECENTRALISED ADMINISTRATION AND DISASTER MANAGEMENT | 2014/2015 | N 03° 30.898' E 035° 13.529' | 12228947 | Nakalale |  | Makutano Gold Junction | Fithergur Gen Mer Ltd | 43966 | 43877 | 8560262.92 |  | 0.75 | No | Not complete,workers on site,complains on access road,no gate,fenced
Kaeris ward admin office 2013/2014 | PUBLIC SERVICE, DECENTRALISED ADMINISTRATION AND DISASTER MANAGEMENT | 2013/2014 | N 03° 59.530' E 035° 28.742' | 9501930 | Kaeris |  | Kaeris |  |  |  | 9501930 | 0 | 1 | Yes | Operational ,toilet doors falling off,outside paint worn out,no staff in the offices,ward admin to take care of maintenance
Kaaleng/Kaikor ward admin office | PUBLIC SERVICE, DECENTRALISED ADMINISTRATION AND DISASTER MANAGEMENT |  | N 04° 31.662' E 035° 25.800' /600 M |  | Kaaleng/Kaikor |  | Kaikor | [5 empty] | 1 | No | Operational
Lapur ward admin office | PUBLIC SERVICE, DECENTRALISED ADMINISTRATION AND DISASTER MANAGEMENT | 2014/2015 | N 04° 16.724' E 035° 52.639' /387 M | 12900075.8 | Lapur |  | Lokitaung | Salnel Const Ltd | 43966 | 43877 | 9030053 |  | 0.7 | No | Work progress is okay,but rum too steep
Lakezone ward admin office | PUBLIC SERVICE, DECENTRALISED ADMINISTRATION AND DISASTER MANAGEMENT | 2014/2015 | N 04° 16.006' E 035° 45.420' /743 M | 13671516 | Lakezone |  | Nachukui | Lapur Trading & Inv Co Ltd | 43966 | 43877 |  |  | 0.8 | No | Wiring done,window works on going,no fence and gate,
ROADS, PUBLIC WORKS, ICT AND TRANSPORT
Nanam- Nakaleso road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N04⁰12.743' E034⁰33.683' ELV 560m | 5276840 | Nanam Ward |  | Nanam Village | Rabbi Building And Const Co Ltd | 1st july2015 | 31st july 2015 |  |  | 1 | Yes | Project complete
Loki junc- Lopiding_Trackmack Road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 5405600 | Lokichoggio Ward |  | Lokichogio | Dafobotaz Transport And Construction Ltd | 1st july2015 | 31st july 2015 |  |  | 1 | Yes | Project complete.
A1 Junc- DRA-HO Zion Hosp_AP Line Kiwanja Ndege water kiosk road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 13960896 | Lokichogio Ward |  | Lokichogio Centre | Chavez Tech Ea Ltd |  |  |  |  | 0 | Yes | The road is at its old stage no garging nor gravelling has been done on the said road
Lokichogio - Lochor Ekope Road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N04⁰12.388' E034⁰20.461' ELV 648m | 7973950 | Lokichogio Ward |  | Lokichogio Centre | Lorado Co Ltd | 20/06/15 | 42163 |  |  | 1 | Yes | Project complete.
Lomidat -Ekaburu Road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N04⁰08.145' E034⁰26.818' | 4469480 | Songot Ward |  | Lomidat | Kaliou Const Co LTD |  |  |  |  | 1 | Yes | Project complete.
Lopiding-Naritae Road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 1900000 | Nanam Ward |  | Naritae | Lelep Inv Ltd |  |  |  |  | 0 | No | The team could not find because the community was not aware.
Aposta-Naremeto-Teremkus Road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N04⁰02.828' E034⁰31.869' ELV 619m | 4000260 | Songot Ward |  | Naremeto | Lokichar Enterprise Ltd |  |  |  |  | 1 | Yes | Project complete
Aposta- lokangae road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N04⁰01.046' E034⁰32.908' ELV 606m | 5948132 | Songot Ward |  | Lokudule | Lizton LTD |  |  |  |  | 1 | Yes | Project complete.
Natiira-Nameitak- Namaanik road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N03⁰53.291' E034⁰33.691' ELV 677m | 4410670 | Kalobeyei Ward |  | Natiira | Napakin Const Co LTD |  |  |  |  | 1 | Yes | Done
A1 junc- Oropoi- NB uganda Road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N03⁰50.900' E034⁰34.822' ELV 685m | 11980480 | Kalobeyei Ward |  | Oropoi- Natiira | Akajere Const Co Ltd |  |  |  |  | 1 | Yes | Done but the rains have destroyed some parts
Nakoyo - ayanae elelea road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N03⁰44.383' E034⁰44.476' ELV 632m | 4175676 | Lopur Ward |  | Nakoyo | Kachodae Building |  |  |  |  | 1 | Yes | Bad work
Kangitesuroi- Kanakuring Road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N03⁰52.258' E034⁰56.104' | 5212344 | Lopur Ward |  | Kangitesroi | [5 empty] | 1 | Yes | Done
Nakitongo Lokipoto- Nawotom | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 4591860 | Letea Ward |  | Lokipoto | Loyoro Investment | 1st july 15 | 31st july 2015 |  |  | 1 | Yes | Was done and is complete
Lorengesinyen drift | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N03⁰02.716' E034⁰48.229' ELV 648m | 18441259.5 | Letea Ward |  | Lorengesinyen | Nanam Const Co Ltd | 27/07/15 | 28/10/15 |  |  | 1 | Yes | Project complete but drift submerged. Project manager to follow up.
Lopwarin Drift | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 18282765 | Nanam Ward |  | Lopwarin | Turkana Engineering Co Ltd |  |  |  |  | 0 | No | The drift has not been done as confirmed by the community. The team could not access site due to prosopis
A1 nadal village- moruangibuin road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 4616800 | Kakuma Ward |  | Moruangibuin | Lochorekope
Construction of Elelea - Katilia Road FY 2014/15 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N02⁰07.831' E036⁰07.040' | 9628000 | Katilia |  | Katilia - Elelea | Natoot Co Ltd |  |  | 6739600 | 2888400 | 1 | Yes | Project complete and the road is motorable.
Construction of Elelea Drift FY 2014/15 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N02⁰06.073' E036⁰09.149' | 6239988 | Katilia |  | Elelea | Natorobee Co Ltd |  |  | 4367991.6 | 1871996.4 | 1 | Yes | Project complete. There is need for embarkment down stream.
Routine maintenance of Lokwamosing/Kakongu Road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N02⁰00.628' E035⁰55.296' | 5868440 | Lokori/Kochodin |  | Lokwamosing - Kakongu | Turkana General Co Ltd |  |  | 4107908 | 1760532 | 1 | Yes | Project complete and the road is motorable.
Routine maintenance of Lopii - Kaaruko - Lokori Road FY 2014/15 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N02⁰03.820' E035⁰52.421' | 4200000 | Lokori/Kochodin |  | Lopii-Kaaruko-Lokori | Lowatat Contractors & Supplies Ltd |  |  | 2940000 | 1260000 | 1 | Yes | Project complete and the road is motorable.
Lotudae-Kaesamalit Road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 3125040 | Katilia |  | Lotudae-Kaesamalit | Jekanas Contractors & Supplies Company Ltd. |  |  | 2187528 | 937512 | 1 | Yes | The team could not locate the road but the information from the Department states that the project is complete.
Kamuge Drift | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 7004399 | Lomelo/Napeitom |  | Kamuge | Suguta Building Contractors & Transporters Co Ltd |  |  | 2101319.7 | 4903079.3 |  |  | The team could not visit the site for security reasons. However, information from the department states that the project is on-going.
Kamuge - Baragoi FY 2013/14 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 12876400 | Lomelo/Napeitom |  | Kamuge - Baragoi |  |  |  |  | 12876400 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Lokori - Paragati FY 2013/14 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 7934400 | Lokori/Kochodin |  | Lokori - Paragati |  |  |  |  | 7934400 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Lomelo - Kamuge FY 2013/14 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 11564040 | Lomelo/Napeitom |  | Lomelo - Kamuge |  |  |  |  | 11564040 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
Kamuge - Baragoi FY 2014/15 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 4902160 | Lomelo/Napeitom |  | Kamuge - Baragoi | Nakuru Machinery |  |  | 1960864 | 2941296 |  |  | The team could not visit the site for security reasons. The committee rocommended the team to visit the projects.
lokichar-loruth road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 03° 30.905' E 035° 13.350' /700 M | 3380000 | Nakalale |  | Loruth | Kalemchuch Contractors | 42044 | 42216 |  | 0 | 1 | Yes | Operational,signage done
Spot improvement Makutano-Lokitaung road A | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 03° 32.581' E 035° 14.874' /693 M | 24985820 | Nakalale |  | Makutano Lokitaung Road |  | 42044 | 42164 |  |  | 1 | Yes | Operational,signage done
losajait-naurugori road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 03° 30.751' E 035° 11.099' /680 M | 1641740 | Nakalale |  | Losajait | Natedelim Construction Ltd. | 42044 | 42259 |  |  | 1 | Yes | Opeational,signage done
nakapelekuruk-nadunga road 2014/2015 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 03° 43.391' E 035° 20.371' /656 M | 2847800 | Kaeris |  | Nakapelkuruk | Moru Edou Investment | 42044 | 42216 |  |  | 1 | Yes | Poorly done,entry ok,a few kilometres shoddy
Spot improvement Makutano-Lokitaung road A 2014/2015 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 04° 12.781' E 035° 28.136' /680 M | 25641800 | Nakalale |  | Makutano Lokitaung Road | Kalemchuch Contractors | 42044 | 42216 |  |  | 1 | Yes | Operational
kaaleng-kamothia-kibish road 2013/2014 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 04° 20.929' E 035° 33.280' /641 M | 23658707 | Kaaleng/Kaikor |  | Kaaleng | Kataboi Investmentd Limited |  |  |  |  | 1 | Yes | Operational
kaaleng-nakapelewoi road 2014/2015 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 04° 22.687' E 035° 30.636' /636 M | 1097360 | Kaaleng/Kaikor |  | Kaaleng/Nakapelewoi | Baross Investment | 42044 | 42269 |  |  | 0.8 | Yes | No levelling
routine maintenance of C47-Kaaleng road 2014/2015 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 04° 20.461' E 035° 36.632' /591 M | 1082472 | Kaaleng/Kaikor |  | Kaaleng Road | Napalakipor Investment Ltd | 42044 | 42216 |  |  | 0.9 | Yes | Operational
routine kachoda-riokomor road 2014/2015 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 04° 19.290' E 035° 40.458' /569 M | 2272788 | Lapur |  | Kachoda Rokomor Road | Jerman Contractors | 42044 | 42249 |  |  | 0.95 | Yes | Operational
routine maintenance of sasame-kabulokok-karioreng 2014/2015 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 04° 30.860' E 035° 44.838' /541 M | 1936620 | Lapur |  | Sasame | Jonice Investment Limited | 42044 | 42254 |  |  |  | Yes | Operational
kaikor-kangikala-lobur road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 04° 30.397' E 035° 25.229' /599 M | 3557996.8 | Lapur |  |  |  | 42044 | 41991 |  |  | 1 | Yes | Operational
riokomor-narengewoi road 2014/2015 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 04° 06.385' E 035° 43.217' /552 M | 2265480 | Lapur |  | Riokomor | Nangorikitoe Investment | 42044 | 42216 |  |  | 1 | Yes | Operational
nachukui-narikiotome-lokapetamoe road 2014/2015 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 04° 04.194' E 035° 53.067' /382 M | 1911888 | Lakezone |  | Nachukui | Lokwairia Enterprises Ltd. | 42208 | 42300 |  |  | 1 | Yes | Operational
nadunga-lochor atesiro road 2014/2015 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 03° 57.907' E 035° 15.452' /565 M |  | Kaeris |  | Nadunga | Kalemchuch Contractors | 41878 | 41970 |  |  | 0.95 | Yes | Operational
kaeris- kalopeta road 2014/2015 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 04° 22.687' E 035° 30.636' /614 M | 2744400 | Nakalale |  | Kapotea |  | 42044 | 42216 |  |  | 0.9 | Yes | Poorly done,operational
kokuro-lobur road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  | N 04° 44.255' E 035° 40.361' /424 M |  | Lapur |  | Kokuro |  | 42044 | 42216 |  |  | 1 | Yes | Operational
Lokamarinyang - Soya road 2014/2015 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 6722102 | Kibish |  |  | Inyang General Suppliers Ltd.
nakalale-nabuskaal-kairima road 2014/2015 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 3580920
Koyasa-Natelo-Natapar 2013/2014 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 9404700
Kataboi-Lopur 2013/2014 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 5215800
Kaimothia-kibish 2013/2014 | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 23658707 | Kibish
Kaikor-Lokiyoto-Loruth Road | ROADS, PUBLIC WORKS, ICT AND TRANSPORT |  |  | 3641889.8 | Kibish |  |  | Synchtolyte Gen.Contractors Ltd.